## Cover
Cutover Plan & Runbook
Stages 15-16 - task-level runbook, dress-rehearsal columns, go/no-go checklist.
How to use this workbook
- Tasks are sequenced by Day (T-7 through T+5). Each task has owner, predecessor, planned/actual time.
- Run THREE dress rehearsals before go-live. Capture actual durations and update planned times each rehearsal.
- Go/No-Go is a separate sheet with explicit criteria and named decision-makers.
- Hypercare task list (Stage 17) is on a separate sheet and runs for 4-8 weeks post go-live.

## Runbook
Cutover Runbook
Day-by-day task list. Update DR1/DR2/DR3 actual durations in each rehearsal.
Task # | Phase | Day | Task | Workstream | Owner | Predecessor | Planned start | Planned (mins) | DR1 actual (mins) | DR2 actual (mins) | DR3 actual (mins) | Status
1 | Pre-cutover | T-7 | Final defect status - confirm zero P1, max 5 P2, plan for residual P3/P4 | Test | Test Lead |  | Mon 09:00 | 60 |  |  |  | Pending
2 | Pre-cutover | T-7 | Communications wave 4 - final user notification, system unavailable window | Change | Change Lead |  | Mon 11:00 | 30 |  |  |  | Pending
3 | Pre-cutover | T-5 | Master data freeze in legacy ERP | Data | Data Mig Lead |  | Wed 17:00 | 30 |  |  |  | Pending
4 | Pre-cutover | T-3 | End-user access granted (security roles loaded in PROD) | Tech | SI Tech Lead | 1 | Fri 09:00 | 120 |  |  |  | Pending
5 | Pre-cutover | T-2 | Dress rehearsal 3 sign-off review | Programme | Programme Mgr |  | Sat 10:00 | 90 |  |  |  | Pending
6 | Cutover | T-1 | Legacy ERP enters read-only mode | Tech | SI Tech Lead | 3 | Fri 18:00 | 60 |  |  |  | Pending
7 | Cutover | T-1 | Final delta extract - all transactional sources | Data | Data Mig Lead | 6 | Fri 19:00 | 180 |  |  |  | Pending
8 | Cutover | T0 | Master data load (full set, post-freeze) | Data | Data Mig Lead | 7 | Sat 00:30 | 240 |  |  |  | Pending
9 | Cutover | T0 | Open balances load (AR, AP, GL, Inventory) | Data | Data Mig Lead | 8 | Sat 04:30 | 360 |  |  |  | Pending
10 | Cutover | T0 | Open transactional load (open POs, open SOs) | Data | Data Mig Lead | 9 | Sat 10:30 | 240 |  |  |  | Pending
11 | Cutover | T0 | Reconciliation - balance-by-balance vs legacy | Finance | Group FC | 10 | Sat 14:30 | 240 |  |  |  | Pending
12 | Cutover | T0 | Integration cutover - all 14 endpoints | Tech | SI Tech Lead | 10 | Sat 14:30 | 240 |  |  |  | Pending
13 | Cutover | T0 | Smoke test - top 20 business scenarios | Test | Test Lead | 12 | Sat 18:30 | 120 |  |  |  | Pending
14 | Cutover | T+1 | GO/NO-GO meeting #1 (Sun 06:00 UK) | Programme | Exec Sponsor | 11,12,13 | Sun 06:00 | 60 |  |  |  | Pending
15 | Cutover | T+1 | Open user access - wave 1 (super users) | Tech | SI Tech Lead | 14 | Sun 07:00 | 30 |  |  |  | Pending
16 | Cutover | T+1 | Super-user smoke test in PROD | Business | Process Owners | 15 | Sun 07:30 | 240 |  |  |  | Pending
17 | Cutover | T+1 | GO/NO-GO meeting #2 (Sun 14:00 UK) | Programme | Exec Sponsor | 16 | Sun 14:00 | 45 |  |  |  | Pending
18 | Go-live | T+2 | All-user access opened | Tech | SI Tech Lead | 17 | Mon 06:00 | 30 |  |  |  | Pending
19 | Go-live | T+2 | Command centre live (in-room war room) | Programme | Programme Mgr |  | Mon 07:00 | 600 |  |  |  | Pending
20 | Go-live | T+2 | First customer transaction processed end-to-end | Business | Process Owners | 18 | Mon 09:00 | 60 |  |  |  | Pending
21 | Go-live | T+3 | First payment run (AP) | Finance | AP Manager | 20 | Tue 14:00 | 120 |  |  |  | Pending
22 | Go-live | T+5 | Day-5 reconciliation review | Finance | Group FC |  | Fri 14:00 | 90 |  |  |  | Pending

## Go-NoGo
Go / No-Go Decision Record
Two scheduled decision points: Day 1 (post data load) and Day 2 (post super-user smoke test).
Criterion | Threshold | Owner | Status | Decision (Go/Hold/Stop) | Notes
Master & open balance loads complete | 100% rows loaded; reconciled to +/-0.5% | Data Migration Lead
Reconciliation result | GL TB difference <= £50k; AP/AR variance <= 1% | Group Financial Controller
Integrations live | All 14 in-scope integrations green for >=2 hrs | SI Technical Lead
Smoke test | 20/20 critical scenarios pass; 0 P1, 0 P2 | Test Lead
Security roles | All wave-1 users provisioned and tested | SI Technical Lead
Defect aging | 0 P1 open; <=3 P2 open with workaround | Test Lead
Hypercare team | Named, on-site, fully briefed | SI Programme Director
Communications | All-user comms wave 5 issued and acknowledged by BU heads | Change Lead
OVERALL DECISION | Decision-maker: Executive Sponsor on advice of Programme Mgr + SI Programme Director

## Hypercare (Stage 17)
Hypercare - Stage 17
4-8 week stabilisation. Track incidents, P1 mean time to resolve, and exit criteria.
Item | Owner | Frequency | Threshold | Wk1 | Wk2 | Wk3
P1 incidents open | SI Tech Lead | Daily | 0
P2 incidents open | SI Tech Lead | Daily | <= 5
Mean time to resolve (P1, hrs) | SI Tech Lead | Daily | <= 4 hrs
Mean time to resolve (P2, hrs) | SI Tech Lead | Weekly | <= 24 hrs
User adoption (% active users) | Change Lead | Weekly | >= 80% by Wk2; >= 95% by Wk4
Self-service tickets resolved at L1 (%) | Service Desk | Weekly | >= 60%
Period close on time? | Group FC | Monthly | Yes
Bank reconciliation variance | Treasury | Daily | <= £10k