Data Strategy

ERP Programme — cross-lifecycle. Migration approach, ownership, cleansing, mock loads, reconciliation, governance.

| Document | Data Strategy |
| --- | --- |
| Version | v1.0 (TEMPLATE) |
| Date | April 2026 |
| Owner | Business Architect (with Data Migration Lead from S10) |
| Classification | Programme Use |

# 1. Purpose

Establishes how data is treated across the ERP programme: master data scope, ownership, cleansing, migration, reconciliation, archiving and ongoing governance. Owned by the Business Architect through Pre-Programme; co-owned with the SI Data Migration Lead from Programme Setup & Mobilisation (S10) through cutover.

Most-common cause of go-live delay Data quality. The single best predictor of go-live slip is a mock load that surfaces data quality issues you didn't already know about. Get to mock load 1 early, treat it as a quality assessment (not a load test), and resource cleansing accordingly.

# 2. Data scope

| Data domain | Type | In scope? | Source system | Owner |
| --- | --- | --- | --- | --- |
| Chart of Accounts | Master | Yes — redesigned | Group Finance | Group FC |
| Customers | Master | Yes | Legacy ERP + CRM | Commercial |
| Suppliers | Master | Yes | Legacy ERP | Procurement |
| Items / SKUs | Master | Yes | Legacy ERP + PIM | Supply Chain |
| Bills of materials | Master | Phase 2 | MES | Operations |
| GL open balances | Transactional | Yes (open period) | Legacy ERP | Group FC |
| Open AR | Transactional | Yes (last 24 months) | Legacy ERP | AR Manager |
| Open AP | Transactional | Yes (last 24 months) | Legacy ERP | AP Manager |
| Open POs / SOs | Transactional | Yes (open only) | Legacy ERP | Procurement / Commercial |
| Inventory balances | Transactional | Yes (count at T-1) | Legacy ERP | Supply Chain |
| Historical transactions | Transactional | Archive only — read-only | Legacy ERP | IT |
| Employees / payroll | Master | No (HR remains in [system X]) | HR system | HR |

# 3. Data ownership

Each in-scope data domain has a named business Data Owner, accountable for: scope, quality rules, cleansing decisions, sign-off at each mock load, and post-go-live stewardship.

The Business Architect coordinates Data Owners. The SI Data Migration Lead executes the technical migration; the Data Owner owns the content.

# 4. Cleansing approach

Data cleansing operates in three modes:

Cleanse-in-source: preferred. Cleansing happens in the legacy system so the source-of-truth improves and the migration is a copy, not a transformation

Cleanse-in-flight: ETL transformations during migration. Acceptable for one-off mappings (e.g. Chart of Accounts redesign) but adds reconciliation complexity

Cleanse-in-target: a structured fix-up after load. Reserved for low-risk attributes; needs explicit sign-off because it bypasses normal data ownership

A dedicated cleansing pod (typically 2 FTE for 8–12 weeks pre-migration) is staffed for the highest-volume, lowest-quality domains identified in mock load 1.

# 5. Mock loads

Three mock loads minimum, spaced through Stages 13–14:

| Mock | When | Primary purpose | Exit criterion |
| --- | --- | --- | --- |
| Mock Load 1 | Build & Configuration (S13) mid | Quality assessment — surface data issues | Issue list captured; cleansing plan signed off |
| Mock Load 2 | Testing (S14) entry | Functional rehearsal — supports SIT | Functional reconciliation passes; SIT can use the data |
| Mock Load 3 | S14 late | Performance + cutover rehearsal | Load completes within cutover window; reconciliation passes |

Each mock load is followed by a Data Owner sign-off meeting. A failed mock load 3 is a Gate 2 stop condition — the Solution Design & Full Business Case (S12) FBC explicitly assumes data readiness at confirmed variance.

# 6. Reconciliation

Reconciliation is the 'data is correct' check. Three axes:

Row count — every record extracted is loaded (or rejected with a documented reason)

Sum / control total — financial values match to a defined tolerance (typically ±0.5%)

Functional walkthrough — sample of records walked through end-to-end by the Data Owner

Reconciliation reports are produced automatically by the SI's migration tooling (typically in Power BI or equivalent). Variances above tolerance halt the load until investigated.

# 7. Cutover data activities

Master data freezes at T-5 in the legacy ERP. Final delta extracts run T-1 through T0. Open-balance loads are the longest single activity in the cutover runbook (typically 6 hours). See the Cutover Plan workbook for sequenced detail.

# 8. Archiving & access to history

Historical transactions remain read-only in the legacy ERP for [N] months post go-live, after which they are archived to a long-term store. Users access history through a reporting view, not by querying the new ERP. This is a deliberate scope decision — migrating closed history into the new system multiplies migration effort with little business value.

# 9. Governance after go-live

From Hypercare & Stabilisation (S17) onwards, data ownership transitions from the programme to BAU:

Master data create / change goes through a workflow with the named Data Owner approving

Data quality KPIs are reported monthly to the operations forum

A Data Quality Council (Process Owners + IT) meets quarterly to triage emerging issues

Annual review of master data scope and cleansing rules at the optimisation forum (Optimisation & Maturity (S19))

# 10. Risks

| Risk | Mitigation |
| --- | --- |
| Mock load 1 surfaces material data quality issues | Resource cleansing pod ahead of mock load 1 — do not wait for the result |
| Reconciliation fails on open balances | Run reconciliation against legacy in parallel for 60 days post go-live |
| Data Owners not named | Block Discovery (S11) entry until named individuals confirmed |
| Source ERP API limits hit during cutover delta | Load-test extracts at peak rate before mock load 3 |
| Cleanse-in-flight transformation breaks audit trail | Document every transformation; SOX evidence pack signed off by Group Audit |