## Slide 1
DevOps & Agile Design
How-To Guide for ERP Programmes
Environments. Release management. CI/CD. Designing, building and testing epics, features and user stories.
Microsoft Dynamics 365 primary | with SAP S/4HANA & Oracle Fusion compare notes
Companion to the ERP Method | v1.0 | April 2026

## Slide 2
What this deck does — and who it's for
What it does
• A practical guide to running ERP delivery with engineering discipline
• Covers the four things every ERP programme needs but few do well
• Filled with examples — D365 (primary), SAP and Oracle (compare)
• Designed for teams without a dedicated DevOps function
Who it's for
• Programme Manager and SI Programme Director
• Solution Architect (Client + SI co-chair)
• Test Lead, SI Technical Lead, SI Functional Leads
• Anyone designing or accepting work in the build phase
Why this matters when you don't have DevOps
ERP programmes that lack DevOps discipline see the same failure modes — broken environment refreshes in mid-build, manual deployments that diverge between sandbox and production, defect-fix loops with no traceability, and user stories that can't be tested. This deck gives you a working operating model you can adopt without a dedicated DevOps engineer.
2 / 32
DevOps & Agile Design How-To | Introduction

## Slide 3
Five things this deck covers
1
Environments
How DEV / TEST / UAT / PROD work together; what to refresh and when
2
Release management
How configuration and code move from build to live, with traceability
3
CI/CD
Build and release pipelines — what to automate first, what to leave alone
4
Agile design
Writing epics, features, user stories — and acceptance criteria that test
5
Build/test loop
Sprints, definition of done, defect lifecycle — the day-to-day cadence
3 / 32
DevOps & Agile Design How-To | Introduction

## Slide 4
Section 1
Environment Strategy
DEV · TEST · UAT · PROD-MIRROR · PROD
4 / 32
DevOps & Agile Design How-To | Section 1: Environments

## Slide 5
Why environments matter
Get this wrong and every other DevOps practice gets harder
If you have too few
Build, test and UAT collide. Defect fixes destabilise testing. UAT testers see different behaviour each day. Cutover rehearsals can't run.
If you have too many
Refresh effort balloons. Configuration drift is unmanageable. SI cost rises with no benefit. Tier-3 sandboxes go unused.
If you don't refresh
Test data ages. Reconciliation becomes a fiction. Defects in old data are mistaken for design issues. Hypercare risk multiplies.
The minimum viable model for an ERP programme without dedicated DevOps:
5 environments — DEV (your build sandbox), TEST (Tier-2 for SIT), UAT (Tier-2 for UAT), PROD-MIRROR (Tier-3, refreshed from PROD for cutover rehearsals + perf testing), PROD.
5 / 32
DevOps & Agile Design How-To | Section 1: Environments

## Slide 6
Environment landscape — D365 Finance & Operations
What you get out of the box, what you typically buy, what flows where
DEV
Tier-1 (Cloud-Hosted or local VM)
X++ build, unit test
BUILD
Tier-1 (Build VM)
Pipeline runs here produces deployable package
TEST
Tier-2 Sandbox (Standard Acceptance — included)
SIT, integration test
UAT
Tier-2 Sandbox (Add-on — recommended)
Pre-UAT, UAT
PROD-MIRROR
Tier-3 Sandbox (Add-on — recommended)
Performance test Cutover rehearsals
PROD
Production (Included — multi-server)
Live system Deployed only via release pipeline
Code flows left → right via release pipeline. Data flows right → left via refresh (PROD copy with PII masking).
What's included vs add-on (D365 F&O)
• Standard subscription includes 1 PROD + 1 Tier-2 sandbox. Anything else is paid uplift.
• Build VM is your responsibility — typically a Cloud-Hosted Tier-1 in Microsoft Hosted Agent. Plan licence cost.
• Tier-3 PROD-mirror is the most-skipped purchase — and the most-regretted when cutover dress rehearsals break.
6 / 32
DevOps & Agile Design How-To | Section 1: Environments

## Slide 7
Refresh patterns — when, what, who
Refreshes are planned events, not panic moves
Default refresh cadence — copy this for your project unless you have a specific reason to change
Environment
Refreshed from
Cadence
Triggered by
Owner
DEV
Build VM (manual import)
Per developer / per feature
Developer
SI Functional Lead
TEST (SIT)
DEV → BUILD → release pipeline
Every sprint end / SIT cycle
Sprint close
Test Lead
UAT
PROD-MIRROR or freshly seeded Tier-2
Pre-UAT entry; UAT entry; Wk 2 of UAT
Test Lead
Test Lead
PROD-MIRROR
PROD (point-in-time copy)
Mock load 1, 2, 3; dress rehearsal 1, 2, 3
Programme Manager
SI Tech Lead
PROD
Never refreshed from elsewhere
Backups only
—
SI Tech Lead
Cardinal rule — every refresh is a freeze event. Lock the source for 24 hours. Communicate. Confirm completion. Run a smoke test. Only then unfreeze. Refresh failures during cutover are top-of-list root causes for go-live slips.
7 / 32
DevOps & Agile Design How-To | Section 1: Environments

## Slide 8
If you're not on D365 — equivalents in SAP & Oracle
Same problems, different vocabulary
Microsoft D365 F&O
Standard environments
DEV (Tier-1) → BUILD VM → TEST (Tier-2) → UAT (Tier-2) → PROD-MIRROR (Tier-3) → PROD
Promotion mechanism
Deployable package built in BUILD VM, uploaded to LCS Asset Library, deployed to environments
Tooling
LCS, Power Platform Admin Center (PPAC from 2026), Azure DevOps
Refresh
PPAC self-service refresh of Tier-2 from PROD
SAP S/4HANA
Standard environments
Sandbox → DEV → QAS (Quality Assurance) → PRD. Often plus a Golden client
Promotion mechanism
Transport requests (TRs) — released in DEV, imported to QAS then PRD
Tooling
Solution Manager (legacy) or Cloud ALM (current), ChaRM for Change Request Management
Refresh
System copy / client copy — heavier than D365 refresh; often needs Basis weekend
Oracle Fusion ERP
Standard environments
Test1 → Test2 → Stage → Production. Plus optional Dev1/Dev2 environments
Promotion mechanism
Configuration migration via Setup & Maintenance, OIC artefacts via Visual Builder Studio
Tooling
Oracle Cloud Console; Visual Builder Studio for OIC; OIC Pipeline for integration deploys
Refresh
Production-to-Test refresh on a quarterly cycle aligned with vendor patches
8 / 32
DevOps & Agile Design How-To | Section 1: Environments

## Slide 9
Section 2
Release & Transport Management
How configuration and code move from build to live
9 / 32
DevOps & Agile Design How-To | Section 2: Release management

## Slide 10
The promotion path — D365 F&O
Source-controlled, packaged, traceable. Production deploys are NEVER manual.
1
Developer commits
X++ + label files committed to feature branch in Azure DevOps Git
2
Pull request
Reviewed; CI build runs on the BUILD VM; quality checks pass
3
Merge to main
Code on main branch; nightly build produces a deployable package
4
Asset uploaded
Package uploaded to LCS Asset Library via Azure DevOps task
5
Deploy to TEST
Package deployed to Tier-2 TEST environment via release pipeline
6
Deploy to UAT
Same package deployed to UAT after SIT exit met
7
Release candidate
Successful UAT package marked as release candidate in LCS
8
Deploy to PROD
Self-service deploy to PROD — scheduled, not automated. Requires Environment Manager role
Microsoft's rule: PROD deployments cannot be fully automated.
You can automate up to PROD, but the actual PROD deploy is a self-service action triggered by an Environment Manager. This is a deliberate guard-rail. Don't try to circumvent it.
Source: Microsoft Learn — Apply updates to cloud environments; Deploy assets by using Azure Pipelines.
10 / 32
DevOps & Agile Design How-To | Section 2: Release management

## Slide 11
Branching strategy — keep it simple
GitFlow works for ERP. Trunk-based works too. Pick one and stick to it.
main
always deployable
release/r1.0
production hotfixes only
feature/p2p-approval
feature/data-mig-supplier
feature/intl-tax
Rules: short-lived feature branches (≤5 days). Sync from main daily. main is locked — only PRs. release branches only carry hotfixes.
11 / 32
DevOps & Agile Design How-To | Section 2: Release management

## Slide 12
Change control — what's in the audit trail
If you can't answer 'what's in PROD and why', you have a problem
Code
What X++ classes / extensions / objects changed
Azure DevOps Git history; PR descriptions
Configuration
What setup, parameters, security roles, workflows changed
Configuration log + Data Management Framework export per release
Data
What master data or mapping was loaded
Data Migration Lead's run log; reconciliation report attached
Approval
Who approved the deploy
PR reviewers + Environment Manager + Design Authority sign-off
Rollback
How to undo if it fails
Previous release candidate retained in Asset Library; rollback runbook
Linkage
Why this change was made
PR linked to Azure DevOps Work Item — Epic / Feature / User Story
12 / 32
DevOps & Agile Design How-To | Section 2: Release management

## Slide 13
Section 3
CI / CD & Automation
Build pipelines · release pipelines · what to automate first
13 / 32
DevOps & Agile Design How-To | Section 3: CI/CD

## Slide 14
Build pipeline — Azure DevOps for D365
What runs every time a developer pushes code
Trigger
Push to feature branch or PR to main
Get sources
Checkout from Azure Repos
Build
MSBuild compile X++ on BUILD VM
Quality gates
Best Practice checks label checks, syntax
Test
Unit tests run on BUILD VM
Package
Create deployable package (.zip)
Publish
Drop artefact to pipeline output
What you gain
• Every commit produces a tested, packaged, traceable artefact
• Failing builds visible to the team within 30 minutes
• No 'works on my machine' — the BUILD VM is the truth
• Audit trail: artefact ↔ commit ↔ work item ↔ user story
What you need
• Azure DevOps organisation with Dynamics 365 F&O extension
• A licensed BUILD VM (Tier-1 Cloud-Hosted or Microsoft-hosted agent)
• Power Platform Build Tools extension if using PPAC pattern
• Azure Key Vault for LCS credentials & secrets
• A user with Environment Manager role in LCS
14 / 32
DevOps & Agile Design How-To | Section 3: CI/CD

## Slide 15
Release pipeline — Azure DevOps tasks
Three tasks every D365 release pipeline runs
Stage 1
Authentication setup
MSAL.PS PowerShell module — installs the auth library on the agent
Outcome: Required once per agent per pipeline
Stage 2
Upload to LCS Asset Library
Dynamics Lifecycle Services Asset Upload task — pushes the deployable package up
Outcome: Asset shows up in LCS Asset Library, tagged with build number
Stage 3
Deploy to environment
Dynamics Lifecycle Services Asset Deployment task — fills LCS Environment ID, project ID, asset ID
Outcome: Sandbox environments fully automatable; PROD requires manual self-service trigger
Source: Microsoft Learn — Deploy assets by using Azure Pipelines (D365 F&O).
15 / 32
DevOps & Agile Design How-To | Section 3: CI/CD

## Slide 16
What to automate first — when you have no DevOps team
Pareto: 20% of automation gives you 80% of the benefit
1
Source control
All X++, all configuration exports, all DMF packages in Git. Day 1 of the project. No exceptions.
2
Build pipeline
CI build on every PR. Stops broken code reaching main.
3
Sandbox deploy automation
Deploy to TEST and UAT via release pipeline. Stops manual error.
4
Test data refresh automation
Power Platform Admin Center self-service refresh on a schedule. Stops stale data.
5
Release notes
Auto-generated from PRs / work items at deploy time. Stops 'what's in this release?' questions.
6
Automated regression
RSAT (Regression Suite Automation Tool) for top 50 scenarios. Worth the effort by Stage 14.
16 / 32
DevOps & Agile Design How-To | Section 3: CI/CD

## Slide 17
Power Platform pipelines — when D365 isn't the only target
If you have Power Apps or Power Automate flows in scope
Power Platform pipelines = ALM-as-a-service. Use them when Azure DevOps would be overkill.
Solution layering — the rule
• Develop in UNMANAGED solution in DEV environment
• Export as MANAGED for any non-DEV environment
• Microsoft now strongly enforces this — Managed Environments will be required for any pipeline target environments from Feb 2026
• Do not edit components directly in TEST/UAT/PROD — that creates an unmanaged layer that will block future imports
Two ALM patterns
Power Platform Pipelines (in-product)
• Configured in maker portal; no Azure DevOps needed
• Approval workflows + automated solution promote
• Best for citizen-developer-led builds
Azure DevOps + Power Platform Build Tools
• Full Azure DevOps pipeline with PowerShell tasks
• Best when you also need D365 F&O ALM in same project
• Recommended for full ERP programmes
Source: Microsoft Learn — Power Platform ALM, Pipelines overview, Solution concepts.
17 / 32
DevOps & Agile Design How-To | Section 3: CI/CD

## Slide 18
Section 4
Agile Design
How to design, build and test Epics, Features and User Stories
18 / 32
DevOps & Agile Design How-To | Section 4: Agile design

## Slide 19
Epic → Feature → User Story
Three levels. Each one tests at a different scale.
EPIC
A large business outcome — months
Example
Working capital efficiency through DSO reduction
Acceptance test
Acceptance = business outcome (KPI moved)
FEATURE
A coherent slice of capability — sprints
Example
Automated dunning workflow with credit limit enforcement
Acceptance test
Acceptance = capability is in production and used
USER STORY
A single behaviour — days
Example
AR clerk receives auto-generated dunning letter on day 31 past due
Acceptance test
Acceptance = automated test passes (Given / When / Then)
Get the level wrong and acceptance is impossible. A 'user story' that takes 6 weeks is a feature. A 'feature' that needs no design is a story.
19 / 32
DevOps & Agile Design How-To | Section 4: Agile design

## Slide 20
Writing user stories — the four-part formula
Role · Goal · Benefit · Acceptance criteria
The formula
AS A [role], I WANT [goal/action], SO THAT [benefit].
GIVEN [pre-condition], WHEN [action], THEN [outcome].
Worked example — P2P / requisition
AS A procurement manager
I WANT to submit a purchase requisition for items from a supplier catalogue
SO THAT approved orders are placed quickly and against negotiated rates.
Acceptance criteria (Gherkin)
GIVEN I am logged in as a procurement manager with an approval limit of £5,000
WHEN I submit a requisition for £4,800 from a catalogue supplier
THEN the requisition is auto-approved and a PO is generated within 60 seconds AND the supplier is notified by email.
20 / 32
DevOps & Agile Design How-To | Section 4: Agile design

## Slide 21
INVEST and Definition of Done
Two checklists every team needs on the wall
INVEST — a good user story is...
Independent — can be built without waiting on another story
Negotiable — the team can challenge / refine before commit
Valuable — delivers a concrete business benefit
Estimable — the team can size it
Small — fits in a sprint — typically 1-3 days
Testable — the acceptance criteria are unambiguous
Definition of Done — example
☐ Code merged to main with PR review and CI build pass
☐ Configuration captured in DMF / solution package
☐ Unit tests written and passing
☐ Acceptance test (Given/When/Then) automated where feasible
☐ SIT scenario added to the regression pack
☐ Documentation updated (process map / training material)
☐ Process Owner has reviewed in TEST environment
☐ Linked to Epic and Feature in Azure DevOps
21 / 32
DevOps & Agile Design How-To | Section 4: Agile design

## Slide 22
Worked example — full hierarchy
DSO reduction → Automated dunning → individual stories
EPIC — Reduce DSO from 58 to 42 days through automated dunning and credit enforcement [Benefit Owner: CFO]
FEATURE 1
Dunning workflow
Automated dunning letters sent on day 7/14/30/60 past due
FEATURE 2
Credit limit enforcement
Hard block on new orders when customer over credit limit
FEATURE 3
AR ageing dashboard
Real-time DSO and aged-debt KPI visible to finance leadership
Stories under Feature 1
• Story 1.1 — Auto-generate first dunning letter at day 7 past due
• Story 1.2 — Auto-generate second dunning letter at day 14 past due, copying credit controller
• Story 1.3 — Escalate to manual review at day 30; remove customer from auto-dunning list
• Story 1.4 — Configure dunning letter template with company branding
Stories under Feature 2
• Story 2.1 — Block new sales order when customer exceeds credit limit
• Story 2.2 — Allow override with credit-controller approval
• Story 2.3 — Email customer when block applied with reason
• Story 2.4 — Bulk credit-limit refresh from credit-bureau API
Stories under Feature 3
• Story 3.1 — Embed Power BI ageing report in workspace
• Story 3.2 — Daily refresh of DSO calculation
• Story 3.3 — Drill from KPI to customer detail
• Story 3.4 — Email digest to credit controllers daily
22 / 32
DevOps & Agile Design How-To | Section 4: Agile design

## Slide 23
Estimating — story points, not days
Why packaged-ERP teams should use story points the same way custom-build teams do
Why points work for ERP
• A 'standard' SO entry story might be 1 point
• An ATP-driven SO entry story might be 5 points
• A multi-currency, multi-warehouse SO entry story might be 13 points
• Same 'feature', vastly different effort
• Story points capture relative complexity better than calendar estimates
• Velocity (points per sprint) becomes the team's productivity metric
• Points are dimensionless — you can't argue 'a 5 should only be 3 days for me'
Fibonacci scale — recommended
1 Trivial — fits a few hours
2 Small — half a day-ish
3 Medium — a day
5 Larger medium — needs design discussion
8 Big — 2-3 days, may need splitting
13 Very big — almost certainly should be split
21+ Too big — break into smaller stories before sprint planning
23 / 32
DevOps & Agile Design How-To | Section 4: Agile design

## Slide 24
Section 5
The Build/Test Loop
Sprints, defect lifecycle, and the daily cadence
24 / 32
DevOps & Agile Design How-To | Section 5: Build/Test loop

## Slide 25
Sprint pattern — 2-week cadence
What happens when, who's in each event
Day 1
Mon
Sprint planning — story commit
1.5 hr
Whole team
Daily
every day
Standup
15 min
Team only
Day 5
Fri
Backlog refinement (mid-sprint)
1 hr
Team + Product Owner
Day 8
Wed
Pre-demo build review
30 min
Team + Solution Architect
Day 10
Fri AM
Sprint review / demo
1.5 hr
Team + Process Owners
Day 10
Fri PM
Retrospective
1 hr
Team only
Sprint reviews are a demo to Process Owners — not a UAT. Sign-off happens later, in the formal UAT cycle.
25 / 32
DevOps & Agile Design How-To | Section 5: Build/Test loop

## Slide 26
Defect lifecycle
Triage daily. Severity defines the response, not the noise level.
Open
Defect raised by tester
Triaged
Severity assigned, owner named
In Progress
Developer working on fix
Fixed in DEV
Awaiting deploy to TEST
Verify in TEST
Tester re-runs case
Closed
Tester signs off
Severity
Definition
Target fix
Escalation
P1 — Showstopper
Blocks testing; no workaround
24 hours
SteerCo if open >48 hrs
P2 — Major
Blocks part of testing
5 working days
SteerCo if open >10 wd
P3 — Minor
Has workaround
Sprint of identification
—
P4 — Cosmetic
Nice-to-have
Backlog
—
26 / 32
DevOps & Agile Design How-To | Section 5: Build/Test loop

## Slide 27
What a 'normal day' looks like in build phase
If everyone knows what they should be doing at 10am, you've got it right
09:00
Standup (15 min)
Each team member: yesterday, today, blockers
09:15
Build phase
Developers code. Testers run scripts. Functional Leads support.
11:00
Defect triage (Tues / Thurs only)
Test Lead + SI Functional Leads + Process Owner rep
12:00
Lunch
Yes, this is in the schedule. Eat away from the desk.
13:00
Build phase continues
15:00
Backlog refinement (Wednesdays)
30 min — Product Owner + Solution Architect
16:30
Pull request reviews
Everyone reviews open PRs by end of day
17:00
Day ends — CI build runs overnight
Defects in CI build raise notifications
27 / 32
DevOps & Agile Design How-To | Section 5: Build/Test loop

## Slide 28
Section 6
Putting It Together
A minimum viable DevOps for an ERP programme without a DevOps team
28 / 32
DevOps & Agile Design How-To | Section 6: Putting it together

## Slide 29
Minimum viable DevOps — what to do, in what order
If you do nothing else, do these eight things
Pre-Stage 10
Set up Azure DevOps
Organisation, project, Git repo, work item structure (Epic / Feature / User Story)
Stage 10
Set up source control
All X++ in main branch from day 1; no exceptions; SI commits go through PRs
Stage 10
Procure environments
1 BUILD VM + Tier-2 TEST + Tier-2 UAT + Tier-3 PROD-MIRROR
Stage 11
Build pipeline live
CI builds on every PR; failures block merge
Stage 12
Release pipeline live
Auto-deploy to TEST on main commit; manual deploy to UAT
Stage 13
Refresh schedule published
Refresh dates locked into the programme plan; communicated to all
Stage 14
RSAT regression suite
Top 50 critical scenarios automated; runs nightly
Stage 15
Cutover dress rehearsal automation
PROD-mirror refresh + cutover runbook executed end-to-end
29 / 32
DevOps & Agile Design How-To | Section 6: Putting it together

## Slide 30
Common pitfalls — and how to avoid them
Same mistakes show up on every programme. Look for these.
✕
Manual config in PROD — Configuration changes made in PROD by 'helpful' admins — drift breaks future imports.
Fix: Lock PROD config from Stage 16. All changes via release pipeline.
✕
'It works on my machine' — Developer's local environment differs from BUILD VM — code passes locally, fails in CI.
Fix: BUILD VM is the truth. If it fails CI, it's broken.
✕
Big-bang releases — Single huge release at end of Stage 13 — first deployable package is two months of work.
Fix: Deploy weekly to TEST from Stage 13. Find issues early.
✕
Stale environments — TEST environment hasn't been refreshed for 6 weeks — defects raised against ghost data.
Fix: Schedule refreshes; communicate; lock the schedule.
✕
UAT script defects — UAT testers find script defects rather than system defects — UAT calendar consumed by re-writes.
Fix: Pre-UAT exists for this. Don't skip it.
✕
No rollback plan — PROD deploy fails; team scrambles for 6 hours.
Fix: Every release has a rollback runbook tested in PROD-MIRROR.
30 / 32
DevOps & Agile Design How-To | Section 6: Putting it together

## Slide 31
Take-home checklist
Print this. Pin it on the wall. Tick it off.
☐ Six environments procured: DEV / BUILD VM / TEST / UAT / PROD-MIRROR / PROD
☐ Refresh schedule published, communicated, locked
☐ Azure DevOps Git repo with main branch protected — PR + CI build required to merge
☐ CI build pipeline running on every PR — fails to merge if build fails
☐ Release pipeline auto-deploys to TEST on main; manual to UAT, manual to PROD
☐ Power Platform pipelines configured if Power Apps / Flows in scope (managed solutions only in non-DEV)
☐ Work item hierarchy in place: Epic → Feature → User Story
☐ Every user story has Given/When/Then acceptance criteria
☐ Definition of Done agreed by team and posted visibly
☐ RSAT regression suite covers top 50 critical scenarios
☐ Defect tracker live with daily triage from start of SIT
☐ PROD deploy rollback runbook tested in PROD-MIRROR
☐ Cutover runbook executed end-to-end in 3 dress rehearsals
☐ All SI commits traceable: PR → work item → user story → acceptance criteria → release
31 / 32
DevOps & Agile Design How-To | Section 6: Putting it together

## Slide 32
Sources & further reading
Microsoft
• Environment planning — Finance & Operations: learn.microsoft.com/dynamics365/fin-ops-core/dev-itpro/organization-administration/environment-planning
• Best practices for ALM in Dynamics 365 applications: learn.microsoft.com/dynamics365/guidance/implementation-guide/application-lifecycle-management-product
• Deploy assets by using Azure Pipelines: learn.microsoft.com/dynamics365/fin-ops-core/dev-itpro/dev-tools/pipeline-deploy-asset
• Branching overview (X++): learn.microsoft.com/dynamics365/fin-ops-core/dev-itpro/dev-tools/branching
• Apply updates to cloud environments: learn.microsoft.com/dynamics365/fin-ops-core/dev-itpro/deployment/apply-deployable-package-system
• Power Platform pipelines overview: learn.microsoft.com/power-platform/alm/pipelines
• Move from unmanaged to managed solutions: learn.microsoft.com/power-platform/alm/move-from-unmanaged-managed-alm
Agile / user stories
• Mountain Goat Software — Epics, features, and user stories
• Scaled Agile Framework — Story
• TestQuality — Gherkin user stories acceptance criteria guide
• Cucumber — User story (Given / When / Then)
• Atlassian — Agile epics: definition, examples, and templates
End — produced for the ERP Method | v1.0 | April 2026
32 / 32
DevOps & Agile Design How-To | Sources