Enterprise AS-IS Assessment

Summary Report

Stages 1–2 · Pre-Programme Deliverable

Worked example: Northwind Industries Ltd

| Organisation | [Insert organisation name] |
| --- | --- |
| Date | [Insert date] |
| Document owner | Solution Architect (Client) |
| Reviewers | Sponsor; Business Architect |
| Sign-off | Executive Sponsor Group |
| Classification | Confidential — internal |

# Document control

Version history and approvals.

| Version | Date | Author | Approver | Status |
| --- | --- | --- | --- | --- |
| 0.1 | 12 Jan | S. Patel (Solution Architect) | — | Draft |
| 0.5 | 26 Jan | S. Patel | Business Architect | Working draft |
| 0.9 | 08 Feb | S. Patel | Sponsor | For review |
| 1.0 | 21 Feb | S. Patel | Executive Sponsor Group | Approved |

# Executive summary

State of the estate at a glance.

Northwind Industries operates 18 production sites across four brands, supported by six legacy ERP instances and an estimated 47 point-to-point integrations. The estate has grown by acquisition over fifteen years and shows the cost of that growth: duplicated master data, manual reconciliation between brands, and a finance close that takes nine working days. There is no single version of the customer, supplier or product.

Top three constraints and dependencies.

First, the central legacy ERP feeds eight downstream systems and cannot be retired in a single weekend cutover. Second, the regulatory reporting toolchain depends on month-end extracts that are themselves built on undocumented SQL views. Third, two of the four brands run on an unsupported platform whose vendor exits the market in eighteen months — that exit date sets the outer bound of the programme.

Capability gaps the new ERP needs to close.

Real-time stock visibility across sites, a single chart of accounts, supplier self-service, consolidated multi-brand customer reporting, and audit-grade traceability for finished goods. These are the capabilities the business has been working around with spreadsheets and after-the-fact reconciliation; they are not nice-to-haves.

AS-IS readiness for transformation.

Readiness is mixed. Finance and procurement leadership are ready and engaged. Operations is sceptical because of two prior failed implementations. IT capacity is the biggest constraint: the team running the estate today is the team that will deliver migration data to the new platform — they cannot do both at full intensity. The data is messier than leadership currently believes; we recommend a focused data-quality wave before Solution Design & Full Business Case (S12) design work begins.

Key risks and mitigations.

The single largest risk is attempting a big-bang cutover across all 18 sites; the dependency tree shows this is not feasible inside the vendor exit window. We recommend a multi-wave shape with finance and one pilot brand first, then the remaining three brands sequenced by complexity. Other top risks: master-data quality below threshold for migration, integration retirement schedule slipping, and operations change-fatigue if delivery drags.

# 1. Estate overview

This section is read alongside the companion deck “AS-IS Estate-on-a-Page.pptx”, which presents the same information as a single layered diagram. The layers below mirror the bands on that slide.

## Customers and markets

B2B retail accounts (62% of revenue) — 4,200 active accounts across UK and EU.

Distributor channel (24%) — 180 distributors, EDI-driven order intake.

Direct B2C (10%) — single brand only, web storefront on legacy platform.

Marketplaces (4%) — Amazon Business, eBay Business; manual SKU sync today.

## Channels

Web storefront (B2C) — bespoke build, ageing, no mobile parity.

EDI (distributors) — works, but every onboarding is a six-week custom project.

Sales rep mobile app — read-only quoting, no order capture in field.

Customer service phone and email — case management in a separate ticketing tool.

In-person trade desks at three sites — paper-based, scanned to email at end of day.

## Operating processes

Order-to-Cash — fragmented; pricing held in three systems and reconciled overnight.

Procure-to-Pay — central PO raising, brand-level GRN, no supplier portal.

Plan-to-Manufacture — MRP runs nightly per site; no cross-site optimisation.

Hire-to-Retire — payroll outsourced; HR system feeds finance via month-end CSV.

Record-to-Report — nine-day close; consolidation in spreadsheets.

Customer service — separate tooling, weak case-to-order linkage.

## Master data

Customers — 84,000 records across instances; ~12% suspected duplicates.

Products — 31,500 active SKUs; brand-level coding, no group hierarchy.

Suppliers — 6,800 records; ~18% duplicates; no centralised onboarding.

Employees — 2,600 records; HR system authoritative, but cost-centre coding drifts.

GL and cost centres — 1,247 GL codes, ~30% suspected duplicates from acquisition heritage.

## Platforms

Six legacy ERPs (one per acquired brand plus two regional instances) — RETIRE.

CRM (mid-market SaaS) — KEEP, but rationalise duplicate accounts.

Warehouse management at three large sites — KEEP, integrate cleanly.

HR information system — KEEP, integration to be re-pointed.

Finance reporting and consolidation tool — REPLACE with new ERP native reporting.

Bespoke pricing engine — RETIRE; logic moves into new ERP.

## Infrastructure

Two on-premise data centres (primary and DR) — exit planned by end of programme.

Hybrid cloud footprint, predominantly one major provider.

MPLS network linking sites; bandwidth adequate for cloud ERP cutover.

Identity managed centrally; SSO available for the new platform.

# 2. Integration landscape

This section is read alongside “AS-IS Integration-on-a-Page.pptx”. Northwind has 47 documented integrations; we expect ten to fifteen further undocumented ones to surface during Discovery (S11) discovery.

| Category | Count | Traffic volume | Reliability | Retirement candidates | Replacement strategy |
| --- | --- | --- | --- | --- | --- |
| Real-time interfaces | 12 | ~180k tx/day | Amber — two flaky | 4 | Re-platform onto new ERP API surface. |
| Batch interfaces | 23 | ~640 jobs/day | Amber — overnight window tight | 15 | Consolidate via new ERP scheduler; standardise file formats. |
| Manual / file-based | 12 | ~80 files/week | Red — error-prone | 10 | Eliminate via portal or self-service; retain two for third-party constraints. |

Per-category commentary.

Real-time interfaces — the CRM-to-ERP customer sync and the marketplace order intake are the two flaky links; both are first-wave fixes.

Batch interfaces — overnight window currently runs 22:00 to 04:30 with no slack. Any new ERP must reduce dependency on overnight reconciliation.

Manual file-based — the bank reconciliation upload and the payroll-to-finance journal post are the highest-risk in this category. Retire both.

# 3. Capability assessment

This section is read alongside “AS-IS Capability Heatmap.pptx”. Each business function is rated against target capability for the new ERP. The headline finding is that current capability is amber-or-red across the majority of the grid — this is normal for a pre-transformation estate but quantifies the size of the change.

## Finance

Top three capability gaps:

Multi-entity consolidation runs in spreadsheets — gap.

Chart of accounts not unified across brands — gap.

Audit trail patchy across legacy GLs — gap.

## Supply chain

Top three capability gaps:

No real-time stock visibility across sites — gap.

Demand planning sits outside ERP, in a standalone tool — gap.

Inter-site transfers reconciled manually — gap.

## Procurement

Top three capability gaps:

No supplier self-service portal — gap.

PO approval workflow inconsistent between brands — gap.

Spend analytics built quarterly in spreadsheets — gap.

## HR

Top three capability gaps:

Manager self-service partial; mobile not supported — gap.

Training records held outside core HR — gap.

Cost-centre coding drifts between HR and finance — gap.

## Operations

Top three capability gaps:

Shop-floor data capture paper-based at smaller sites — gap.

Cycle-time reporting weekly, not real-time — gap.

Quality records not linked to batch records — gap.

## Customer service

Top three capability gaps:

Cases not linked to orders or shipments — gap.

No single view of customer across brands — gap.

Returns process manual end-to-end — gap.

# 4. Dependencies and constraints

This section is read alongside “AS-IS Dependency Tree.pptx”. The tree groups systems into Retire, Replace and Keep, and shows what each one depends on or feeds.

## Legacy systems to retire

Six legacy ERPs (one per brand plus two regional instances) — together feed 31 of the 47 integrations.

Bespoke pricing engine — depends on legacy customer master; logic must be re-implemented before retirement.

Standalone consolidation spreadsheet stack — eliminated by new ERP native reporting.

Worked example: the legacy ERP at the Doncaster site feeds the WMS, the pricing engine, the consolidation tool, two EDI links, and the bank file generator. Retiring it is a six-system co-ordination, not a single switch.

## Systems that must remain

CRM — KEEP. Integration to be re-pointed to new ERP customer master.

Warehouse management at three large sites — KEEP. Re-implementing would breach operations risk appetite.

HR information system — KEEP. Re-point payroll and finance feeds.

Worked example: the WMS at the Birmingham distribution centre processes 28,000 lines a day; replacement is out of scope for this programme. Integration design must protect that throughput across cutover.

## Regulatory and compliance dependencies

HMRC Making Tax Digital — VAT submission flow must remain certified through and after cutover.

Industry traceability requirement — finished-goods batch records must be migrated, not summarised.

Data protection — legacy customer data with consent flags must migrate with consent intact, not re-set.

Worked example: traceability records currently sit in three places (legacy ERP, bespoke quality tool, paper batch sheets). Migration approach must consolidate without losing the audit chain.

# 5. Data quality snapshot

Headline state of master-data hygiene per domain. Numbers are first-pass estimates from initial profiling; S11 discovery will refine them.

| Domain | Volume | Known issues | Suspected duplicates | Action plan |
| --- | --- | --- | --- | --- |
| Customers | 84,000 | Inconsistent address formatting; six brand-local segmentations. | ~12% | De-duplicate; agree group segmentation; cleanse before migration. |
| Suppliers | 6,800 | Multiple records for same legal entity; bank details not centrally validated. | ~18% | Consolidate; validate bank details; introduce supplier portal. |
| Products | 31,500 SKUs | No group hierarchy; brand-local coding; obsolete SKUs not flagged. | ~8% | Build group hierarchy; flag and archive obsolete SKUs; re-code. |
| Employees | 2,600 | Cost-centre drift between HR and finance; training records external. | ~2% | Reconcile cost-centre mapping; bring training records inside HR scope. |
| GL and cost centres | 1,247 codes | Acquisition-era duplicates; descriptions inconsistent; mapping logic in spreadsheets. | ~30% | Build target chart of accounts; map old to new; retire duplicates. |

Recommendation: a focused data-quality wave runs in parallel with Solution Design and Full Business Case (S12). Migration readiness is the single best leading indicator of cutover risk and should be tracked from now.

# 6. Risks and recommendations

## Top five enterprise-architecture risks

| # | Risk | Impact | Mitigation |
| --- | --- | --- | --- |
| 1 | Big-bang cutover across all 18 sites | Programme failure; vendor exit window missed | Adopt multi-wave shape; finance and pilot brand first. |
| 2 | Master data quality below migration threshold | Cutover delayed; bad data in new platform | Data-quality wave starts in S12; clear pass/fail gates. |
| 3 | IT capacity stretched between run and migrate | Slippage; staff burnout | Backfill run-the-business roles; ring-fence migration team. |
| 4 | Integration retirement schedule slips | Old and new platforms run in parallel longer than planned | Retirement plan owned by Solution Architect; gated review each wave. |
| 5 | Operations change fatigue from prior failed projects | Adoption resistance; benefit realisation underperforms | Visible early wins in pilot brand; communications and engagement plan from S10. |

## Recommended sequencing

First: data quality, target chart of accounts, integration retirement plan.

Then: design and build for finance and pilot brand (single site, lowest complexity).

Then: roll out remaining three brands in waves, sequenced by complexity, not size.

Last: bespoke pricing engine retirement and final WMS re-pointing.

## Recommended programme shape

Multi-wave is recommended over single-wave. The dependency tree, vendor exit window and operations change appetite all point the same way: a pilot wave to prove the design, then three brand waves on a quarterly cadence. A single-wave shape would compress data, integration and change risk into one cutover weekend, which the AS-IS evidence does not support.

# Appendices

## A. Source data and bibliography

Legacy ERP system inventories (six instances; 2025 year-end exports).

Integration register maintained by the central IT team (last refresh: November 2025).

Group finance consolidation pack (Q4 2025).

Internal audit report on master-data quality (November 2025).

Vendor end-of-life notice for legacy platform supporting two brands.

Prior transformation programme post-mortems (2019, 2022).

## B. SMEs interviewed

| Name | Role | Domain covered |
| --- | --- | --- |
| [Name placeholder] | Group Financial Controller | Finance, consolidation, GL |
| [Name placeholder] | Director of Operations | Plan-to-Manufacture, sites, WMS |
| [Name placeholder] | Head of Procurement | Procure-to-Pay, suppliers |
| [Name placeholder] | Group HR Director | Hire-to-Retire, payroll interface |
| [Name placeholder] | Head of IT Architecture | Platforms, integrations, infrastructure |
| [Name placeholder] | Customer Service Manager | Customer service, returns, case-to-order |
| [Name placeholder] | Brand MD (pilot brand) | Operating model, change appetite |

## C. Methodology

Stakeholder interviews (1:1 and small-group) across the seven domains above.

System inventory review for each legacy ERP and surrounding tool.

Document review: organisation charts, prior post-mortems, audit findings, vendor notices.

Master-data profiling pass: volumes, duplicate rates, completeness against a defined quality rubric.

Workshops to validate the Estate-on-a-Page, the Integration-on-a-Page and the Capability Heatmap.