## Cover
Funding Envelope & Benchmark Costs
Stage 6 - Gate 1 input. Variance +/-30-40%.
Purpose
Establishes the cost side of the business case at programme initiation. Built bottom-up from benchmark unit rates and top-down from analogous programmes. Board-approved at Stage 6 to authorise market engagement (Stage 7). Refined to +/-30% with SI ROM at Stage 9, then to +/-10-15% in the Full Business Case at Stage 12.

## Inputs
Inputs & Assumptions
Blue cells = user inputs. All downstream costs flow from here.
| Programme size (band) | Mid (£100-500m revenue) | S/M/L
| Number of legal entities | 6 | Drives complexity multiplier
| Number of countries | 3 | Drives localisation effort
| Number of users (named) | 850 | Per-seat licence basis
| Number of business units / divisions | 4
| Number of integrations (in-scope) | 14 | Drives integration build effort
| Data sources to migrate | 3 | Each adds cleansing + reconciliation
| Programme duration (months) | 22 | From Stage 10 mobilisation to Stage 17 close
| Build phase duration (weeks) | 14 | Drives SI build pricing
| Region (cost band) | UK / Western EU | Affects daily rates

## Cost Build
Cost Build - Bottom Up
Categories per industry benchmarks. Variance band shown at the bottom.
Category | Sub-category | Driver | Unit | Quantity | Unit cost (£) | Cost (£)
Software | ERP licences (annual) | Named users x £/user | Year | 1 | 595000 | 595000
Software | Power Platform / add-ons | Per-app licences | Year | 1 | 85000 | 85000
Software | Sandbox / non-prod tier upgrades | 1 standard + 1 high-perf | Year | 1 | 110000 | 110000
Implementation | SI Build & Configuration | FTE-weeks x blended £ | Bundle | 1 | 2200000 | 2200000
Implementation | Data Migration | Per source x complexity | Bundle | 3 | 180000 | 540000
Implementation | Integrations | Per integration band | Each | 14 | 28000 | 392000
Implementation | Testing tooling + automation | Tool licences + setup | Bundle | 1 | 95000 | 95000
Implementation | Training & enablement (SI) | Train-the-trainer | Bundle | 1 | 140000 | 140000
Programme | Programme Manager (client) | Per month, 22 months | Month | 22 | 14000 | 308000
Programme | Business Architect (client) | Per month, 22 months | Month | 22 | 12000 | 264000
Programme | PMO + tooling | Tools + 1 PMO analyst | Bundle | 1 | 180000 | 180000
Programme | Change Management (client+ext) | FTE-weeks | Bundle | 1 | 320000 | 320000
Programme | Backfill of business SMEs | Avg 6 SMEs x 12 months | FTE-month | 72 | 9500 | 684000
Infrastructure | Cloud subscription consumption | Annual estimate | Year | 1 | 165000 | 165000
Infrastructure | Network / VPN / connectivity | Setup + run | Bundle | 1 | 60000 | 60000
Other | External assurance / Big-4 audit | Quality gate reviews | Bundle | 1 | 120000 | 120000
Other | Travel & expenses | 10% of SI build | % of SI | 0.1 | 2200000 | 220000
Contingency | Contingency (15% of build+programme) | Risk reserve | % | 0.15 |  | 971700
Funding Envelope (TOTAL) | [5 empty] | 7449700
Variance band (Stage 6: +/-30-40%)
Lower bound (-35%) | [5 empty] | 4842305
Upper bound (+35%) | [5 empty] | 10057095

## Phasing
Annual Phasing
Spread of cost over the 22-month programme.
Category | Year 0 (mob) | Year 1 (build/test) | Year 2 (deploy) | Year 3 (hypercare/BAU) | Total
Software | 39500 | 316000 | 237000 | 197500 | 790000
Implementation | 168350 | 2188550 | 841750 | 168350 | 3367000
Programme | 175600 | 878000 | 526800 | 175600 | 1756000
Infrastructure | 45000 | 78750 | 67500 | 33750 | 225000
Other | 34000 | 153000 | 119000 | 34000 | 340000
Contingency | 97170 | 485850 | 291510 | 97170 | 971700
TOTAL | 559620 | 4100150 | 2083560 | 706370 | 7449700