## Worked example
Funding Envelope Estimator (Stage 6) — Worked Example
AcmeWidget Ltd — Medium programme, ERP only, 16 months, Market rates, Moderate customisation
A. Input parameters
Programme size | Medium (4,500 days mid-point)
Pillars | ERP only (×1.00)
Duration | 16 months
Rate posture | Market (Senior £1,100 / Lead £800 / Specialist £650)
Customisation | Moderate (×1.00 effort)
B. Role-mix breakdown
Role group | Effort % | Days | Rate tier | Day rate | Cost
Programme Director / Programme Manager | 8% | 360 | Senior | 1100 | 396000
Project Managers | 7% | 315 | Lead | 800 | 252000
Solution Architects | 8% | 360 | Senior | 1100 | 396000
Functional Consultants | 30% | 1350 | Lead | 800 | 1080000
Developers | 15% | 675 | Specialist | 650 | 438750
Test team | 18% | 810 | Lead | 800 | 648000
Data team | 6% | 270 | Specialist | 650 | 175500
Change & Training | 5% | 225 | Lead | 800 | 180000
Cutover & Hypercare | 3% | 135 | Specialist | 650 | 87750
Subtotal | 100% | 4500 | — | — | 3654000
Contingency (10%) |  |  |  |  | 365400
Total (mid-point) |  |  |  |  | 4019400
C. Envelope range (±30–40%)
Low (×0.625) | 2512125
Mid-point | 4019400
High (×1.375) | 5526675
Reported envelope | £2.5m – £5.5m
Envelope basis: programme team & SI implementation (the contracted delivery team, at blended day-rates)
D. Headcount sanity-check
Role group | Days | Duration (months) | Working days/month | Implied FTE
Programme Director / Programme Manager | 360 | 16 | 19.3 | 1.17
Project Managers | 315 | 16 | 19.3 | 1.02
Solution Architects | 360 | 16 | 19.3 | 1.17
Functional Consultants | 1350 | 16 | 19.3 | 4.37
Developers | 675 | 16 | 19.3 | 2.19
Test team | 810 | 16 | 19.3 | 2.62
Data team | 270 | 16 | 19.3 | 0.87
Change & Training | 225 | 16 | 19.3 | 0.73
Cutover & Hypercare | 135 | 16 | 19.3 | 0.44
E. Citation
Rates published May 2026, reviewed periodically. Derived from IT Jobs Watch UK contract median day-rates for Programme Manager, Solution Architect, Functional Consultant and Developer roles, cross-referenced with Hays Salary Guide and Free-Work, and adjusted for senior D365 programme delivery context based on practitioner experience.
F. Caveat
Headcount is indicative. Some roles (e.g. 1 Business Architect per workstream, 1 SI Functional Lead per workstream) are fixed-per-workstream in practice and don't scale linearly with programme size.
G. Wider programme costs — outside the envelope (illustrative, verify with vendor)
Indicative software subscription (Microsoft Dynamics 365, 600 users, 25% on full licences)
Annual range (low) | 266400
Annual range (high) | 360000
Over 5 years (low) | 1332000
Over 5 years (high) | 1800000
Basis: D365 medium band — Full £130–170, Team Member £6–10 per user/month
H. Indicative 5-year cost — implementation + software
Low | 3844125
High | 7326675
Excludes infrastructure and internal client cost. Not a full total cost of ownership.
I. Backfill — indicative (your assumption)
2 FTE × £450/day × 309 working days (16 months, contractor cover) | 278100
Count only materially-seconded roles; ~half a role or less is usually absorbed internally.
J. Also budget separately (not estimated)
Infrastructure / hosting + paid vendor service tiers; internal client team's own time; integration tooling; optimisation backlog.
ERP + CRM adds its own user licences (e.g. D365 Customer Engagement) — not modelled; priced at Software Selection (S8).
K. Delivery cost split (of the role-mix subtotal £3,654,000)
SI implementation | 2178000
Programme team | 1476000
Indicative split — mixed roles shown on their predominant side.
Working-days basis: 19.3/month (net of annual leave & public holidays, ~232/yr — not the ~260 gross).
L. Indicative return — illustrative (your benefit, not the vendor's return)
Break-even annual benefit (to cover 5-yr cost) | 1117080
Illustrative annual benefit (example — replace with yours) | 1700000
5-year ROI % | 52
Net over 5 years | 2914600
Simple payback (years) | 3.3
Based on your Benefits Map (S2), not vendor returns. Benefits ramp after go-live; firmed at the Full Business Case (S12).

## Your programme
Funding Envelope Estimator (Stage 6) — Your Programme
Yellow cells are inputs. Adjust to size your own programme. All other cells are formula-driven.
A. Input parameters
Programme size — mid-point (days) | 4500
Pillars multiplier | 1
Customisation multiplier | 1
Rate posture multiplier | 1
Duration (months) | 16
Total effort (days) — derived
Base day-rates (Market)
Senior | 1100
Lead | 800
Specialist | 650
B. Role-mix breakdown
Role group | Effort % | Days | Rate tier | Day rate | Cost
Programme Director / Programme Manager | 8% |  | Senior
Project Managers | 7% |  | Lead
Solution Architects | 8% |  | Senior
Functional Consultants | 30% |  | Lead
Developers | 15% |  | Specialist
Test team | 18% |  | Lead
Data team | 6% |  | Specialist
Change & Training | 5% |  | Lead
Cutover & Hypercare | 3% |  | Specialist
Subtotal |  |  | — | —
Contingency (10%)
Total (mid-point)
C. Envelope range (±30–40%)
Low (×0.625)
Mid-point
High (×1.375)
Envelope basis: programme team & SI implementation (the contracted delivery team)
D. Headcount sanity-check
Role group | Days | Duration (months) | Working days/month | Implied FTE
Programme Director / Programme Manager |  |  | 19.3
Project Managers |  |  | 19.3
Solution Architects |  |  | 19.3
Functional Consultants |  |  | 19.3
Developers |  |  | 19.3
Test team |  |  | 19.3
Data team |  |  | 19.3
Change & Training |  |  | 19.3
Cutover & Hypercare |  |  | 19.3
E. Citation
Rates published May 2026, reviewed periodically. Derived from IT Jobs Watch UK contract median day-rates for Programme Manager, Solution Architect, Functional Consultant and Developer roles, cross-referenced with Hays Salary Guide and Free-Work, and adjusted for senior D365 programme delivery context based on practitioner experience.
F. Caveat
Headcount is indicative. Some roles (e.g. 1 Business Architect per workstream, 1 SI Functional Lead per workstream) are fixed-per-workstream in practice and don't scale linearly with programme size.
G. Wider programme costs — software (illustrative; enter bands for your platform/size)
Users / employees | 600
Share on full licences | 25%
Full licence £/user/month — low | 130
Full licence £/user/month — high | 170
Light licence £/user/month — low | 6
Light licence £/user/month — high | 10
(D365 Full: small £150–200 / medium £130–170 / large £100–140; Team Member £6–10. SAP/Oracle/Workday per Vendor & Platform tab.)
Software annual — low
Software annual — high
Software 5-year — low
Software 5-year — high
H. Indicative 5-year cost — implementation + software
Low
High
Excludes infrastructure + internal client cost. Not a full TCO.
I. Backfill — indicative (your assumption)
Internal FTE backfilled | 2
Backfill day-rate (£/day) | 450
Working days (duration × 19.3)
Backfill cost (contractor cover)
Recruitment alternative (one-off): FTE × cost-per-hire (e.g. £11,000). Count only materially-seconded roles.
J. Also budget separately (not estimated)
Infrastructure/hosting + vendor service tiers; internal client team's own time; integration tooling; optimisation backlog. CRM adds its own licences (priced at S8).
K. Delivery cost split (of the role-mix subtotal)
SI implementation
Programme team
Indicative split — mixed roles shown on their predominant side.
Working-days basis: 19.3/month (net of leave & holidays, ~232/yr — not the ~260 gross).
L. Indicative return — illustrative (your benefit, not the vendor's return)
5-year cost mid-point
Break-even annual benefit
Expected annual benefit (your figure) |  | ← enter your figure; leave blank for break-even only
5-year ROI %
Net over 5 years
Simple payback (years)
Replace the expected-benefit cell with your Benefits Map (S2) figure. Not a vendor projection; benefits ramp after go-live; firmed at S12.
Note on B5: Small 2,000 / Medium 4,500 / Large 8,000 — or override with custom value
Note on B6: ERP only = 1.00; ERP + CRM = 1.25
Note on B7: Light 0.90 / Moderate 1.00 / Heavy 1.15
Note on B8: Conservative 0.85 / Market 1.00 / Premium 1.15