Programme Charter

ERP Programme — Programme Setup & Mobilisation (S10) anchor document. Establishes scope, governance, sponsorship, success criteria and gates.

| Document | Programme Charter |
| --- | --- |
| Version | v1.0 (TEMPLATE) |
| Date | April 2026 |
| Owner | Programme Manager (on behalf of Executive Sponsor) |
| Classification | Programme Use |

# 1. Purpose of this document

This Charter is the formal authority for the ERP Programme. It is signed by the Executive Sponsor at Stage 10 (Programme Setup & Mobilisation) once the Funding Envelope (Funding Envelope & Benchmark Costs (S6)) has been approved at Gate 1 and the SI ROM (SI Selection with ROM Pricing (S9)) has been secured. It is the basis on which the programme team is mobilised and on which all subsequent governance (Steering Committee from Solution Design & Full Business Case (S12), Design Authority from S9) operates.

This Charter is re-baselined once — at S12, when the Full Business Case is confirmed at ±10–15% variance and the board commits to build (Gate 2). After that point, scope changes are managed through the change-control process, not by reissuing the Charter.

# 2. Programme context

## 2.1 Strategic rationale

[Insert business context — typically 2–3 paragraphs setting out why ERP transformation is needed now: legacy ERP end-of-life dates, M&A history, regulatory pressure, competitive cost-to-serve, growth ambition. This text should be a précis of the Vision & Strategy (S1) Vision & Strategy document.]

## 2.2 Strategic outcomes (top-level)

The programme will deliver against the following strategic outcomes, each of which has at least one named Benefit Owner (see Benefits Map):

Working capital efficiency — DSO and inventory reduction

Operational productivity — finance close speed, AP automation

Compliance and audit — SoD enforcement, automated controls

Decision support — real-time management reporting

Platform consolidation — retire legacy ERP and tactical systems

# 3. Programme structure

This programme follows the ERP Method, which structures the lifecycle into six governance phases and twenty stages (Stage 0–19), nominally 18–24 months end-to-end with c.8–10 days of cumulative executive commitment.

| Phase | Stages | Duration (typical) |
| --- | --- | --- |
| Pre-Programme | Stages 0–5 | 12 weeks |
| Selection | Stages 6–9 | 17–24 weeks |
| Setup & Design | Stages 10–12 | 12–18 weeks |
| Build & Test | Stages 13–14 | 14–24 weeks |
| Deploy | Stages 15–17 | 8–14 weeks |
| Post-Programme | Stages 18–19 | 12–26 weeks formal, then ongoing |

# 4. Scope

## 4.1 In scope

Core ERP — General Ledger, AP, AR, Fixed Assets, Intercompany

Procure-to-Pay end-to-end (requisition, PO, GR, invoice, payment)

Order-to-Cash end-to-end (sales order, ATP, fulfilment, invoicing, collection)

Inventory & supply planning (MRP, replenishment, WMS for two sites in Phase 1)

Reporting & analytics (embedded BI, group consolidation pack)

Migration of [N] legal entities across [N] countries

Integration to [N] in-scope systems (HR, CRM, Bank, Tax engine, EDI)

## 4.2 Out of scope

HR / payroll (remains in [system X] in Phase 1)

Manufacturing execution (deferred to Phase 2 roadmap)

Field service mobile app (deferred to Phase 2 roadmap)

Master data governance tooling (handled as a separate workstream outside this programme)

## 4.3 Phasing

Phase 1 covers the entities and processes above and is the subject of this Charter. Phase 2 (manufacturing execution, field service, additional countries) is out of scope of this Charter and will be sponsored separately following Benefits Realisation & Review (S18) benefits review.

# 5. Governance

Two real board gates Gate 1 (S6): Funding Envelope approved, ±30–40% variance — authorises Selection. Gate 2 (S12): Full Business Case confirmed, ±10–15% variance — commits to build. Stages 7, 9 and 13 are NOT gates and must not be presented as such.

| Body | Active period | Cadence | Decisions owned |
| --- | --- | --- | --- |
| Executive Sponsor Group | Phase 1 Wk1 throughout | As required + every gate | Gate 1, Gate 2, escalations, scope change >5% |
| Steering Committee | Stages 3–18 (BAU at 19) | Monthly | RAID, plan, budget within tolerance, sign-off on stage closures |
| Design Authority | End of S9 through Hypercare & Stabilisation (S17) | Bi-weekly | Solution decisions, design exceptions, deviation from standard |

# 6. Roles & accountabilities

Full-lifecycle roles: Executive Sponsor, Programme Manager, Business Architect.

Phase-specific roles (per ERP Method):

| Role | Joins at | Notes |
| --- | --- | --- |
| Solution Architect (Client + SI co-chair) | S9 | Co-chair of Design Authority |
| Project Managers (per workstream) | S10 | NOT staffed before S10 — there are no workstreams |
| Process Owners | S10 | Named individuals from the business |
| Change Lead | S10 | Ramps with adoption through deploy |
| Client Test Manager | Discovery (S11) | Owns SIT, UAT, regression and performance testing |
| Benefit Owners | Stage 2 (named); active S18 | On the hook for benefit realisation |
| SI roles (PD, SA, FL, TL, DM, SM) | S10 | Onboarded against signed MSA |

# 7. Funding & business case

The business case matures across four checkpoints. This Charter operates within the S6 Funding Envelope (±30–40%) until the Full Business Case is confirmed at Stage 12 (±10–15%). Any forecast that breaches the S6 upper bound triggers an ESG decision before continuing.

| Stage | Business case milestone | Variance | Authority |
| --- | --- | --- | --- |
| 2 | Benefits Map and ROI Driver Matrix | n/a | Sponsor |
| 6 | Funding Envelope (Gate 1) | ±30–40% | Board |
| 9 | SI ROM added | ±30% | Sponsor |
| 12 | Full Business Case (Gate 2) | ±10–15% | Board |

# 8. Success criteria

The programme is deemed successful when ALL of the following are achieved:

Go-live without a P1 incident open at T+5 working days

Period-end close completed in the new system within target working days for the first three closes

User adoption ≥ 95% by end of hypercare (Wk 8 post go-live)

Benefits tracked and reported quarterly from S18 against the ROI Driver Matrix

Total programme cost within ±10% of the S12 Full Business Case

Zero SOX exceptions in the first audit cycle post go-live

# 9. Risk overview

Top-of-mind risks at Charter sign-off (full register held in the RAID Log):

| Risk | Likelihood | Impact | Owner |
| --- | --- | --- | --- |
| Process Owners not named in time for Discovery | Medium | High | Programme Manager |
| Master data quality below threshold for mock loads | High | High | Data Migration Lead |
| UAT run by Process Owners rather than independent testers | Medium | High | Client Test Manager |
| SI firm pricing exceeds S9 ROM upper bound | Medium | High | Executive Sponsor |
| Hypercare resourcing not contractually locked | Medium | High | SI Programme Director |

# 10. Sign-off

| Role | Name | Date | Signature |
| --- | --- | --- | --- |
| Executive Sponsor |  |  |  |
| Programme Manager |  |  |  |
| CFO |  |  |  |
| CIO |  |  |  |
| Business Architect |  |  |  |