## Cover
RACI Matrix - Full Lifecycle
Roles x Stages 0-19 across all six governance phases
Reading the matrix
R - Responsible: Does the work. Multiple Rs allowed.
A - Accountable: Owns the outcome. Exactly ONE A per activity. Cannot be delegated.
C - Consulted: Two-way conversation before decision. Subject-matter input.
I - Informed: One-way notification after decision.
Method rules honoured in this matrix
- Project Managers appear from Stage 10 onwards (per workstream). They are NOT staffed in Pre-Programme or Selection - there are no workstreams yet.
- Solution Architect (Client + SI co-chair) appears from Stage 9.
- Process Owners and Change Lead appear from Stage 10.
- Test Lead appears from Stage 11.
- Benefit Owners are named at Stage 2 and most active in Stage 18 reporting.
- SI roles join from Stage 10.
- Stage 6 and Stage 12 are the only two true board gates. Stage 6 = proceed; Stage 12 = commit to build (Final Investment Decision).

## RACI by Stage
RACI by Stage
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Role | S0 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19
| Problem / Opportunity | Vision & Strategy | Value Definition & Case for Change | Design Governance & Sponsorship | Execution Enablement | Benefits & Continuous Alignment | Funding Envelope * Gate 1 | Market Engagement & RFI | Software Selection | SI Selection (ROM) | Programme Setup & Mobilisation | Discovery | Solution Design & FBC * Gate 2 | Build & Configuration | Testing | Cutover Planning | Deployment & Go-Live | Hypercare & Stabilisation | Benefits Realisation & Review | Optimisation & Maturity
Executive Sponsor | A | A | A | A | A | A | A | C | C | A | C | C | A | I | I | I | A | C | A | C
Programme Manager | R | R | R | R | R | R | R | R | R | R | A | A | R | A | A | A | R | A | R | R
Business Architect | R | R | R | C | R | R | C | R | R | C | R | R | R | C | C | C | C | C | R | R
Benefit Owners |  |  | R | C | C | R | C | I | I | I | C | C | C | I | C | C | C | C | R | R
Project Managers (per workstream) | [10 empty] | R | R | R | R | R | R | R | R
Process Owners | [10 empty] | C | R | R | R | C | R | C | R | R | R
Change Lead | [10 empty] | R | R | R | R | C | R | R | R | C | R
Solution Architect (Client+SI) | [9 empty] | R | R | R | R | R | C | C | C | C |  | C
Test Lead | [11 empty] | R | C | R | R | C | C | C
SI Programme Director | [10 empty] | R | R | R | R | R | R | R | R |  | C
SI Functional Leads | [11 empty] | R | R | R | R | R | R | R |  | C
SI Technical Lead | [11 empty] | R | R | R | R | R | R | R |  | C
SI Data Migration Lead | [11 empty] | R | R | R | R | R | R | C
Steering Committee |  |  |  | C | C | C | A | A | A | A | C | C | C | C | C | C | C | C | A
Executive Sponsor Group | I | I | I | I | I | I | A | I | I | I | I | I | A | I | I | I | A | I | I | I
Design Authority | [9 empty] | A | C | A | A | A | A | A | A | A