## Cover
RAID Log
Risks - Assumptions - Issues - Dependencies
Purpose
The RAID log is the operational record of risks, assumptions, issues and dependencies across the ERP programme. It is the single source of truth for the Steering Committee and Design Authority. The Programme Manager owns the log; workstream leads update their items weekly; the SteerCo reviews top items monthly.
How to use this workbook
- Risks: Anything that COULD happen and would affect cost / time / scope / benefit. Score = Likelihood x Impact (1-5 each).
- Assumptions: Anything we are taking as true, that we have not yet verified. Convert to a Risk if it is high-impact and unproven.
- Issues: Something that HAS happened and is causing impact now. Move from Risk to Issue when it has materialised.
- Dependencies: Anything we need from another programme, function, vendor or third party. Track inbound and outbound.
- Heat Map: Visual 5x5 grid showing where risks sit. Refreshed automatically from the Risks sheet.
Severity scales
Score | Likelihood | Impact
1 | Rare (<10%) | Negligible - absorbed in contingency
2 | Unlikely (10-30%) | Minor - slips one workstream by <2 weeks
3 | Possible (30-60%) | Moderate - slips programme by <4 weeks or <5% cost
4 | Likely (60-85%) | Major - slips programme by 4-8 weeks or 5-15% cost
5 | Almost certain (>85%) | Severe - Gate-stopping, viability of programme threatened

## Risks
Risks
Score = Likelihood x Impact (1-5 each). RAG = Red >=15, Amber 8-14, Green <=7.
ID | Date raised | Phase / Stage | Workstream | Risk description | Likelihood (1-5) | Impact (1-5) | Score | RAG | Owner | Mitigation / response | Target close date | Status
R-001 | 2026-01-15 | Stage 11 - Discovery | Solution | Process Owners not yet named; Discovery workshops at risk of being attended by deputies, leading to rework in Stage 12. | 3 | 4 | 12 | Amber | Programme Manager | Sponsor letter to BU heads requesting nominations by 31-Jan; escalate to ESG if not closed. | 2026-01-31 | Open
R-002 | 2026-02-02 | Stage 13 - Build | Data | Master data quality in legacy ERP is below 70% completeness on supplier records; cleansing effort risks slipping mock load 1. | 4 | 4 | 16 | Red | Data Migration Lead | Stand up data cleansing pod (2 FTE) for 8 weeks; cut over to source-of-truth in legacy by 15-Mar. | 2026-03-15 | Open
R-003 | 2026-02-18 | Stage 14 - Testing | Test | UAT being run by Process Owners rather than independent testers - risks confirmation bias and incomplete coverage. | 3 | 5 | 15 | Red | Test Lead | Move UAT to dedicated business testers per ERP Method; Process Owners sign off but do not execute. | 2026-03-30 | Open
R-004 | 2026-03-05 | Stage 12 - FBC | Commercial | SI ROM at Stage 9 was +/-30%; firm SI pricing for Stage 12 trending 18% above ROM, threatens Gate 2. | 4 | 5 | 20 | Red | Executive Sponsor | Negotiate scope re-baseline; bring forward FBC review with SI; ESG decision before Gate 2. | 2026-04-15 | Open
R-005 | 2026-03-12 | Stage 17 - Hypercare | Operations | Hypercare resourcing not booked - SI proposing to pull people to next engagement on Day 8. | 3 | 4 | 12 | Amber | SI Programme Director | Lock hypercare team in MSA; named individuals; 8 weeks minimum. Escalate via SteerCo if not in contract. | 2026-04-30 | Open

## Assumptions
Assumptions
Anything taken as true that has not yet been verified. Convert to Risk if material and unproven.
ID | Date raised | Phase / Stage | Workstream | Assumption | Validation approach | Validation by (date) | Owner | Status
A-001 | 2026-01-10 | Stage 10 - Mobilisation | Programme | SI Programme Director and Solution Architect remain on-engagement through Stage 17 hypercare. | Confirmed by name in MSA Schedule 4; ratify at first SteerCo. | 2026-02-01 | Programme Manager | Open
A-002 | 2026-01-22 | Stage 11 - Discovery | Process | Existing legacy ERP can run in parallel for 60 days post go-live to support reconciliation. | IT operations confirm dual-run capacity and licence implications. | 2026-02-15 | Business Architect | Open
A-003 | 2026-02-05 | Stage 13 - Build | Data | Source ERP API rate limits are sufficient for delta extracts during cutover weekend. | Data Migration Lead to load-test extracts at peak rate. | 2026-03-01 | Data Migration Lead | Open
A-004 | 2026-02-12 | Stage 14 - Test | Test | Business UAT testers will be released full-time for 4 weeks of UAT. | BU heads confirm via signed RACI; backfill arrangements in place. | 2026-02-28 | Change Lead | Open

## Issues
Issues
Something that HAS happened and is causing impact now. Severity = High / Medium / Low.
ID | Date raised | Phase / Stage | Workstream | Issue description | Severity | Impact statement | Owner | Resolution | Target close | Status
I-001 | 2026-02-20 | Stage 13 - Build | Integration | Sandbox refresh from production failed twice; build environment unavailable for 5 working days. | High | Build slipped 5 days; mock load 1 at risk. | SI Technical Lead | Microsoft support ticket raised (sev A); refresh succeeded on attempt 3 with manual cache clear. | 2026-02-27 | Closed
I-002 | 2026-03-08 | Stage 14 - Test | Test | Defect aging - 14 P2 defects open >10 working days, exit criteria threshold breached. | High | SIT exit slipping 1 week; UAT start at risk. | Test Lead | Daily defect triage; SI stood up two extra developers; SteerCo informed. | 2026-03-22 | Open

## Dependencies
Dependencies
Inbound (we need from others) and outbound (others need from us). Track owners on both sides.
ID | Date raised | Phase / Stage | Direction | Description | From (party) | To (party) | Required by | Owner (our side) | Status | Notes
D-001 | 2026-01-20 | Stage 11 | Inbound | Chart of accounts redesign signoff required from Group Finance. | Group Finance | ERP Programme | 2026-02-15 | Business Architect | Open | On Group Finance steering agenda 12-Feb.
D-002 | 2026-02-10 | Stage 13 | Inbound | AD/Entra ID groups for security roles must be created by Corporate IT. | Corporate IT | ERP Programme | 2026-03-01 | SI Technical Lead | Open
D-003 | 2026-03-02 | Stage 15 | Outbound | Cutover blackout period to be communicated to Customer Service Centre 4 weeks ahead. | ERP Programme | Customer Service Centre | 2026-04-01 | Change Lead | Open | Comms plan v0.3

## Heat Map
Risk Heat Map
5x5 Likelihood x Impact. Counts pulled live from the Risks sheet.
| Impact --> | 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Severe
Likelihood | 5 Almost certain | 0 | 0 | 0 | 0 | 0
| 4 Likely | 0 | 0 | 0 | 1 | 1
| 3 Possible | 0 | 0 | 0 | 2 | 1
| 2 Unlikely | 0 | 0 | 0 | 0 | 0
| 1 Rare | 0 | 0 | 0 | 0 | 0
Legend:
| Red | Score 15-25 - escalate to ESG
| Amber | Score 8-14 - manage actively at SteerCo
| Green | Score 1-7 - monitor at workstream level