Risk Management Plan

ERP Programme — process, severity scales, escalation. Companion document to the RAID Log.

| Document | Risk Management Plan |
| --- | --- |
| Version | v1.0 (TEMPLATE) |
| Date | April 2026 |
| Owner | Programme Manager |
| Classification | Programme Use |

# 1. Purpose

Defines how risks are identified, assessed, owned, mitigated, escalated and closed across the ERP Programme. Operates with the RAID Log workbook (which is the operational artefact). This document is approved by the Steering Committee at Solution Design & Full Business Case (S12).

# 2. Process

1. IDENTIFY — workstream leads raise risks weekly; programme members raise as soon as identified. Sources include workshops, standups, defect triage, third-party advice and audit findings.

2. ASSESS — Likelihood (1–5) × Impact (1–5) = Score (1–25). Scoring is done by the risk owner with challenge from the Programme Manager. RAG: Red ≥ 15, Amber 8–14, Green ≤ 7.

3. RESPOND — chosen response is one of: Avoid, Reduce, Transfer, Accept. Mitigation actions have an owner and a due date.

4. MONITOR — risk owners update weekly. Programme Manager reviews aged risks fortnightly. SteerCo reviews Top 10 monthly.

5. ESCALATE — see Section 4.

6. CLOSE — risk is closed when no longer applicable, mitigated below tolerance, or has materialised (in which case it becomes an Issue and moves to the Issues sheet).

# 3. Severity scales

| Score | Likelihood | Impact |
| --- | --- | --- |
| 1 | Rare (<10%) | Negligible — absorbed in contingency |
| 2 | Unlikely (10–30%) | Minor — slips one workstream by <2 weeks |
| 3 | Possible (30–60%) | Moderate — slips programme by <4 weeks or <5% cost |
| 4 | Likely (60–85%) | Major — slips programme by 4–8 weeks or 5–15% cost |
| 5 | Almost certain (>85%) | Severe — Gate-stopping, viability of programme threatened |

# 4. Escalation routes

| RAG / Trigger | Forum | Decision-maker |
| --- | --- | --- |
| Green (1–7) | Workstream stand-up | Workstream Lead |
| Amber (8–14) | Steering Committee — monthly | Programme Manager (with SteerCo) |
| Red (15–25) | Steering Committee — next slot, or extraordinary | Executive Sponsor |
| Gate-threatening | Executive Sponsor Group | Board (Sponsor proposes) |

# 5. Roles

| Role | Responsibility |
| --- | --- |
| Risk Owner (named) | Owns mitigation; updates weekly; closes when complete |
| Programme Manager | Aggregates, challenges scoring, owns SteerCo Top 10 view |
| Steering Committee | Reviews Top 10 monthly; approves response on Red risks |
| Executive Sponsor | Owns escalation to Board for gate-threatening risks |
| Business Architect | Subject-matter input on solution and data risks |
| SI Programme Director | Co-owns SI-side risks and joint mitigations |

# 6. Tolerance levels

The programme operates with the following tolerance band (set at Programme Setup & Mobilisation (S10) Charter):

Cost: ±10% of S12 FBC. Forecast outside tolerance → ESG decision

Schedule: ±2 weeks against the published end-stage milestone. Greater slip → ESG decision

Scope: Any change >5% of build effort → ESG decision

Benefits: Forecast benefit reduction >10% → ESG decision

# 7. Reporting

Weekly: workstream Top 5 risks at standup. Monthly: SteerCo Top 10 view; trend chart; new / closed / changed since last month. At every gate: full Red and Amber risk list.