## Site Cover
Site Readiness Checklist
One workbook per site. Owned by the Site Readiness Lead. Active S14 (Testing) through S17 (Hypercare & Stabilisation).
Programme | Northwind ERP Transformation
Site name | Northwind Industries Ltd - Birmingham Manufacturing
Site address | Unit 14, Tyburn Industrial Estate, Birmingham B24 9QH
Site type | Factory
Wave number | Wave 2
Go-Live date for this site | 2026-09-21
Hypercare exit date | 2026-11-30
Site Readiness Lead | Priya Shah (Operations Programme Office)
Site senior management contact | Mark Henderson - Plant Director
Site IT contact | Dan Ellis - Site IT Manager
Site BAU operations contact | Lisa Brennan - Production Manager
Date this checklist initiated | 2026-05-12
Last updated | 2026-05-04
Status (RAG) | Amber
Worked example: Northwind Industries Ltd is a fictional manufacturer used across the AS-IS artefacts. Replace with your own site details before use.

## Infrastructure Readiness
Infrastructure Readiness
Validate every item against the site spec. Status, owner and verified date carry through to Sign-off.
Item | Detail | Status | Owner | Due Date | Verified Date | Notes
Network bandwidth tested at peak load expected | Run loaded test against the planned mix of ERP / MES / scanner traffic at the busiest hour. Sign off against site spec. | Not started
Hardware delivered and racked | Servers, desktops, mobile devices, scanners and printers per site spec. Asset tags reconciled to inventory. | Not started
Environment access provisioned for end users | Badges, accounts and roles created. SSO mapping verified. New starters since plan baseline added. | Not started
Test environment access available for Super Users | Super Users can log in to the training / UAT environment from their own device, on site. | Not started
Connectivity to head office / cloud verified | End-to-end latency, throughput and authentication tested. Firewall rules confirmed in writing. | Not started
Backup connectivity provisioned and tested | Secondary link (4G / 5G failover, alternative ISP) tested with live cutover drill. | Not started
Local printers configured | Label printers, picking lists, despatch notes - default queues set per role / location. | Not started
Barcode scanners / mobile devices configured | If applicable. MDM enrolled, app installed, paired with the right printer / dock. | Not started
Wireless coverage tested in operational areas | Heat-map walkthrough of warehouse / shop floor / despatch. Dead zones logged. | Not started
Power and UPS verified for new equipment | Load calculations updated. UPS runtime tested. Generator test recorded if applicable. | Not started
Cabinet space and cooling adequate | Comms cabinet capacity, cooling and earthing signed off by Facilities. | Not started

## Super User Roster
Super User Roster
Named Super Users for this site. Confirm BAU cover so they are genuinely freed up across cutover and the first 2 weeks of hypercare.
Super User name | Role / Function | Modules supported | Backup person | BAU coverage dates (cutover + first 2 weeks) | BAU duties covered by | Manager sign-off (Y/N) | Notes

## Super User Training Log
Super User Training Log
Training status per Super User per module. Train-the-Trainer cascade tracked here too.
Super User | Module | Training method | Scheduled date | Completed date | Assessment score | Sign-off date | Notes

## Senior Mgmt Briefing Log
Senior Management Briefing Log
Standing record of meetings between the Site Readiness Lead and site senior management. Decisions belong here, not in inboxes.
Date | Attendees (names + roles) | Topics covered | Decisions / actions captured | Next meeting date | Notes

## Site Tour Log
Site Tour Log
Programme team site visits. Walking the operation builds shared context and surfaces issues that don't show up on Teams.
Date | Programme team visitors (names + roles) | Areas visited | Findings / observations | Actions arising | Owner | Due date

## Site Risk Log
Site Risk Log
Site-specific risks and issues. Material items escalate to the programme RAID Log; the Site Readiness Lead owns the link.
Risk ID | Description | Likelihood (H/M/L) | Impact (H/M/L) | Mitigation | Owner | Status | Notes
SR-001
SR-002
SR-003
SR-004
SR-005
SR-006
SR-007
SR-008
SR-009
SR-010

## Sign-off
Sign-off
Formal site readiness sign-off. All three signatures plus a clean confirmation matrix are required before cutover proceeds for this site.
Sign-off
Role | Name | Signature | Date
Site Readiness Lead
Site senior manager
Programme Manager
Confirmation matrix
Confirmation | Yes / No / Partial | Rationale / evidence
Infrastructure ready
Super Users trained
Senior management aligned
Site tours completed
Risks documented and accepted
Site ready for cutover |  | Provide a one-line rationale even if Yes.