Test Strategy

ERP Programme — Stages 13–17. Approach to SIT, UAT, Pre-UAT, regression, performance and cutover dress rehearsal.

| Document | Test Strategy |
| --- | --- |
| Version | v1.0 (TEMPLATE) |
| Date | April 2026 |
| Owner | Client Test Manager |
| Classification | Programme Use |

# 1. Purpose & scope

This document is the canonical test strategy for the ERP Programme. It applies from Stage 11 (Discovery — where testable requirements are first written) through Stage 17 (Hypercare). It is owned by the Client Test Manager, approved by the Design Authority, and ratified by the Steering Committee at Build & Configuration (S13) entry.

Method rule UAT is run by independent business testers, not Process Owners. Process Owners SIGN OFF UAT — they do not execute it. Letting Process Owners run UAT introduces confirmation bias and incomplete coverage; this is a flagged risk in the canonical RAID log.

# 2. Test levels

| Level | Stage | Run by | Purpose |
| --- | --- | --- | --- |
| Unit Test | S13 (per sprint) | SI Developer (signed off by SI Tech Lead) | Individual components in isolation; code quality; fits SI definition of done. |
| FAT — Functional Acceptance Test | S13 (per sprint) | SI Tester (Process Owner accepts at sprint review — Process Owners do NOT execute) | User stories meet acceptance criteria. Field-level / configuration-level. |
| Mini-BAT | S13 (every 2nd or 3rd sprint) | Benefit Owner or Senior User | Realistic scenario walk-through ~1–2 hours; early warning of process-fitness issues. No scripts. |
| SAT — System Acceptance Test | S14 (post-build, before SIT) | SI Test Lead + SI Test Team (Process Owner observers) | Integrated solution meets the Solution Design — functional + usability + regression. |
| SIT — System Integration Test | S14 (after SAT) | Joint Client + SI; Client Test Manager owns; signed off with Solution Architect | End-to-end + 3rd-party integrations work. |
| UAT — User Acceptance Test | S14 (preceded by Pre-UAT preparation) | Users / End Users (Process Owners do NOT execute scripts; Client Test Manager + Process Owners sign off) | End-to-end business processes work; the formal scripted audit trail. |
| BAT — Business Acceptance Test | S14 (after UAT) | Process Owners + Senior Users (scenario-based, unscripted); Benefit Owners + Exec Sponsor sign off | Wider business can operate the system under realistic conditions; readiness check. |
| NFT — Non-Functional Test | S14 (in parallel with BAT) | IT Ops + SI Infrastructure; IT Ops Lead + Solution Architect sign off | Performance, load, security, DR, batch — a level in its own right, not a footnote. |

# 3. Entry & exit criteria

## 3.1 SIT entry / exit

SIT entry: 100% functional build complete; unit testing signed off; integrations end-to-end callable; test data loaded; defect tracker live.

SIT exit: ≥95% scenarios pass; 0 P1 open; ≤5 P2 open with workaround; defect ageing ≤10 working days; Pre-UAT scripts ratified.

## 3.2 Pre-UAT entry / exit

Pre-UAT entry: SIT exit met; UAT scripts written; UAT data set loaded; UAT testers identified.

Pre-UAT exit: ≥90% UAT scripts dry-run successfully; remaining defects triaged; UAT cohort briefed.

Why Pre-UAT exists Skipping Pre-UAT pushes script defects and data quality issues into UAT — eroding business tester confidence and consuming UAT calendar time on environmental fixes. Compressing testing by removing Pre-UAT is one of the clearest predictors of a delayed go-live.

## 3.3 UAT entry / exit

UAT entry: Pre-UAT exit met; UAT environment refreshed and stable for 5 working days; Process Owners briefed and available for sign-off.

UAT exit: 100% critical and high-priority scripts passed and signed off by Process Owners; 0 P1 open; ≤5 P2 open with documented workaround; performance tests passed; defect ageing ≤7 working days.

# 4. Defect management

| Severity | Definition | Target fix | Escalation |
| --- | --- | --- | --- |
| P1 | Showstopper — no workaround, blocks testing | 24 hrs | SteerCo if open >48 hrs |
| P2 | Major — blocks part of testing or critical scenario | 5 working days | SteerCo if >10 wd |
| P3 | Minor — has workaround | Sprint of identification | — |
| P4 | Cosmetic / nice-to-have | Backlog | — |

Daily triage during SIT and UAT, chaired by the Client Test Manager with SI Functional Leads and Process Owner representation. Triage outputs go to the daily standup and the weekly Design Authority. Aged P2s breach SIT exit criteria.

# 5. Test data

Three test data tiers are used:

Synthetic data — generated by SI for unit and string testing (S13)

Sanitised production data — masked extract from legacy ERP for SIT (Testing (S14))

Mock production data — full migrated data set from mock load 2 onwards, for UAT and rehearsals

Data refreshes are scheduled at SIT entry, Pre-UAT entry, UAT entry, dress-rehearsal 1, dress-rehearsal 2, and dress-rehearsal 3. Each refresh is a planned event with a 24-hour freeze on the originating environment.

# 6. Environments

Test execution maps to environments as follows:

| Test level | Primary environment | Refresh source |
| --- | --- | --- |
| Unit / string | DEV | Manual seed |
| SIT | TEST (Tier-2 sandbox) | From DEV (build promotion) |
| Pre-UAT | UAT (Tier-2 sandbox) | From PROD-mirror (mock load) |
| UAT | UAT (Tier-2 sandbox) | Refreshed pre-UAT entry |
| Performance | PERF (Tier-3 sandbox) | PROD-equivalent volumes |
| Dress rehearsal | PROD-mirror (Tier-3 or PROD-staging) | From PROD copy |

# 7. Roles

| Role | Responsibility |
| --- | --- |
| Client Test Manager (Client) | Owns this strategy; SIT/UAT entry & exit; defect triage; reporting |
| SI Test Manager | Coordinates SI testers; provides SIT execution capacity |
| Business UAT testers | Execute UAT scripts independently; raise defects |
| Process Owners | Sign off UAT — DO NOT execute it |
| Design Authority | Approves this strategy and resolves test-related design decisions |
| Steering Committee | Governs against entry / exit criteria; decides go-live readiness |

# 8. Reporting

Weekly test report (Client Test Manager) covering: scripts planned vs run vs passed, defect count by severity, defect ageing, blocked scripts, environment availability, and forecast to next milestone. Goes to SteerCo monthly and Design Authority bi-weekly.

# 9. Risks & mitigations

| Risk | Mitigation |
| --- | --- |
| UAT compressed below 4 weeks | Hold the line at SteerCo; if compressed, stage release is the only safe option |
| Process Owners executing UAT scripts | Educate sponsors at S13 entry; named independent testers in RACI |
| Defects accumulate without triage | Daily triage from Day 1 of SIT; defect ageing as exit gate |
| Environment refresh failures | 3 mock loads minimum; Microsoft / SAP / Oracle support relationships in place |
| Test data quality below threshold | Mock load 1 dedicated to data quality assessment, not test execution |