CHANGE REQUEST FORM Programme: [Programme Name] · Stage: [10–17] · CR No: [auto]

Purpose. A Change Request (CR) is required when any one of: (a) a contracted deliverable or the SDD is changed; (b) effort exceeds the threshold set in the Programme Setup & Mobilisation (S10) Change Control Procedure; (c) scope, cost, timeline or benefits are affected; (d) the change crosses workstream boundaries. Anything below all four is sprint-level discretion and is logged in the sprint backlog or Design Decisions Log instead.

Approval path. Level 3 (design deviation) — Design Authority. Level 4 (scope/commercial) — DA + Steering, plus ESG if material to the Business Case or wave plan.

1. Identification

| CR ID | [programme-CR-001] |
| --- | --- |
| Title | [short, plain-English title] |
| Raised by | [name, role] |
| Raised date | [dd Mmm yyyy] |
| Workstream(s) affected | [Functional / Technical / Data / Integration / Test / Cutover / Cross] |
| Stage | [10–17] |
| Wave (multi-wave only) | [Wave 1 / 2 / 3 / Programme-wide] |

2. Type and trigger

| Type | [Level 3: Design deviation / Level 4: Scope or commercial change] |
| --- | --- |
| Trigger | [defect investigation / Process Owner request / Discovery gap / regulatory change / business priority shift / SI proposal] |
| Surfaced at | [forum and date — sprint review / DA / Steering / Process Owner workshop] |

3. Description

What is being requested:

[Describe the change in plain English — what is to be added, removed or modified; what is the as-is and what would change.]

Reason for the change:

[Why now? What is the business need, regulatory driver, defect or omission this corrects?]

4. Options considered

Show the alternatives that were considered. A CR with only one option is not an analysis — it is a request. Minimum: do nothing, the recommended option, and one other.

| Option | Description | Pros / cons | Effort (SI days) |
| --- | --- | --- | --- |
| Do nothing | [] | [] | [] |
| Option A (recommended) | [] | [] | [] |
| Option B | [] | [] | [] |

5. Recommendation

[State which option is recommended and why. Single paragraph, no hedging.]

6. Impact assessment

| Cost impact (£) | [firm if Solution Design & Full Business Case (S12)+; ROM otherwise] |
| --- | --- |
| SI effort (days) | [breakdown by role] |
| Client effort (days) | [Process Owner, BA, Test, IT — by role] |
| Timeline impact (weeks) | [on critical path / off / parallel] |
| Scope impact | [adds / removes / modifies named function] |
| Benefits impact | [changes to Benefits Map — refer to entry; named Benefit Owner sign-off] |
| Risk impact | [new risks, retired risks, severity changes] |
| Dependencies | [cross-workstream sequencing, third-party touchpoints] |
| Test impact | [scripts to add/change; regression scope; UAT impact] |
| Data impact | [migration, master data, integration] |

7. Approval path

Tick the route this CR will travel. A Level 4 CR cannot skip Steering. An ESG-impacting change cannot skip ESG.

| Approver | Decision | Decision date | Signed by |
| --- | --- | --- | --- |
| Design Authority | [ ] | [ ] | [ ] |
| Steering Committee (if Level 4) | [ ] | [ ] | [ ] |
| Executive Sponsor Group (if material to BC) | [ ] | [ ] | [ ] |

8. Decision and follow-up actions

| Decision | [Approve / Reject / Defer / Further info] |
| --- | --- |
| Decision rationale | [1–3 sentences] |
| Conditions of approval | [any caveats, monitoring requirements] |
| SDD update required? | [Yes / No — section reference] |
| Backlog update required? | [Yes / No — sprint reference] |
| PO / contract amendment required? | [Yes / No] |
| Communications required | [Process Owner cohort, end users, third parties] |
| Owner of follow-up actions | [name, due date] |

Authored as a S10 deliverable under the Programme Change Control Procedure. Not for use without that procedure being signed by both Client and SI.