## Cover
DESIGN DECISIONS LOG
Programme | [Programme name]
Owner | Solution Architect (Client) — co-signed by SI Solution Architect at DA
Stage span | Stages 11–17 (Discovery through Hypercare)
Purpose
This log captures every design decision taken in workshops, sprint reviews and Design Authority sessions. It is the operational record that prevents 'we always agreed that' disputes later in the build. A design decision is logged when the decision is consistent with the signed SDD's intent — Level 2 in the change control hierarchy. If the decision deviates from the SDD or affects scope, cost, timeline or benefits, it stops being a Decision and becomes a Change Request (Level 3 or 4). See the Change Control Procedure for thresholds.
How to use
1. New decision → add a row on the Decisions tab. Auto-incrementing ID.
2. Status starts as 'Open'. Move to 'Ratified' once the DA or sprint review approves.
3. 'Implemented' once the configuration has been built and tested.
4. If a logged decision is later challenged, do not edit. Add a new row referencing the original.
5. Decisions of cross-workstream impact must be tagged 'Cross' on Workstream and tabled at the next DA.
6. Anything that changes the SDD = stop. Raise a Change Request instead.

## Decisions
ID | Date raised | Title | Workstream | Stage | Description (the decision) | Rationale | Alternatives considered | Decision maker | Status | Date ratified | Linked CR (if any) | SDD section | Implemented in sprint
DD-001 | 2026-06-12 | Customer master record key — use ABN where present | Functional · Sales | S11 | Customer master uses ABN as primary identifier where present, falling back to internal key for non-ABN customers. | ABN provides single source of truth for B2B customers and aligns with ATO reporting requirements. Internal key alone produces duplicates after migration. | (a) Internal key only — risk of duplicates. (b) ABN only — fails for non-ABN customers. (c) Hybrid — chosen. | Functional Lead + Process Owner (Sales) | Ratified | 2026-06-19 |  | SDD §4.2
DD-002 | 2026-06-14 | Workflow approver levels — three-tier purchase approval | Functional · Procurement | S11 | Purchase orders use three-tier approval: <£10k = manager, £10k–£100k = department head, >£100k = Finance Director. | Aligns to existing AS-IS approval matrix; Stage 11 Discovery confirmed Process Owners want the existing tiers preserved. | Two-tier (rejected — too coarse), four-tier (rejected — bureaucratic). | Process Owner (Procurement) | Open |  |  | SDD §6.1
DD-003 | 2026-06-21 | Default reporting currency — GBP at programme level | Cross | S11 | GBP set as programme reporting currency. Local entities transact in local currency; consolidation in GBP. | Group reports to LSE in GBP; FY-end consolidation already runs on GBP. | EUR (rejected — group reporting is GBP), local-only (rejected — no consolidation). | Solution Architect + Finance Process Owner | Ratified | 2026-06-28 |  | SDD §3.4

## Cross-workstream view
Cross-workstream decisions — items tagged 'Cross' on the Decisions tab. Filter the main tab by Workstream = Cross.

## Summary
Summary
Status | Count
Open
In review
Ratified
Implemented
Superseded
Withdrawn