## Slide 1
20-Stage Programme Lifecycle
From Vision to Maturity
From Vision to Maturity
Strategic Alignment Framework embedded throughout · 20 stages · 6 governance phases
20
Lifecycle Stages
12 Wks
Pre-Programme
6
Governance Phases
PRE-PROGRAMME
SELECTION
SETUP & DESIGN
BUILD & TEST
DEPLOY
POST-PROG
Programme Lifecycle · Strategic Alignment Framework · From Vision to Maturity
Notes: This is the master view — 20 stages, six phases, the whole journey from problem statement to optimisation. Don't try to walk the room through every stage on this slide. Let it land as a picture, then jump straight to the phase view next. The ribbon at the top is the storytelling spine; the rest is reference.

## Slide 2
Programme Lifecycle · 20 Stages at a Glance
PRE-PROGRAMME (Prep-work)
SELECTION
Setup & DESIGN
BUILD & TEST
DEPLOY
POST-PROG
0
Problem /
Opportunity
1
Vision &
Strategy
2
Value Defn
& CfC
3
Design
Governance
4
Execution
Enablement
6
Funding
Envelope
7
Market
Engage.
8
Software
Select.
9
SI Select
Contract
10
Prog.
Mobilise
11
Discovery
12
Design /
Full BC
13
Build &
Config
14
Testing
15
Cutover
Plan.
16
Deploy
Go-Live
17
Hypercare
& Stab.
18
Benefits
Review
19
Optimise
& Maturity
Programme Charter produced during Design Governance & Sponsorship (S3) · Activated at SI Selection with ROM Pricing (S9) · Governs all 20 stages
Establishes the strategic baseline, investment case, governance and benefit ownership before a single supplier is engaged · 12 weeks · 6 stages · Pre-Programme (S0–S5)
Investment-grade decisions · Funding Envelope with benchmark costs at S6 · SI ROM (not firm costs) at S9 · Selection (S6–S9)
Design Authority live and governing · S12: Full Business Case confirmed with firm SI costs (±10–15%) · Requirements, architecture and data migration agreed · Setup & Design (S10–S12)
Build scope governed against the Benefits Map · Acceptance criteria set against baseline KPIs · Integration, data migration and UAT all signed off · Build & Test (S13–S14)
Baselines 12+ months old — KPI measurement begins at go-live · Cutover, deployment and hypercare stabilisation · Deploy (S15–S17)
ROI Driver Matrix used as the scorecard · Benefits proven against Week 6 baselines · Continuous optimisation and platform maturity · Post-Programme (S18–S19)
Programme Charter produced during Design Governance & Sponsorship (S3) · Activated at SI Selection with ROM Pricing (S9) · Governs all 20 stages
PRE-PROG
SELECTION
SETUP &
DESIGN
BUILD &
TEST
DEPLOY
POST-PROG
5
Benefits &
Alignment
Notes: The thing to land here is that the business case isn't one moment — it matures across four. Value Definition & Case for Change (S2) is where you set the benefits side. Funding Envelope & Benchmark Costs (S6) adds benchmark costs for funding approval. SI Selection with ROM Pricing (S9) folds in the SI's ROM at plus-or-minus 30 per cent. Solution Design & Full Business Case (S12) is the final number — firm and capped at plus-or-minus 10 to 15. Worth flagging that the SI genuinely cannot give firm end-to-end costs until after Discovery and Design. Anyone pressing for firm pricing earlier is asking them to make it up.

## Slide 3
Pre-Programme Framework · Stages 0–5 · 12 Weeks
Establishes the baselines, governance and ownership that make Selection through Optimisation (S6–S19) investment-grade · Programme Charter produced in Design Governance & Sponsorship (S3), activated at SI Selection with ROM Pricing (S9)
0
Problem / Opportunity Identification
Defines the strategic trigger. Confirms the business problem or opportunity exists before any programme activity begins.
· Business problem or opportunity clearly articulated
· Current state pain points documented with evidence
· Strategic alignment to organisational priorities confirmed
· Executive sponsor identified and mandate confirmed
1
Vision & Strategy Alignment
Establishes the strategic baseline. Everything in Selection through Optimisation (S6–S19) is validated against the outputs of this stage.
· Purpose statement drafted and agreed
· Capability baseline established
· Heatmap scored by functional leaders
· Operating model intent and guiding principles agreed
2
Value Definition & Case for Change
Builds the investment case from real baselines. Benefits mapped to named owners before any funding is approved.
· Benefits map: every benefit linked to a named owner
· KPI baselines captured from live systems — not estimates
· ROI Driver Matrix completed
· Case for Change documented for Funding Envelope & Benchmark Costs (S6) gate
3
Design Governance & Sponsorship
Governance structures and accountability confirmed. Programme Charter signed before Funding Envelope & Benchmark Costs (S6) gate.
· RACI: roles and accountability confirmed
· Decision Rights Framework established
· Design Authority terms of reference agreed
· Steering Committee membership and cadence confirmed
4
Execution Enablement
Programme readiness confirmed. Mobilisation plan, risk register, and stage gate criteria locked before delivery begins.
· Stage gate readiness criteria defined
· Change impact assessment and risk register completed
· Mobilisation plan confirmed with resource commitments
· Scope prioritisation matrix confirmed against benefits map
5
Benefits Realisation & Continuous Alignment
Measurement framework locked. Every benefit owner has a confirmed KPI, baseline, target, and reporting cadence.
· Measurement framework per benefit owner locked
· Reporting cadence and review packs confirmed
· Benefits tracker template in place
· Exec oversight commitment and review cadence confirmed
⚠ Gate Check
If Problem / Opportunity (S0) is incomplete or informal, a 2-hour executive session is required to document and confirm the strategic trigger before proceeding. Do not start the 12-week clock until S0 is signed off.
Notes: Talk the room through three scenarios for Problem / Opportunity (S0). One: it's done — there's a real, signed business case and you go straight to S1. Two: it's been done informally — leadership knows there's a problem but nobody's written it down. Three: it hasn't happened. For two and three, don't start the 12-week clock until you've run a 2-hour exec session to formalise the trigger — what's the problem, what's the evidence, who's the sponsor. Without that, you're aligning a programme to something nobody's actually agreed needs doing.

## Slide 4
Selection · Stages 6–9
Investment-grade selection decisions · Real baselines, agreed capability heatmap and signed Decision Rights Framework already in place
6
Funding Envelope & Benchmark Costs
Funding envelope built on benchmark costs from the Case for Change. Board-ready with named executive sponsor and agreed budget.
· Funding envelope with benchmark costs completed and board-ready
· Options appraisal documented with recommended approach
· Funding approval obtained with agreed budget envelope
· Programme initiation authorised with named executive sponsor
7
Market Engagement & RFI
Capability heatmap defines exactly which gaps need addressing. RFIs are targeted, not a fishing exercise.
· Longlist of vendors and SIs identified via RFI responses
· Capability heatmap gaps mapped to vendor capability responses
· Reference sites and analyst briefings completed
· Shortlist of 3–5 vendors agreed for formal evaluation
8
Software Selection
Validated against strategic priorities from Vision & Strategy (S1). Selection criteria come directly from the Vision Charter.
· Weighted scoring evaluation completed against agreed criteria
· Proof of concept or scripted demo conducted against key scenarios
· Preferred vendor selected with documented rationale
· Commercial terms and licensing model agreed in principle
9
SI Selection (ROM Pricing)
SI contracted with ROM estimate (±30% variance). Firm costs not available until Discovery & Design complete at Solution Design & Full Business Case (S12).
· SI ROM estimate included in business case (±30% variance)
· Contracts and statements of work signed — ROM basis
· Preferred SI selected and heads of terms agreed
· Firm SI costs deferred to Solution Design & Full Business Case (S12) (post-Discovery & Design)
Notes: This is the Selection phase — Funding through SI Selection. The room is usually most engaged here because they can see the suppliers, the demos, the contracts. Worth noting in passing: the Heatmap and Decision Rights Framework from pre-programme are doing the real work in the background. Without them, you're scoring vendors on demo polish, not capability fit.

## Slide 5
Setup & Design / Build & Test · Setup & Design through Build & Test (S10–S14)
Design Authority live · Every design decision traced to the Benefits Map · Solution Design & Full Business Case (S12): Full Business Case with firm SI costs · Teams structured at Programme Setup & Mobilisation (S10)
10
Programme Setup & Mobilisation
Programme team onboarded and workstreams activated. Scope prioritised against benefits map.
· Governance cadence live — Steering Committee and Design Authority scheduled
· Programme environments provisioned and tooling in place
· Scope prioritisation matrix confirmed against benefits map
11
Discovery
Detailed requirements gathered. As-is process maps and gap analysis completed across all workstreams.
· As-is process maps documented and gap analysis completed
· Data assessment completed with migration strategy defined
· Integration catalogue confirmed with technical approach per interface
12
Solution Design & Full Business Case
Design documents produced. Full Business Case confirmed with firm SI costs (±10–15%). Final investment decision before build begins.
· Technical architecture and integration design confirmed
· Data migration design and cleansing rules agreed
· Full Business Case confirmed with firm/capped SI pricing
13
Build & Configuration
System configured and custom development completed per design. Integration build unit tested.
· Integration build completed and unit tested
· Data migration scripts built and dry run completed
· Test environments populated and ready for SIT
14
Testing
SIT, UAT and performance testing completed. Go-live readiness confirmed against baseline KPIs.
· UAT signed off by process owners
· Performance and load testing completed against volume benchmarks
· Regression testing passed and go-live readiness confirmed
Notes: Setup & Design through Build & Test — the heaviest delivery phases. Two things to emphasise: the Full Business Case lands at end of Solution Design & Full Business Case (S12), so that's the real investment decision, not the original board approval. And every design decision from Programme Setup & Mobilisation (S10) onwards traces back to the Benefits Map. If a design doesn't link to a benefit, ask why you're building it.

## Slide 6
Deploy & Post-Programme · Stages 15–19
Benefit owners briefed and KPI tracking ready · Baselines already 12+ months old by go-live · Benefits measured against pre-programme baselines from Value Definition & Case for Change (S2)
15
Cutover Planning
Cutover strategy confirmed — go/no-go criteria defined. Contingency and rollback plan rehearsed before go-live.
· Go/no-go criteria defined and signed off by Steering Committee
· Contingency and rollback plan documented and rehearsed
· Cutover rehearsal completed with timing and sequencing validated
16
Deployment & Go Live
Data migration executed and validated. System live for all users with war room and hypercare support in place.
· Data migration executed and validated against quality thresholds
· Cutover completed and system live for all users
· Go-live communication issued to all stakeholders
17
Hypercare & Stabilisation
Critical defects resolved within SLA. User adoption monitored. Hypercare exit criteria met before transition to BAU.
· Critical defects resolved within agreed SLA
· System performance validated against baseline benchmarks
· Hypercare exit criteria met and transition to BAU confirmed
18
Benefits Realisation & Review
KPI actuals measured against Value Definition & Case for Change (S2) baselines. Benefit owner reviews completed and programme closure documented.
· KPI actuals measured against baselines set in Value Definition & Case for Change (S2)
· Benefits tracker updated and presented to Steering Committee
· Programme closure report produced with lessons learned
19
Optimisation & Maturity
Continuous improvement pipeline identified. Additional phase roadmap agreed and platform health reviewed.
· Additional module or phase roadmap agreed and funded
· User adoption deepened through enhanced training and self-service
· Platform health reviewed and technical debt remediation plan in place
Notes: Deploy and Post-Programme. The thing to flag here is that the benefit baselines were set in Value Definition & Case for Change (S2) — typically 12 to 18 months before go-live. That's why the work in Pre-Programme matters. Without those baselines, you can't prove the programme delivered. You're just hoping it did.

## Slide 7
Governance Model · Three Bodies · One Connected Accountability Chain
Every governance body and every governance artefact is established in the pre-programme — before a single supplier is engaged
Executive Sponsor Group
Formed: Phase 1, Week 1 · Active: Throughout the full SDLC
Composition: Programme Sponsor (chair), CXO stakeholders, Finance lead, Business Change lead
Mandate: Produced by Programme Sponsor. Signed at Design Governance & Sponsorship (S3) gate. Reconfirmed at each phase gate.
Cadence: Monthly steering review. Quarterly strategic review. Attends every phase gate.
Sign-offs: Execution Enablement (S4) Mandate · Phase gate reconfirmations · Benefits Review · BAU handover
Vision Alignment Charter · Strategic Priority Ranking
Design Authority
Established: Phase 3, Week 12
Governs every design and build decision against the benefits map and ROI Driver Matrix. Enforces the Decision Rights Framework for all scope changes.
Active: Stages 9–14 · Closes: End of S14
ROI Driver Matrix · Decision Rights Framework · Benefits Map
Steering Committee
Active: Stages 9–17 · Bi-weekly
Monthly reviews of benefit realisation against the pre-programme baselines. Governs optimisation investment decisions in the post-programme phase.
Active: Stages 3–18 · Transitions to BAU at S19
Benefits Map · ROI Driver Matrix · Governance Charter
GOVERNANCE ARTEFACTS — All created in the pre-programme, before Funding Envelope & Benchmark Costs (S6)
Vision Charter
Week 4
Capability Heatmap
Week 1
Benefits Map
Week 8
ROI Driver Matrix
Week 8
Case for Change
Week 8
Risk Register
Week 8
RACI
Week 12
Decision Rights
Week 12
All artefacts are live documents — updated as the programme progresses through each phase
Notes: Three governance bodies, one accountability chain. Worth pausing here. Most failed programmes have these bodies on paper but they don't actually connect. The Exec Sponsor Group sets direction. Steering Committee makes decisions inside that direction. Design Authority makes design decisions inside what Steering approves. If a design decision hits Steering, governance has broken. Land that point.

## Slide 8
Programme Lifecycle · Entry & Exit Gates
Three gate tiers — Board Gates · Executive Go/No-Go · Phase Checkpoints | Diamonds are not indicative of time
Pre-Programme
Stages 0–5 · 12 wks
Selection
Stages 6–9 · 17–24 wks
Setup & Design
Stages 10–12 · 12–18 wks
Build & Test
Stages 13–14 · 14–24 wks
Deploy
Stages 15–17 · 8–14 wks
Post-Programme
Stages 18–19 · 12–26 wks
Programme Trigger
Confirmed
Programme Charter
Signed
G1
BOARD GATE 1
Funding Envelope Approved
SI Contracts
Signed
Discovery
Sign-Off
G2
BOARD GATE 2
Full Business Case Approved
Build
Complete
Test Exit /
Cutover Readiness
!
GO-LIVE
GO / NO-GO
GO-LIVE
Hypercare Exit /
BAU Transition
Programme
Closure
Gate Tiers
Board Gate (binary go/no-go)
Binding board decision. Two only — Funding Envelope & Benchmark Costs (S6) (proceed into market) and Solution Design & Full Business Case (S12) (commit to build). Never present these as soft milestones.
Executive Go/No-Go
Single binary decision by the Executive Sponsor — go-live readiness. Cutover does not start without it.
Phase Checkpoint
Forum review at a phase boundary. Confirms exit/entry criteria are met before the next phase begins. Not a board gate.
Go-Live Event
System live. Hypercare begins. KPI measurement against Value Definition & Case for Change (S2) baselines starts here.
Diamond positions are illustrative — they show sequence, not duration. Phase widths reflect indicative ranges; actual durations confirmed at Solution Design & Full Business Case (S12).
Notes: Three tiers of gates and they do different jobs. Board Gates (Gate 1 at end of S6, Gate 2 at end of S12) are the two big funding decisions — board-level go/no-go on real money. Go-Live Gate is different — that's the Exec Sponsor's binary call, not a board decision. Phase Checkpoints in between are governance hygiene — are we ready to move on. The diamonds aren't to scale; that's deliberate, because timing varies.