## Slide 1
Programme Lifecycle · Plan on a Page
20 Stages · 6 Governance Phases · Illustrative Timeline
Pre-Programme
Selection
Setup & Design
Build & Test
Deploy
Post-Programme
Strategic overview — not a project plan. Durations are indicative and will be refined during programme mobilisation.
~18–24 months
Indicative total programme duration
20
Stages
Notes: One-page programme view. Don't try to read it line by line — let people scan. Then move to slide 2 for the actual phase walkthrough. This is the slide they'll print and pin to the wall, so the value is the shape, not the detail.

## Slide 2
Programme Lifecycle · Plan on a Page 20 Stages · 6 Phases · ~18–24 Months
PHASE
Pre-Programme
Stages 0–5
12 wks
Selection
Stages 6–9
17–24 wks
Setup & Design
Stages 10–12
12–18 wks
Build & Test
Stages 13–14
14–24 wks
Deploy
Stages 15–17
8–14 wks
Post-Programme
Stages 18–19
12–26 wks
STAGES
0 Problem / Opportunity
1 Vision & Strategy
2 Value Defn & CfC
3 Design Governance
4 Execution Enablement
5 Benefits & Alignment
6
Funding
7
RFI
8
Software
9
SI Select
10
Mobilise
11
Discovery
12
Design
S0
Sprint 0
13
Build
14
Test
15
Cutover
16
Go-Live
17
Hypercare
18
Benefits
19
Optimise
KEY
MILESTONES
Problem Confirmed
Vision Charter
Benefits Map
Programme Charter
Funding Approved
Vendor Shortlist
Preferred Vendor
Contracts Signed
Governance Live
DA Sign-Off
Sprint 0 Complete
Build Complete
Go-Live Ready
GO-LIVE ★
Hypercare Exit
Benefits Review
Programme Closure
PARALLEL
ACTIVITIES
Client BAs: Requirements Mapping (Epics, Features, User Stories)
Change Management: Impact Assessment → Training → Adoption → Hypercare
Benefits Tracking: KPIs measured from go-live against Value Definition & Case for Change (S2) baselines
GOVERNANCE
BODIES
Executive Sponsor Group (Full Lifecycle)
Steering Committee (Monthly, Stages 3–18)
Design Authority (Bi-weekly, Stages 9–14)
Illustrative timeline — durations are indicative ranges. Actual timeline refined during Programme Setup & Mobilisation (S10) mobilisation. Total duration typically 18–24 months.
TIMELINE
Wk 1
Wk 12
Wk 32
Wk 47
Wk 66
Wk 77
Wk 96+
~18–24 months
Total Programme Duration
20 Stages
6 Governance Phases · 19 Gate Milestones
~8–10 days
Total Executive Time Commitment
Biz Case Confirmed
Notes: Walk the room through the six phases left to right. Pre-Programme is fixed at 12 weeks — don't compress. Selection runs 17 to 24 because vendor cycles vary. Setup & Design and Build & Test are the workhorse phases. Deploy is short and intense. Post-Programme runs at least two quarterly review cycles. The total range is 18 to 24 months and you should resist anyone who wants a single number this early.

## Slide 3
Phase Detail View Activities · Milestones · Executive Time
Pre-Programme 12 weeks · Stages 0–5
Activities Strategic workshops, Benefits Map, Governance Charter
Milestones Vision Charter (Wk 4) · Benefits Map (Wk 8) · Charter signed (Wk 12)
Exec Time 1.5 days workshops + pre-work
Selection 17–24 weeks · Stages 6–9
Activities Business case, RFI, scripted demos, SI evaluation, contracts
Milestones Funding (S6) · Shortlist (S7) · Vendor (S8) · Contracts (S9)
Exec Time 4–5 days (demos, interviews, approvals)
Setup & Design 12–18 weeks · Stages 10–12
Activities SI onboarding, discovery workshops, FDDs, DA sign-off
Milestones Governance live (S10) · Discovery (S11) · DA sign-off + Biz Case Confirmed (S12)
Exec Time Monthly Steering Committee
Build & Test 14–24 weeks · Build & Test (S13–S14)Activities Agile sprints, Unit, FAT, Mini-BAT, SAT, SIT, UAT, BAT, NFTMilestones Sprint 0 complete · Build complete (S13) · Go-live ready (S14)Exec Time Monthly Steering + BAT participation
Deploy 8–14 weeks · Stages 15–17
Activities Cutover planning, go-live, war room, hypercare
Milestones Go/no-go decision · GO-LIVE · Hypercare exit
Exec Time Go/no-go decision, weekly updates
Post-Programme 12–26 weeks · Stages 18–19
Activities Benefits tracking, quarterly reviews, programme closure, CI pipeline
Milestones First review (M3) · Closure (M6–9) · BAU transition
Exec Time Quarterly benefits reviews
Total: ~75–105 weeks (18–24 months) | Executive commitment: ~8–10 days across full lifecycle
Illustrative timeline — durations are indicative ranges. Executive time is approximate and depends on programme scope.
Notes: This is the detail behind the POAP. Walk it phase by phase, but keep it brisk.
Pre-Programme is 12 weeks and it cannot be compressed — that's the most important thing on the slide. About 1.5 days of executive time across workshops plus pre-work. Best return on time you'll get all programme.
Selection is where the room is most active — scripted demos, vendor scoring, SI interviews, contracts. Client BAs run requirements mapping in parallel, so the Selection time is doing two jobs.
Setup & Design — SI is in, embedded in governance. Discovery is joint. Design Authority signs off everything before build. Exec involvement drops to monthly.
Build & Test is the longest stretch. Agile sprints with FAT and Mini-BAT during build, then SIT, UAT, BAT, SAT post-build. Programme team is heads-down. Execs surface for the readiness gate.
Deploy is compressed and intense. Cutover, go/no-go, go-live, hypercare. The go/no-go is the single biggest exec call in the programme.
Post-Programme runs at least two quarterly review cycles. Programme formally closes at end of Benefits Realisation & Review (S18); Optimisation & Maturity (S19) carries on as continuous improvement.
The right-hand column — exec time — is the one to highlight. Across an 18 to 24 month programme, total exec commitment is 8 to 10 days. That's tiny. But it determines the quality of every decision the room will make.

## Slide 4
POAP: Key Assumptions 8 Planning Assumptions for Executive Discussion
1
Durations are illustrative ranges
Actual timeline depends on: number of process streams, legal entities and sites, integration complexity, data migration complexity, organisational change readiness, and SI delivery methodology.
2
Phases are sequential but stages may overlap
Discovery for one workstream can begin while another is completing. Build sprints can start for early workstreams while later workstreams are still in design.
3
Pre-Programme (12 weeks) should not be compressed
This is the foundation for everything. Compressing below 10 weeks risks poor-quality baselines and unprepared executives.
4
Requirements mapping runs in parallel with Selection
Completed by Client BAs at Client cost. This is not additional elapsed time — it runs alongside vendor and SI evaluation.
5
Benefits tracking starts at go-live (minimum 12 months)
Optimisation & Maturity (S19) transitions to BAU governance and is ongoing. Quarterly reviews against Case for Change (S2) baselines.
6
SI embedded from Programme Setup & Mobilisation (S10) to Hypercare & Stabilisation (S17) (hypercare exit)
Knowledge transfer to Client team must be complete before SI exit. Contract should include minimum commitment periods for key personnel.
7
Go-live date is an output of planning, not an input
The go-live date emerges from approved design scope and build velocity — it is not set before Solution Design & Full Business Case (S12) is complete. Setting a date before that increases risk.
Key Executive Question
"Would you rather have a date that is right, or a date that is early? Because you cannot reliably have both."
These assumptions should be discussed with the Executive Sponsor Group before programme mobilisation begins.
8
Firm SI costs not available until Solution Design & Full Business Case (S12)
SI provides ROM at SI Selection with ROM Pricing (S9) (±30%). Board approves Funding Envelope at Funding Envelope & Benchmark Costs (S6) (benchmarks). Final build commitment at Solution Design & Full Business Case (S12) with firm SI pricing. Two board gates: S6 (proceed) and S12 (commit).
Notes: Eight planning assumptions. Walk the ones that matter most for this room.
Assumption 1 — durations are ranges. Someone will ask for a single number. Resist. A range is more honest. The range narrows as you progress; by Solution Design & Full Business Case (S12) you'll have a confident date.
Assumption 3 — Pre-Programme can't be compressed. People try. The result is always the same: estimated baselines instead of real ones, template governance instead of tailored, named-only Benefit Owners. Every shortcut shows up downstream.
Assumption 4 — requirements mapping runs parallel with Selection. This is a capacity question. You need 2 to 3 BAs for 8 to 12 weeks. If you don't fund it, the SI does the work at their day rate during Discovery. More expensive, no faster.
Assumption 6 — SI is embedded from Programme Setup & Mobilisation (S10) to Hypercare & Stabilisation (S17). Build named personnel and minimum commitment periods into the SI contract during SI Selection with ROM Pricing (S9). Otherwise they swap people out.
Assumption 7 is the big one — go-live date is an output, not an input. Every exec wants a go-live date on day one. The honest answer: we'll give you a range now, a confident date after S12. Setting a firm date earlier creates a deadline the programme cuts corners to hit. If someone pushes back, ask them: would you rather have a date that's right, or a date that's early? You can't reliably have both.

## Slide 5
Programme Constraints: What Is Fixed and Non-Negotiable
Programme Lifecycle · POAP · Constraints
# | Constraint | Rationale
1 | Pre-Programme cannot compress below 10 weeks | Baselines require real data from functional leaders. Workshops need exec pre-work, BA synthesis, and review time.
2 | Stage gates cannot be skipped without evidence | Each gate prevents proceeding on assumption. Skipping transfers risk downstream at higher cost.
3 | Design Authority must approve all designs before build | Unsigned designs create uncontrolled scope, rework, and integration defects.
4 | SI operates within Client’s governance framework | DA decisions are binding. Scope changes go through the Decision Rights Framework.
5 | UAT and BAT are separate, sequential test phases | UAT confirms requirements (scripted). BAT confirms operations (scenario-based). Both required.
6 | Go-live requires zero P1, and zero P2 unless a workaround is agreed and documented | A 2-week delay costs far less than a failed go-live with critical defects.
7 | Benefits tracking runs minimum 12 months post go-live | Benefits stabilise over 2–3 months. Revenue benefits take 6–12 months to materialise.
8 | Named Benefit Owners assigned before Funding Envelope (S6) | Without personal accountability for KPI targets, benefits will not be tracked or realised.
9 | Go-live date set after Solution Design & Full Business Case (S12), not before | Premature dates create fixed deadlines the programme optimises against by cutting testing.
10 | Knowledge transfer must complete before SI exit | Without KT, Client depends on SI at premium rates. Co-delivery is contractual.
11 | Build commitment not authorised until SI provides firm pricing at S12 | Board approves Funding Envelope at S6, confirms build budget at S12. Committing before firm costs are known creates budget risk.
Notes: Ten constraints. Frame these as the rules of the road — not suggestions, agreed before mobilisation.
Constraint 1 will get challenged. "Can we do Pre-Programme in 8 weeks?" You can. The quality drops. Real baseline data takes time. BA synthesis takes time. Compress below 10 weeks and you're choosing speed over quality, and that choice echoes through the whole programme.
Constraint 4 gets tested during delivery. The SI brings their own methods — some are good, adopt those. But the governance framework is the Client's. Design Authority decisions bind the SI. If the SI builds something DA hasn't approved, you've lost control of scope.
Constraint 9 is the one execs push back on hardest. They want a date for the board. Offer the range, explain it narrows, hold the line. Committing to a date before Solution Design & Full Business Case (S12) is a political call, not a planning call — and political dates have a poor track record.

## Slide 6
Key Dependencies: What Depends on What
Programme Lifecycle · POAP · Dependencies
Internal Dependencies (between stages)
Dependency | Up | Down | Impact if Delayed
Vision Charter complete before funding | S1–2 | S6 | No evidence-based value case for board
Capability Heatmap scored before RFI | S1 | S7 | RFI questions cannot be targeted
Requirements Baseline before SI Discovery | S7–9 | S11 | SI starts from scratch at day rates
All FDDs DA-signed before Sprint 1 | S12 | S13 | Unsigned designs create rework
Unit pass before FAT begins | S13 | S13 | Defects cascade into Sprint Review — late rework at SI cost
FAT + Mini-BAT pass at Sprint Review | S13 | S13 | Sprint not closeable — build slips
SAT pass before SIT begins | S13 | S14 | System-level defects surface in joint testing — Client time wasted, integrations rework
SIT pass before UAT begins | S14 | S14 | Users hit broken integrations — adoption damage, UAT halts
UAT pass before BAT begins | S14 | S14 | Cannot simulate end-to-end ops if requirements unmet
NFT certificate before Go-Live Gate | S14 | S16 | Performance, security, DR not assured — go-live risk
BAT signed off before Go-Live Gate | S14 | S16 | No business validation for go-live
Hypercare exit criteria met before BAU | S17 | S18 | Premature exit collapses adoption
SI firm pricing required before build commitment | S12 | S13 | Cannot commit build budget without firm costs — programme pauses
External Dependencies
Dependency | Owner | Impact if Delayed
Executive availability for workshops and go/no-go | Exec Sponsor | Workshops reschedule — cascading delays
IT infrastructure provisioning (dev, test, prod) | IT Ops / CIO | Environments not ready delays mobilisation
Functional leader availability for requirements | Functional Leaders | Requirements baseline incomplete
Data quality for baseline and migration | Data Lead, Data Owners / IT | Poor data extends migration, go-live risk
SI resource availability — named personnel | SI Programme Dir | Key personnel lost — knowledge gap
Third-party system access for SIT | Vendors / IT | Integration testing blocked
Change readiness — training, BAU release | Change Lead / HR | Users untrained — adoption fails
Procurement/legal process for SI contract | Procurement / Legal | Contract delays push mobilisation
Cutover Lead confirms cutover readiness before Go-Live Gate | Cutover Lead | Cutover plan unsigned — GLG cannot proceed
Executive Sponsor signs Go-Live Gate (GLG) | Exec Sponsor | No formal authorisation to deploy
Notes: Dependencies are the hidden timeline risk. Most delays aren't caused by the work — they're caused by something upstream not being ready.
The internal chain is straightforward: Benefits Map (S2) → Funding (S6) → Requirements Baseline (S7–S9) → SI Discovery (S11) → FDDs (S12) → Build (S13) → Testing (S14) → Go-Live (S16). A delay anywhere cascades.
Three external ones cause most pain. Executive availability — get the Sponsor's calendar blocked 6 weeks ahead for Week 1 workshops, non-negotiable. IT infrastructure — environment provisioning is always underestimated; if you don't start until S10, you've lost weeks before the SI can be productive. Data quality — if Discovery (S11) shows 30 per cent of customer records are duplicates, you start cleansing immediately, not at Testing (S14). Flag data quality as a risk at S2 and track it through.

## Slide 7
Key Programme Risks: Top 13
Programme Lifecycle · POAP · Key Risks
# | Risk | Likelihood | Impact | Mitigation
1 | Executive disengagement after Pre-Programme | High | Critical | Sponsor attendance at all Steering Committees non-negotiable. Escalate if missed.
2 | Scope creep during Discovery — no filtering | High | High | DA governs all scope. Every requirement traced to Benefits Map.
3 | SI key personnel reassigned post-contract | Med | Critical | Named personnel with 6–12 month commitment. Replacement needs Sponsor approval.
4 | Data quality worse than assessed | High | High | Assessment at Discovery (S11). Cleansing starts immediately. Min 2 dry runs.
5 | Requirements mapping incomplete before Discovery | Med | High | 2–3 BAs from Market Engagement & RFI (S7). BA Lead monitors weekly.
6 | Customisation exceeds plan — unapproved builds | Med | High | DA approval for ALL customisations. Decision log audited monthly.
7 | Testing compressed — UAT or BAT rushed | High | Critical | Gates cannot be skipped. Zero P1/P2 for go-live. PM holds the line.
8 | User adoption below target post go-live | Med | High | Change Lead from Programme Setup & Mobilisation (S10). Adoption tracked. Floor-walking support.
9 | Integration failures during SIT | Med | High | Catalogue confirmed at Discovery (S11). Each integration unit tested independently.
10 | Go-live date set before design — political date | High | Critical | Go-live is output of planning. Range first. Firm date after Solution Design & Full Business Case (S12).
11 | Benefits not tracked — team disbands | Med | High | Min 12 months tracking. Benefit Owners report quarterly.
12 | Knowledge transfer from SI insufficient | Med | High | Mandatory KT plan. Co-delivery. Client self-sufficient before SI exits.
13 | SI firm pricing exceeds Funding Envelope | Med | High | ROM at SI Selection with ROM Pricing (S9) provides early warning. DA manages scope during Design. Regular cost tracking Setup & Design (S10–S12).
Scoring: Likelihood High = probable without controls | Med = possible with partial controls | Low = unlikely with controls in place Impact Critical = programme failure or >3 month delay | High = significant delay or rework | Med = manageable with intervention
Notes: Thirteen risks. These aren't theoretical — they're patterns. Every one has happened on a real programme.
Risk 1, executive disengagement, is the most common and most damaging. Sponsor is engaged through Pre-Programme and Selection, then build starts, it feels like a tech project, they delegate to the PMO. By the time go/no-go arrives, they don't have the context. Prevention: Steering Committee attendance is a personal commitment, not a calendar option.
Risk 3, SI key personnel reassignment, is the most predictable. Their best people win the deal, then move to the next one. Prevention is contractual — named personnel, minimum commitment, replacement approval.
Risk 7, compressed testing, is the most dangerous. There'll be a moment when the timeline's under pressure and someone suggests cutting test. Always say no. Hold the gates.
Risk 10, political go-live dates, is the most insidious. A board member says "we need to go live by March." The plan reverse-engineers to March. Testing compressed, hypercare shortened, go-live happens with open P2s and 65 per cent adoption. Within 3 months the programme is in recovery. The date was hit. The programme failed.

## Slide 8
Critical Success Factors: 8 Conditions for Timeline Success
Programme Lifecycle · POAP · Critical Success Factors
# | Critical Success Factor | What This Means in Practice
1 | Visible, active Executive Sponsorship | Sponsor attends all Steering Committees, makes go/no-go personally, available for escalations within 48 hours. Not delegated.
2 | Named, accountable Benefit Owners from Value Definition & Case for Change (S2) | Each benefit has a named functional leader treating realisation as a performance objective. Quarterly reporting.
3 | Client-side requirements mapping during Selection | 2–3 BAs full-time for 8–12 weeks produce Epics, Features, draft User Stories before SI arrives. Halves Discovery.
4 | SI embedded in governance from day one | SI Solution Architect co-chairs DA. SI Programme Dir attends Steering Committee. No shadow governance.
5 | Design Authority decisions are final | DA decisions documented and final. SI builds per DA. Stakeholders do not relitigate offline.
6 | Testing is thorough, layered, and protected | Seven test levels in sequence. Gates held. PM escalates if compression proposed. Zero P1/P2 for go-live.
7 | Data quality as first-class workstream | Assessment at Discovery (S11), cleansing starts immediately, min 2 dry runs, validation thresholds, Data Owners accountable.
8 | Go-live date set by programme, not imposed | Range communicated early. Firm date after Solution Design & Full Business Case (S12). Date reflects the plan, not a political commitment.
These 8 factors consistently differentiate successful ERP programmes from failed ones. If any factor is absent, the timeline is at risk.
Notes: Eight critical success factors. If all eight are in place, the conditions are right. If any are missing, the timeline extends and risk goes up.
Factor 1 — active exec sponsorship — is the foundation. Never seen a successful programme without it. Have seen several failures where the Sponsor was engaged at the start and gone by build.
Factor 3 — requirements mapping during Selection — is the one execs underfund because they see it as optional prep. It isn't. It's the difference between a 6-week Discovery and a 12-week Discovery, and between SI validating requirements and SI gathering them.
Factor 6 — testing protection — is the one the PM fights for. Around Build & Configuration (S13) sprint 6 the build will be 2 weeks behind and someone will propose cutting UAT. The PM has to say no. Every test day cut increases go-live defects.
Factor 8 — go-live date is the output of design, not the input. Worth repeating because it's worth repeating. Most common cause of ERP programme failure is a date set before the scope was understood. Set the date after design. Not before.
The Data Lead callout is just for reference — Client-side coordinator of the Data workstream from S2 to Hypercare & Stabilisation (S17). Data Owners report in.

## Slide 9
Programme Lifecycle · Entry & Exit Gates
Three gate tiers — Board Gates · Executive Go/No-Go · Phase Checkpoints | Diamonds are not indicative of time
Pre-Programme
Stages 0–5 · 12 wks
Selection
Stages 6–9 · 17–24 wks
Setup & Design
Stages 10–12 · 12–18 wks
Build & Test
Stages 13–14 · 14–24 wks
Deploy
Stages 15–17 · 8–14 wks
Post-Programme
Stages 18–19 · 12–26 wks
Programme Trigger
Confirmed
Programme Charter
Signed
G1
BOARD GATE 1
Funding Envelope Approved
SI Contracts
Signed
Discovery
Sign-Off
G2
BOARD GATE 2
Full Business Case Approved
Build
Complete
Test Exit /
Cutover Readiness
!
GO-LIVE
GO / NO-GO
GO-LIVE
Hypercare Exit /
BAU Transition
Programme
Closure
Gate Tiers
Board Gate (binary go/no-go)
Binding board decision. Two only — Funding Envelope & Benchmark Costs (S6) (proceed into market) and Solution Design & Full Business Case (S12) (commit to build). Never present these as soft milestones.
Executive Go/No-Go
Single binary decision by the Executive Sponsor — go-live readiness. Cutover does not start without it.
Phase Checkpoint
Forum review at a phase boundary. Confirms exit/entry criteria are met before the next phase begins. Not a board gate.
Go-Live Event
System live. Hypercare begins. KPI measurement against Value Definition & Case for Change (S2) baselines starts here.
Diamond positions are illustrative — they show sequence, not duration. Phase widths reflect indicative ranges; actual durations confirmed at Solution Design & Full Business Case (S12).
Notes: Same gate map as the Overall Timeline deck. Three tiers: two Board Gates (end of S6 and end of S12) doing the heavy money lifting, the Go-Live Gate which is the Exec Sponsor's binary call (not a board gate), and Phase Checkpoints in between for governance hygiene. Worth flagging the GLG distinction explicitly — people often assume it's another board call. It isn't.