## Slide 1
Investment-Grade Selection
Selection (S6–S9): From Funding Approval to Signed Contracts
Programme Lifecycle · Selection Phase · Built on Pre-Programme Foundations
Notes: This deck covers Selection (S6–S9). By the time you're standing here, the Pre-Programme work should be done — signed Vision Alignment Charter, Capability Heatmap scored by your functional leaders, Benefits Map with named owners and real baselines, Governance Charter with decision rights.
Every decision in this phase anchors back to those foundations. This isn't a beauty parade. It's investment-grade selection — and it's investment-grade because of the work you did in the first 12 weeks.

## Slide 2
Why Selection Rigour Matters
Purpose: Make investment-grade software and supplier decisions built on the strategic foundations established in Pre-Programme (S0–S5).
Three risks when selection is poorly run:
Wrong software: chosen on demos and relationships, not strategic fit — leads to costly customisation or re-platforming
Wrong partner: SI selected on price alone — capability gaps emerge mid-delivery, costs escalate
No decision trail: selection rationale undocumented — challenged later by new leadership or audit
What investment-grade selection ensures:
Software evaluated against the Capability Heatmap and strategic priorities from Vision & Strategy (S1)
SI selected against delivery capability, cultural fit, and commercial rigour
Every decision documented with evidence and governed by the Decision Rights Framework
“Without pre-programme foundations: selection is opinion.
With them: selection is evidence.”
Programme Lifecycle · Selection Phase · Stages 6–9
Notes: The why. Three failure patterns I've seen repeatedly in ERP selection — all of them avoidable.
Wrong software: a manufacturer picked their ERP off a polished demo and a vendor relationship. Eighteen months in, the platform couldn't handle their multi-site inventory model without significant customisation. Cost overrun: 40 per cent. Root cause: nobody mapped vendor capability against the actual Heatmap gaps. They bought what was sold, not what they needed.
Wrong SI: another organisation picked the SI on lowest price. Six months in, the SI's named architect had been swapped twice, the team was junior, the methodology was templated rather than tailored. Programme recovered but lost 4 months and £2M.
Wrong commercial structure: classic. Fixed-price contract signed at S9 covering all of build and test before Discovery. The SI gave a number to win the deal, then re-priced as scope clarified. The board felt deceived. The relationship never recovered.
Land the message: Selection rigour isn't optional. It's the difference between a programme that delivers and one that recovers.

## Slide 3
What This Deck Covers
A practical guide for executives and programme teams on how we will run an evidence-based selection process across four stages:
6
Funding Approval Case & Budget Envelope
Translate the Case for Change from Value Definition & Case for Change (S2) into a board-ready funding decision
7
Market Engagement & RFI
Use the Capability Heatmap to target the right vendors with the right questions
8
Software Selection
Evaluate, score, and select against pre-agreed strategic criteria
9
SI / Supplier Selection
Select the delivery partner with rigour, governed by the Decision Rights Framework
Appendix: Selection Playbook
Templates, scoring frameworks, example evaluation criteria, and stage gate checklists for the programme team.
Parallel activity: Client-side requirements mapping during Market Engagement through SI Selection (S7–S9) (detailed in the Setup & Design deck)
Illustrative — to be adapted to your organisation’s context and procurement requirements
Notes: Two documents in one. The first 12 slides are the strategic overview for this room — what you're doing, why, and what you need from them. Appendix from slide 13 is the Selection Playbook for the team — templates, scoring matrices, gate checklists.
Four stages, each building on the last. Funding Envelope & Benchmark Costs (S6) gets funding approved. Market Engagement & RFI (S7) engages the market against the Heatmap. Software Selection (S8) picks the platform via scripted demos. SI Selection with ROM Pricing (S9) selects the SI and signs the contract. End of S9 is Board Gate 1 — first of two big board funding decisions.

## Slide 4
Selection Phase · Stages 6–9 at a Glance
STAGE 6
Funding Approval
›
Key Output
Board-approved investment case with budget envelope
3–4 weeks
STAGE 7
Market Engagement
›
Key Output
Vendor longlist refined to shortlist of 3–5
4–6 weeks
STAGE 8
Software Selection
›
Key Output
Preferred vendor selected with documented rationale
6–8 weeks
STAGE 9
SI / Supplier Selection
Key Output
Preferred SI selected, contracts signed
4–6 weeks
Total Selection duration: typically 17–24 weeks depending on procurement complexity
Pre-requisite: All Pre-Programme artefacts (Pre-Programme (S0–S5)) must be signed off before Funding Envelope & Benchmark Costs (S6) begins
Programme Lifecycle · Selection Phase · Stages 6–9
Parallel activity: Client BAs and Process Owners conduct requirements mapping workshops during Market Engagement through SI Selection (S7–S9), producing Epics, Features, and draft User Stories. This work runs alongside selection activities and is handed to the SI at Programme Setup & Mobilisation (S10). See Setup & Design deck for full methodology.
Notes: Walk the four stages with typical durations.
Funding Envelope & Benchmark Costs (S6) is usually fastest — 3 to 4 weeks. The Case for Change from Value Definition & Case for Change (S2) does most of the heavy lifting; this stage just adds benchmark costs and approval-grade structure.
Market Engagement & RFI (S7) runs 4 to 6 weeks. Vendors need 3 to 4 weeks to respond well. Don't compress; you'll get rushed responses you can't compare.
Software Selection (S8) is the longest at 6 to 10 weeks because of scripted demos. Each shortlisted vendor gets 1 to 2 days. Scoring takes a week. Reference checks add another week or two.
SI Selection with ROM Pricing (S9) runs 4 to 6 weeks. RFP, evaluation, contract negotiation. Then Board Gate 1.

## Slide 5
Funding Envelope (S6): Funding Approval Case & Budget Envelope
Key Objectives
Translate the Value Definition & Case for Change (S2) Case for Change into a board-ready investment case
Include full cost/benefit analysis with real baselines (not estimates)
Document options appraisal with recommended approach
Obtain formal funding approval with agreed budget envelope
Confirm named executive sponsor and programme initiation authority
Outputs
Funding Approval Case (board-ready)
Options Appraisal with recommended approach
Budget envelope and funding approval
Programme initiation authority
“The Case for Change from Value Definition & Case for Change (S2) provides the value story. Funding Envelope & Benchmark Costs (S6) adds cost estimates and options analysis to secure a funding envelope.
The full investment case is confirmed at the end of SI Selection with ROM Pricing (S9) when actual vendor and SI costs are known.”
Programme Lifecycle · Selection Phase · S6
Notes: Funding Envelope & Benchmark Costs (S6) takes the Case for Change from Value Definition & Case for Change (S2) and develops it into a funding approval case. Not the final business case — that lands at Solution Design & Full Business Case (S12). What this stage does: turn benefits into pounds and benchmark costs into a funding envelope.
The output is a 10 to 15 page document, board-ready. Worth flagging the structure: executive summary, business problem, proposed solution direction, benefits, costs (benchmark only at this stage), risks, recommendation. Not 50 pages — execs won't read 50 pages.
Common trap: treating S6 as the final business case. It's not. The number gets refined twice more — at S9 with the SI ROM, and at S12 with firm pricing. Set that expectation now.

## Slide 6
Market Engagement & RFI (S7)
Key Objectives
Engage the market using targeted criteria derived from the Capability Heatmap
Issue RFI to longlist of vendors with structured questions aligned to strategic priorities
Evaluate RFI responses against pre-agreed criteria
Refine longlist to a shortlist of 3–5 vendors for formal evaluation
Complete reference site visits and analyst briefings
Outputs
RFI document aligned to Heatmap gaps and strategic priorities
Vendor longlist with initial assessment
Shortlist of 3–5 vendors with documented rationale
Reference site and analyst briefing summaries
“The Capability Heatmap defines exactly which gaps need addressing.
RFIs are targeted, not a fishing exercise.”
Programme Lifecycle · Selection Phase · S7
Notes: Market Engagement & RFI (S7) — going to market in a targeted way. The Capability Heatmap from Vision & Strategy (S1) tells you where your gaps are. Don't send a generic RFI; send one anchored to your scored gaps.
Worth flagging: vendors get dozens of RFIs. They invest real effort only in the ones that are clearly well-prepared. A targeted RFI gets serious vendor attention. A generic one gets boilerplate.
The output is a vendor longlist scored against the Heatmap, narrowed to a shortlist of 3 to 5 for the demo phase.

## Slide 7
Software Selection (S8)
Key Objectives
Conduct structured evaluation of shortlisted vendors
Run scripted demonstrations against key business scenarios from the Heatmap
Complete proof of concept where required for high-risk capability gaps
Apply weighted scoring evaluation against pre-agreed criteria
Select preferred vendor with fully documented rationale
Outputs
Scripted demo evaluation scores
Proof of concept results (where applicable)
Weighted scoring matrix with final rankings
Preferred vendor recommendation with documented rationale
Commercial terms and licensing model agreed in principle
“Selection criteria come directly from the Vision Alignment Charter and Capability Heatmap.
The preferred vendor is the one that best addresses our strategic gaps, not the one with the best demo.”
Programme Lifecycle · Selection Phase · S8
Notes: Software Selection (S8) is the most important stage in Selection because the wrong platform is the most expensive mistake in the entire programme.
The mechanism is the scripted demo. Each shortlisted vendor demonstrates against your scenarios — not theirs. Scenarios come from the Heatmap reds and ambers. You're testing whether the platform handles your hardest cases, not whether it handles theirs.
Worth landing: the scoring matrix is agreed before demos. Weights are set by Steering Committee. Functional fit at 35 per cent, total cost of ownership at 25, vendor strength at 20, technical fit at 20 — that's typical, but tune to your priorities.
Common trap: scoring against your favourite demo, not against your scenarios. Hold the discipline.

## Slide 8
SI Selection (S9): SI / Supplier Selection
Key Objectives
Issue RFP to shortlisted systems integrators with defined scope and delivery expectations
Evaluate SI proposals against delivery capability, sector experience, team quality, and commercial terms
Conduct SI team interviews and reference checks
Negotiate contracts, statements of work, and commercial terms
Confirm programme governance integration — SI accountability mapped to RACI and Decision Rights Framework
Define SI governance integration requirements in contract — Design Authority co-chair, RACI mapping, named personnel, knowledge transfer
Outputs
RFP document with defined scope, timelines, and governance expectations
SI evaluation scoring matrix
Preferred SI selected with documented rationale
Signed contracts and statements of work
SI team mapped into programme RACI
"At SI Selection with ROM Pricing (S9) the SI provides a Rough Order of Magnitude for end-to-end delivery. Firm costs for Build and Test are confirmed after Design is complete (Solution Design & Full Business Case (S12)).
The SI may fix-price Discovery and Design (Setup & Design (S10–S12)) as a discrete engagement."
Programme Lifecycle · Selection Phase · S9
Notes: The big misconception to clear up here: people assume the SI gives firm end-to-end costs at contract signing. They can't. The SI cannot price Build and Test accurately until they've finished Discovery and Design — they don't know the scope yet.
So how do you contract? Phase the commercials. Discovery and Design are fixed-price or capped — the SI can scope those. Build and Test are priced after S12, once the scope is known. The contract names personnel, sets minimum commitment periods, and includes replacement approval. That's how you protect against the SI swapping people out.
End of SI Selection with ROM Pricing (S9) is Board Gate 1 — the first of two board funding decisions. Worth flagging the gate structure now so the room knows what's coming.

## Slide 9
Inputs & Outputs Across the Selection Stages
Stage | Name | Key Inputs | Key Outputs
6 | Funding Approval Case | Case for Change (S2), Benefits Map, ROI Driver Matrix | Funding Approval Case, Options Appraisal, Budget Envelope, Programme initiation authority
7 | Market Engagement & RFI | Capability Heatmap, Strategic Priorities, Budget Envelope | RFI, Vendor Longlist, Shortlist of 3–5, Reference Summaries
8 | Software Selection | Shortlist, Heatmap Scenarios, Guiding Principles, Scoring Weights | Scripted Demo Scores, PoC Results, Weighted Scoring Matrix, Preferred Vendor
9 | SI / Supplier Selection | Scope from Heatmap/Benefits Map, Governance Charter, RACI | Signed contracts, SI ROM estimate (±30%), fixed-price agreement for Setup & Design (S10–S12) (if applicable), SI team mapped into RACI, mobilisation plan
Notes: Inputs and outputs across the four stages. Each stage's outputs are the next stage's inputs. The thread runs from the Pre-Programme artefacts (Charter, Heatmap, Benefits Map) through Funding Envelope, RFI, Software Selection, SI Selection, into Programme Setup & Mobilisation (S10).
Walk left to right; the value is the linkage, not the detail. Pause where the Heatmap appears multiple times — that's the same artefact doing different jobs across stages.

## Slide 10
Roles & Responsibilities During Selection
Role | Selection Accountability
Executive Sponsor | Approves business case, signs off vendor and SI selection, chairs Steering Committee
Programme Manager | Runs selection process day-to-day, coordinates evaluations, manages vendor engagement
Business Architect | Maps Heatmap gaps to vendor capabilities, designs scripted demo scenarios, validates strategic fit
CFO / Finance | Validates business case financials, reviews commercial proposals, approves budget envelope
Procurement Lead | Manages RFI/RFP process, leads commercial negotiations, ensures compliance with procurement policy
Functional Leaders | Participate in scripted demos, score vendors against their process area, validate fit-to-purpose
Notes: Six roles, each with a distinct purpose.
Exec Sponsor: makes the final calls — business case approval, vendor selection, contract signing. Not delegated. If the Sponsor isn't available for a decision point, the decision waits.
Steering Committee: approves scoring weights, reviews shortlists, recommends to Sponsor.
Programme Manager: runs the day-to-day, owns the timeline, coordinates the workstreams.
Business Architect: anchors decisions back to the Heatmap and Benefits Map. The artefact-keeper.
Procurement: runs the commercial process — RFI/RFP issuance, contract drafting, negotiation support.
Functional Leaders: own scoring of vendors against their stream's gaps. They scored the Heatmap; they score vendors against it.
The role to watch: Procurement. They'll want to drive on commercial terms. The Exec Sponsor and BA must keep them anchored to capability fit, not lowest price.

## Slide 11
Selection Timeline
One real board gate (Funding Envelope & Benchmark Costs (S6)) plus three phase checkpoints — no stage begins without the previous outputs signed off
Week 1 4 5 10 11 18 19 24
Funding Envelope (S6): Funding Approval
Market Engagement & RFI (S7)
Software Selection (S8)
SI Selection (S9): SI / Supplier Selection
Week 4
BOARD GATE 1 · Funding
Week 10
Shortlist Checkpoint
Week 18
Preferred Vendor Checkpoint
Week 24
Contracts Signed
S6 (Wk 1–4)
Funding Envelope (Board Gate 1)
Options appraisal
Funding approval
S7 (Wk 5–10)
RFI issued
Responses evaluated
Shortlist agreed
S8 (Wk 11–18)
Scripted demos
Proof of concept
Preferred vendor selected
S9 (Wk 19–24)
RFP issued
SI evaluation
Contracts signed
Timeline is indicative. Duration depends on procurement complexity, number of vendors, and organisational approval processes. Stages can overlap where checkpoint dependencies are met.
Client BAs: Requirements Mapping
Wk 10: Draft Epics & Features
Wk 20: Draft User Stories & Traceability Matrix
Wk 24: Requirements Baseline to SI
Notes: 17 to 24 weeks is typical. The range depends on your organisation.
Funding Envelope & Benchmark Costs (S6) is fastest — you're building on Pre-Programme work.
Market Engagement & RFI (S7) needs 4 to 6 weeks because vendors need response time.
Software Selection (S8) is the longest — scripted demos, scoring, references.
SI Selection with ROM Pricing (S9) closes with the contract.
Worth flagging: you can run requirements mapping in parallel during Selection. Your BAs map current and target processes against the Heatmap while the vendor activity runs. By the time the SI starts Discovery, you've already done significant scope shaping.

## Slide 12
Executive Call to Action
Four decisions needed to begin the Selection phase
1
Approve the Funding Approval Case and confirm the budget envelope for Funding Envelope & Benchmark Costs (S6) gate
2
Agree the evaluation criteria and scoring weights before any vendor engagement begins
3
Commit named functional leaders to participate in scripted demos and scoring
4
Confirm the Decision Rights Framework governs all selection decisions — no informal commitments to vendors
“The pre-programme gave us the foundations. Selection is where we make the investment decisions. These decisions must be as rigorous as the foundations they are built on.”
Programme Lifecycle · Selection Phase · Stages 6–9
Notes: Four commitments to land. All about rigour.
1. Approve the business case and budget envelope. You can't engage the market without knowing what you can spend.
2. Confirm scoring weights for software and SI evaluation. Set by Steering Committee before any vendor activity.
3. Block calendars for scripted demos. Each vendor gets 1 to 2 days; you need the same Functional Leaders in every demo for valid comparison.
4. Commit to the timeline. 17 to 24 weeks. Don't compress to fit a board date — you'll get a worse decision.
These aren't asks for a future meeting. They're asks for the room, today.

## Slide 13
APPENDIX
Selection Playbook: Templates, Scoring Frameworks & Gate & Checkpoint Checklists
Stages 6–9 · Detailed reference for programme teams
Notes: Appendix is the Selection Playbook for the programme team — PM, BA, procurement. Each stage has the same structure: templates showing what to produce, scoring matrices, gate checklists. Reference material, not slides for the exec room.

## Slide 14
Funding Envelope (S6): Funding Approval Case — Recommended Structure
1. Executive Summary (1 page)
Strategic context, recommended option with headline financials, key risks
2. Strategic Alignment (1–2 pages)
Link to Vision Charter, Capability Heatmap summary, Operating Model Guardrails
3. Options Appraisal (2–3 pages)
Do Nothing, Incremental, Full Replacement, Best-of-Breed — each assessed on strategic fit, cost, risk
4. Financial Case (2–3 pages)
Benefits from Benefits Map, full cost breakdown, 3yr/5yr TCO, ROI, sensitivity analysis
5. Delivery Approach (1–2 pages)
Implementation approach, high-level timeline, resource requirements
6. Risk Assessment (1 page)
Top 10 programme risks with mitigations, dependencies and assumptions
7. Recommendation (1 page)
Recommended option, budget envelope requested, approval signatures
Appendix · S6 · Business Case Structure
Notes: This is the suggested structure for the full business case. Seven sections, typically 10 to 15 pages in total. Not 50 pages — executives will not read 50 pages.
The executive summary is one page maximum. If you can't summarise the case in one page, you don't understand it well enough. Lead with the recommendation, the headline financials, and the top 3 risks.
The options appraisal is where rigour matters most. Include at least three genuine options. For example: Option 1, do nothing — continue with the current platform, invest 200K per year in maintenance, accept the operational limitations. Option 2, incremental improvement — upgrade the current platform, address the top 5 Heatmap gaps through configuration, estimated cost 500K. Option 3, full replacement — implement a new platform addressing all Heatmap gaps, estimated cost 1.5M to 2.5M based on market benchmarks.
Assess each option against the same criteria: strategic fit, cost, risk, timeline, and benefit realisation potential. The Benefits Map provides the data to compare. If full replacement delivers 800K in annual benefits and incremental improvement delivers 300K, the investment case for replacement is clear.
The financial case must use real baseline data from the Benefits Map — not estimates. Include sensitivity analysis: what happens if benefits are 20 percent lower than forecast, or costs are 20 percent higher? If the case still works under pessimistic assumptions, it is robust.
If someone asks why we need an options appraisal when we already know we want a new ERP — the answer is governance and due diligence. Boards expect to see alternatives. Auditors expect to see alternatives. And sometimes the analysis genuinely reveals that incremental improvement is the right answer.

## Slide 15
Funding Envelope (S6): Funding Approval Gate Checklist
# | Criterion | Evidence Required | Approved By
1 | Full Business Case complete and board-ready | Business Case document | CFO
2 | Options appraisal with minimum 3 options | Options Appraisal section | Steering Committee
3 | Financial case validated by Finance | Finance sign-off on costs/benefits | CFO / Mgmt Accountant
4 | Budget envelope agreed | Board/IC approval | Executive Sponsor
5 | Named Executive Sponsor confirmed | Sponsor confirmation | CEO / Board
6 | Risk assessment reviewed | Risk register updated | Programme Manager
7 | Procurement approach agreed | Procurement plan | Procurement Lead
Notes: Seven criteria, all must be met. No exceptions, no partial passes.
Watch out for criterion is number 3 — Finance sign-off on costs and benefits. This is not a rubber stamp. The CFO or Management Accountant should validate the cost assumptions, challenge the benefit projections, and confirm the ROI model is sound. If Finance has not properly scrutinised the numbers, the business case will not survive board challenge.
Criterion 7, procurement approach agreed, is important to address early. Different organisations have different procurement rules — competitive tender thresholds, EU or public sector regulations, preferred supplier agreements. The Procurement Lead should confirm the approach at Funding Envelope & Benchmark Costs (S6) so that Market Engagement through SI Selection (S7–S9) comply from the start. Discovering a procurement policy issue at Software Selection (S8) can delay the programme by months.
If an executive asks whether we can start vendor conversations informally while the business case is being finalised — the answer is no. Informal conversations create expectations, leak budget information, and can compromise the competitive process. Engage the market formally at S7, not before.

## Slide 16
Market Engagement & RFI (S7): Recommended Structure and Content
Section 1: Organisation Overview
Brief description, strategic context (ref Vision Charter), scope, timeline
Section 2: Functional Requirements
Derived from Heatmap: for each Amber/Red stream, current state, target state, key questions
Section 3: Technical Requirements
Integration landscape, data volumes, cloud/hosting, security and compliance
Section 4: Vendor Information
Company overview, financial stability, sector experience, methodology, licensing, support
Section 5: Response Format
Structured template, deadline, submission instructions, clarification process
Example Functional Question (Section 2):
“Order-to-Cash is rated Red. Current order error rate is 8%. We need to reduce this to 2%. Describe how your platform supports order validation, automated credit checks, and exception management.”
Best Practice:
RFI should be 15–20 pages maximum — not a 100-page requirements document
Target 6–10 vendors maximum; RFI response period of 2–3 weeks
Use Heatmap to ask targeted questions, not generic feature comparisons
Appendix · S7 · RFI Template Structure
Notes: The RFI should be 15 to 20 pages. Not 100 pages. Vendors receive dozens of RFIs — they invest serious effort only in the ones that are well-structured and realistic.
Section 2, functional requirements, is the most important. This is where the Heatmap drives the conversation. For each process stream rated Amber or Red, we give the vendor specific context and specific questions.
For example, Procure-to-Pay is Amber with a 14-day cycle time. We write: Our current P2P cycle averages 14 days from requisition to payment. Key pain points include manual three-way matching, lack of spend visibility below 10K, and no automated approval routing. Describe how your platform addresses these specific gaps. What P2P cycle time reduction have comparable clients achieved?
Compare that to the generic alternative: describe your procurement module. The first version gets a detailed, useful response. The second gets a brochure.
Section 5, response format, matters more than people think. Provide a structured template — ideally a spreadsheet — so all vendors respond in the same format. This makes comparison dramatically easier and fairer. If one vendor writes 20 pages of prose and another fills in a structured table, comparing them is subjective. Standardise the format and you standardise the comparison.

## Slide 17
Market Engagement & RFI (S7): Evaluation Scoring Matrix — Example
Criteria Category | Weight | Vendor A | Vendor B | Vendor C
Functional fit against Heatmap gaps | 35% |  |  | 
Technical architecture & integration | 20% |  |  | 
Sector experience & reference sites | 15% |  |  | 
Licensing model & indicative cost | 15% |  |  | 
Vendor viability & platform roadmap | 10% |  |  | 
Support model & SLAs | 5% |  |  | 
Weighted Total | 100% |  |  | 
Scoring: 1 = Does not meet, 2 = Partially meets, 3 = Meets, 4 = Exceeds • Criteria weights agreed by Steering Committee BEFORE responses received • Scoring completed independently, then calibrated in moderation session • Shortlist decision is a Steering Committee decision
Notes: This matrix is the tool for evaluating RFI responses. The weights must be agreed by Steering Committee before any responses arrive.
The weighting reflects strategic priorities. Functional fit at 35 percent is deliberately the highest weight because the primary purpose of the ERP is to address capability gaps identified in the Heatmap. If a vendor is technically excellent but functionally weak in our priority areas, they are not the right choice.
Cost is weighted at 15 percent, not higher. This surprises some executives who expect cost to dominate. The reason: at the RFI stage, cost is indicative. Vendors give list prices that will change during negotiation. A vendor quoting 10 percent less at RFI may cost 20 percent more after implementation due to customisation requirements. We get real cost clarity at Software Selection (S8) and 9.
Scoring uses a simple 1 to 4 scale. 1 means does not meet the requirement. 4 means exceeds it. Avoid using 5-point scales with a middle option — evaluators default to the middle and you lose discrimination.
Each evaluator scores independently before the moderation session. In moderation, we discuss the outliers — where one evaluator scored 4 and another scored 2 on the same criterion. These are the most valuable discussions because they surface different interpretations and hidden risks.

## Slide 18
Market Engagement & RFI (S7): Shortlist Checkpoint Checklist
# | Criterion | Evidence Required | Approved By
1 | RFI responses received and evaluated | Completed scoring matrix | Programme Manager
2 | Shortlist of 3–5 vendors documented | Shortlist recommendation paper | Steering Committee
3 | Reference checks completed | Reference summary reports | Programme Manager
4 | Indicative terms within budget | Commercial summary | Procurement / CFO
5 | Scripted demo scenarios drafted | Demo scripts per process stream | Business Architect
6 | Software Selection (S8) evaluation criteria agreed | Weighted scoring matrix template | Steering Committee
Notes: Six criteria for the shortlist gate. Criterion 5 is the one most often forgotten — scripted demo scenarios must be drafted and agreed before we invite vendors to demonstrate.
If we wait until after shortlisting to create demo scripts, we lose 2 to 3 weeks. The BA should begin drafting scenarios as soon as the RFI is issued, using the highest-priority Heatmap process streams.
Criterion 6 requires the Software Selection (S8) evaluation weights to be agreed at this gate — before demos begin. This is a Steering Committee decision because it determines what matters most in the final selection. If the Steering Committee has not agreed the weights, the PM should not schedule demos.
For example, if the Steering Committee decides implementation approach should be weighted at 20 percent rather than 15 percent — perhaps because they have been burned by poor implementations before — that changes the evaluation dynamics. Make that decision now, not after the first demo when it could look like you are adjusting criteria to favour a particular vendor.

## Slide 19
Software Selection (S8): Scripted Demonstration — Approach & Best Practice
What is a Scripted Demo?
Vendors demonstrate against YOUR specific scenarios, not standard sales demos
Scenarios from Heatmap process streams rated Amber or Red
Each includes: context, process steps, data, expected outcome
How to Create Demo Scripts
Select 4–6 priority scenarios from Heatmap
Each scenario: 30–60 minutes including Q&A
Same data set to all vendors for consistency
Include at least one complex end-to-end scenario
Scoring Approach
Functional leaders score their own area independently
Use same 1–4 scale as RFI evaluation
Moderation session after all demos to calibrate
Document strengths, weaknesses, risks per vendor
Example Scenario Structure
Title: “Order-to-Cash with Multi-Currency”
Context: “We process 5,000 orders/month across 3 currencies. Current error rate: 8%”
Steps: Order creation → Credit check → Fulfilment → Multi-currency invoicing → Cash allocation → Exceptions
Expected outcome: “Demonstrate how the platform reduces order error rate from 8% to 2%”
Do not let vendors control the narrative. Give them your scenarios, your data, and your questions.
Appendix · S8 · Scripted Demonstration Approach
Notes: Scripted demos are the single most important evaluation activity. Everything else — RFI responses, analyst reports, reference visits — is secondary to seeing the software work against your actual business scenarios.
Creating good scripts takes effort. Select 4 to 6 priority scenarios from the Heatmap. Each scenario should run 30 to 60 minutes including Q&A. Provide the same sample data set to all vendors for consistency.
For example, an Order-to-Cash scenario might read: Your customer Acme Ltd places an order for 500 units across 3 product lines. 200 units ship from Warehouse A, 300 from Warehouse B. One line is back-ordered. The customer has a 30-day credit term but their account is 5 days overdue on a previous invoice. Show us: How does the system handle the split shipment? How does the credit check work — does it block the order, flag it, or escalate? How does the back-order process work? How does the invoice generate for the partial shipment? Walk us through the whole process end to end.
That level of specificity reveals how the software actually works, not how the sales team says it works. Vendors who welcome scripted demos are confident in their platform. Vendors who push back or try to redirect to their standard demo are telling you something important.
The right people must be in the room. For Finance scenarios, the Financial Controller and Management Accountant must attend and score. For Operations scenarios, the Operations Director and relevant Process Owners. If a functional leader sends a junior analyst who does not understand the current pain points, the scoring is worthless.
--- PRESENTER DEPTH ---
Vendor / LCS / FastTrack questioning of SI candidates: Ask SI candidates about their LCS / vendor engagement model. Will they secure FastTrack (or equivalent) for the Client if eligible? How does that affect their pricing? An SI that says 'we don't engage with FastTrack' or 'that's the Client's responsibility' is signalling either a gap in their capability or a desire to bill for what Microsoft would have funded for free. Lock the answer into the SOW at SI Selection (S9).

## Slide 20
Software Selection (S8): Weighted Scoring Matrix
Criteria Category | Weight | Sub-Criteria | Vendor A | Vendor B
Functional Fit | 35% | Heatmap gap coverage, scripted demo scores, fit-to-standard |  | 
Technical | 20% | Architecture, scalability, integration, data migration tooling |  | 
Implementation | 15% | Methodology, accelerators, timeline credibility |  | 
Commercial | 20% | Licence cost (3yr/5yr TCO), implementation cost, support cost |  | 
Vendor Viability | 10% | Financial stability, platform roadmap, sector commitment |  | 
Weighted Total | 100% |  |  | 
• PoC results factored into functional fit score • Commercial scoring uses TCO over 3 and 5 years, not just licence cost • Lowest-cost vendor is NOT automatically best value
Notes: This is the detailed scoring matrix for software selection. It breaks each category into sub-criteria for more granular evaluation.
Functional fit at 35 percent has three sub-criteria: Heatmap gap coverage, scripted demo scores, and fit-to-standard. Fit-to-standard is important — it measures how much of our requirement the vendor meets with standard configuration versus how much requires customisation. A vendor that covers 90 percent of our needs out of the box scores higher than one that covers 100 percent but requires 30 percent customisation.
Commercial at 20 percent must use total cost of ownership, not just licence price. TCO includes: licence costs over 3 and 5 years, implementation costs, change management costs, ongoing support and maintenance, and estimated customisation costs. The cheapest licence is often the most expensive TCO.
For example, Vendor A quotes 200K annual licence with a 1.5M implementation estimate. Vendor B quotes 300K annual licence but their out-of-the-box fit is so strong that implementation is estimated at 800K. Over 5 years: Vendor A costs 2.5M total, Vendor B costs 2.3M total. Vendor B is cheaper despite the higher licence.
Proof of concept results should be factored into the functional fit score. If we ran a PoC for multi-entity consolidation and one vendor handled it flawlessly while another required workarounds, that evidence should directly affect the scoring — not be treated as a separate data point.

## Slide 21
Software Selection (S8): Preferred Vendor Checkpoint Checklist
# | Criterion | Evidence Required | Approved By
1 | All shortlisted vendors completed scripted demos | Demo evaluation forms per vendor | Programme Manager
2 | PoC completed for high-risk areas (if required) | PoC results and findings report | Business Architect
3 | Weighted scoring matrix completed and moderated | Final scoring matrix with commentary | Evaluation Panel
4 | Preferred vendor recommendation documented | Vendor recommendation paper | Programme Manager
5 | Commercial terms agreed in principle | Commercial summary | Procurement Lead
6 | No unresolved high-risk findings | Risk assessment per vendor | Programme Manager
7 | Steering Committee approval | Steering Committee minutes | Executive Sponsor
Notes: Seven criteria for the preferred vendor gate. This is the most consequential gate decision in the entire Selection phase.
Criterion 4, the vendor recommendation paper, is the document that must withstand scrutiny. It should include: the scoring matrix results, the rationale for the recommendation, a summary of strengths and weaknesses of the preferred vendor, key risks and mitigations, and a comparison with the runner-up. If a board member or auditor asks why this vendor was chosen 2 years from now, this paper is the answer.
Criterion 6, no unresolved high-risk findings, is where the PM must be honest. If the proof of concept revealed a significant limitation — for example, the platform can't handle a critical integration natively — that risk must be resolved or formally accepted by Steering Committee before proceeding. Burying it in the risk register and hoping for the best is not acceptable.
If the scoring is very close between two vendors — say within 5 percent — consider a best and final offer round before making the decision. Give both vendors the opportunity to sharpen their commercial proposal and address specific concerns raised during evaluation.

## Slide 22
SI Selection (S9): RFP for Systems Integrator — Recommended Structure
Section 1: Programme Overview
Organisation context, strategic objectives (Vision Charter), programme scope, governance framework the SI must operate within
Section 2: Scope of Work
Implementation by workstream (Heatmap streams), data migration, integration scope, change management, hypercare requirements
Section 3: Delivery Expectations
Methodology preference, timeline, governance integration (Design Authority, SteerCo), quality standards, knowledge transfer
Section 4: Team Requirements
Named key personnel (PD, SA, Func. Leads), CVs required, minimum experience, onshore/offshore mix, resource continuity
Section 5: Commercial Model
Preferred model (fixed/T&M/capped/hybrid), milestone payments tied to deliverables, rate card, warranty period
Section 6: Response Requirements
Proposal structure, page limits, pricing template for comparison, minimum 3 reference sites, deadline
Critical RFP Best Practices:
Insist on named key personnel with CVs — interview the actual team who will deliver, not the sales team
SI must operate within your governance framework — Design Authority and Steering Committee as defined in RACI
Provide a standard pricing template so proposals are comparable — avoid bespoke formats that hide costs
Appendix · S9 · RFP Structure
Notes: The RFP is the most detailed document in the Selection phase. Unlike the RFI, which asks about capability, the RFP asks for a specific proposal to deliver.
Section 4, team requirements, is where most organisations don't push hard enough. Do not accept a proposal that says experienced consultants will be assigned. Insist on named individuals with CVs. For the Project Director and Solution Architect at minimum, require interviews before you select.
For example, an RFP team requirements section might read: The Programme Director must have delivered at least 2 ERP implementations of comparable scope and complexity within the last 5 years. Provide their CV and 2 client references. They must be available to commit a minimum of 80 percent of their time for the first 6 months. Replacement of the Programme Director requires written approval from our Executive Sponsor.
Section 5, commercial model, should explain the options honestly. Fixed price gives cost certainty but reduces flexibility — change requests become expensive negotiations. Time and materials gives flexibility but no cost ceiling — the SI has less incentive to be efficient. Capped time and materials is often the best compromise — flexibility within a defined envelope. Ask the SI to propose their preferred model with rationale, and compare.
Section 1 should reference the Vision Charter and governance framework but should not share the full Benefits Map or detailed financial data with bidders. They need enough context to scope accurately but not so much that they know your budget ceiling.
--- PRESENTER DEPTH ---
Vendor / LCS / FastTrack questioning of SI candidates: Ask SI candidates about their LCS / vendor engagement model. Will they secure FastTrack (or equivalent) for the Client if eligible? How does that affect their pricing? An SI that says 'we don't engage with FastTrack' or 'that's the Client's responsibility' is signalling either a gap in their capability or a desire to bill for what Microsoft would have funded for free. Lock the answer into the SOW at SI Selection (S9).

## Slide 23
SI Selection (S9): Evaluation Scoring Matrix — Example
Criteria Category | Weight | Description
Delivery capability & methodology | 25% | Approach, tooling, accelerators, quality assurance, risk management
Sector & platform experience | 20% | Comparable implementations, reference site quality, platform certification level
Proposed team quality | 20% | Named personnel experience, CV review, interview performance, continuity commitment
Commercial model & value | 20% | TCO, pricing structure, payment terms, flexibility, warranty
Cultural fit & partnership | 15% | Communication style, collaboration approach, escalation handling, knowledge transfer
Interview the actual team
Proposed Project Director and Solution Architect determine success more than any other factor
Check references independently
Do not rely solely on the references the SI provides — call independently
Evaluate the team, not the brand
A tier-1 SI with a weak team will underperform a mid-tier SI with an excellent team
Appendix · S9 · SI Evaluation Criteria
Notes: Five criteria, weighted to reflect what actually determines implementation success.
Proposed team quality at 20 percent deserves emphasis. Research consistently shows that the quality of the delivery team is the single biggest predictor of implementation success — more than methodology, more than the SI’s brand, more than price. A tier-1 SI with a weak team will underperform a mid-tier SI with an excellent team.
Interview the proposed Project Director. Ask them: walk me through the last implementation that went wrong and what you did about it. Tell me how you would approach our most complex Heatmap scenario. What would you do in the first 2 weeks of mobilisation? Their answers tell you far more than their CV.
Cultural fit at 15 percent is not soft. It determines whether the SI will tell you hard truths or tell you what you want to hear. Ask during the interview: describe a time you told a client they were wrong. If they can't give a convincing example, they will not challenge your team when it matters — and they will raise change requests instead.
For example, an SI that scores well on cultural fit might say in the interview: on our last programme, the client wanted to customise 40 percent of the platform. We pushed back hard and showed them the cost and risk implications. We agreed on 15 percent customisation with a formal review process for each request. The client was not happy initially but the programme delivered on time and on budget. That is the kind of partner you want.
--- PRESENTER DEPTH ---
Vendor / LCS / FastTrack questioning of SI candidates: Ask SI candidates about their LCS / vendor engagement model. Will they secure FastTrack (or equivalent) for the Client if eligible? How does that affect their pricing? An SI that says 'we don't engage with FastTrack' or 'that's the Client's responsibility' is signalling either a gap in their capability or a desire to bill for what Microsoft would have funded for free. Lock the answer into the SOW at SI Selection (S9).

## Slide 24
SI Selection (S9): Contract & Statement of Work — Essentials Checklist
Area | Must Include
Scope | Defined scope with explicit inclusions/exclusions; change control mechanism for scope changes
Commercials | Milestone-based payments tied to deliverable acceptance; rate card for change requests; cap on expenses
Team | Named key personnel with minimum commitment period (6–12 months); replacement requires Client Executive Sponsor approval; resource continuity clause; SI must provide: Programme Director, Solution Architect (DA co-chair), Functional Lead per workstream, Technical Lead, Data Migration Lead, Scrum Master
Quality | Deliverable acceptance criteria; defect classification and resolution SLAs; warranty period (min. 12 months)
Governance | SI Programme Director attends Steering Committee monthly with delivery status report; SI Solution Architect co-chairs Design Authority bi-weekly; SI operates within Client’s Decision Rights Framework; all scope changes governed by DA
IP & Data | Clear IP ownership of deliverables and configurations; data ownership and return provisions; GDPR compliance
Exit | Termination provisions (for cause and convenience); transition and knowledge transfer obligations; data extraction rights
Performance | KPIs for SI delivery performance; remedies for underperformance; earn-back or penalty mechanisms
Design Authority | SI Solution Architect named as co-chair of Design Authority; SI attendance at all DA meetings is mandatory; DA decisions are binding on the SI; SI cannot build anything DA has not approved
Knowledge Transfer | Mandatory KT plan with defined deliverables; co-delivery with Client team (not SI-only build); formal KT period before SI exit; all configuration documented with rationale; Client team capable of BAU support before SI disengages
Commercial Phasing | Separate commercial agreement for Discovery & Design (Setup & Design (S10–S12)) and Build & Test (Build & Test (S13–S14)). SI provides ROM for end-to-end at SI Selection with ROM Pricing (S9). Firm pricing for Build & Test confirmed after S12 Design Authority sign-off. Board approval gate before build commitment.
Notes: The commercial phasing clause protects the organisation from committing to build costs before they are known. The SI prices Discovery and Design as a fixed-price or capped engagement — this is typically 15 to 20 percent of the total programme cost. Build and Test pricing is confirmed after Design is complete, when the SI knows exactly what they are building. This gives the board a genuine decision point at Solution Design & Full Business Case (S12): here are the firm costs, here are the confirmed benefits, do we proceed?
--- PRESENTER DEPTH ---
Vendor / LCS / FastTrack questioning of SI candidates: Ask SI candidates about their LCS / vendor engagement model. Will they secure FastTrack (or equivalent) for the Client if eligible? How does that affect their pricing? An SI that says 'we don't engage with FastTrack' or 'that's the Client's responsibility' is signalling either a gap in their capability or a desire to bill for what Microsoft would have funded for free. Lock the answer into the SOW at SI Selection (S9).

## Slide 25
SI Selection (S9): Programme Initiation Checkpoint Checklist
# | Criterion | Evidence Required | Approved By
1 | SI proposals evaluated and scored | SI scoring matrix | Evaluation Panel
2 | Key personnel interviewed and approved | Interview assessment forms | Programme Manager
3 | References checked independently | Reference check summaries | Programme Manager
4 | Preferred SI selected with documented rationale | SI recommendation paper | Steering Committee
5 | Contracts and statements of work signed | Signed contracts | Exec Sponsor / Legal
6 | SI team mapped into programme RACI | Updated RACI | Programme Manager
7 | Programme Setup & Mobilisation (S10) mobilisation plan agreed | Mobilisation plan | PM / SI
8 | Programme initiation meeting scheduled | Calendar confirmation | Programme Manager
9 | SI governance integration confirmed in contract (DA co-chair, SC attendance, Decision Rights) | Contract clauses | Client PM + Legal
10 | Requirements Baseline Documents complete and ready for SI handover | Requirements baseline per process stream, traceability matrix | BA Lead
11 | SI ROM estimate received and within Funding Envelope range | SI ROM document | PM + CFO
12 | Commercial phasing agreed — firm pricing for Setup & Design (S10–S12), ROM for Stages 13+ | Contract commercial schedule | Procurement Lead + CFO
Completion of SI Selection with ROM Pricing (S9) marks the end of the Selection phase. Programme Setup & Mobilisation (S10) (Programme Setup & Mobilisation) begins. The Design Authority activates at S9 completion.
Appendix · S9 · Programme Initiation Checkpoint
Notes: Eight criteria for the programme initiation gate. This is the final gate before Programme Setup & Mobilisation (S10) mobilisation — the last checkpoint before significant expenditure begins.
Criterion 6, SI team mapped into programme RACI, is easy to overlook but essential. The SI does not operate as a separate entity — their Project Director reports to your Steering Committee, their Solution Architect sits in your Design Authority, their functional consultants are assigned to your workstreams. If the RACI does not explicitly include the SI team, accountability gaps will emerge in the first month.
Criterion 7, S10 mobilisation plan agreed, should be a joint document between your PM and the SI. It covers: team onboarding, environment provisioning, governance activation, kick-off workshops, and the first 4 weeks of activity. If the SI can't produce a credible mobilisation plan before contract signature, question their readiness to deliver.
If all eight criteria are met, the Selection phase is complete. The Design Authority activates, the SI team integrates into the programme structure, and S10 begins. This is the moment the programme transitions from planning to delivery — and everything we built in the pre-programme and selection phases is put to work.
Criterion 9 confirms that the governance integration we need from S10 onwards is contractually committed — not just discussed in principle. If the contract does not specify DA co-chair, mandatory SC attendance, and binding DA decisions, the governance framework will be difficult to enforce once the SI is on site.
Criterion 10 confirms the Client-side requirements mapping is complete and ready for handover. The SI should receive the Requirements Baseline Documents as part of their onboarding pack at S10. If the requirements mapping is not finished — perhaps because the organisation is large and the work took longer than expected — identify which process streams are complete and which need finishing during S10 mobilisation.

## Slide 26
Roles & Responsibilities Across the Selection Stages
Role | S6: Business Case | S7: RFI | S8: Software Selection | S9: SI Selection
Executive Sponsor | Approves business case, confirms budget | Approves shortlist | Approves preferred vendor | Signs contracts, authorises initiation
Programme Manager | Coordinates business case, manages approvals | Manages RFI process, coordinates evaluation | Runs demo logistics, manages scoring | Manages RFP, coordinates negotiation
Business Architect | Validates strategic alignment, maps Heatmap | Designs RFI questions from Heatmap | Creates scripted demos, validates fit | Maps scope to Heatmap, validates SI approach
CFO / Finance | Validates financials, confirms budget | Reviews indicative pricing | Reviews commercial proposals | Approves commercial terms
Procurement Lead | Advises procurement approach | Manages vendor engagement, issues RFI | Manages commercial negotiations | Leads contract negotiation
Functional Leaders | Input from Benefits Map | Score RFI for their area | Score demos for their process area | Validate SI approach for their function
Management Accountant | Supports cost modelling, TCO | Reviews vendor cost structures | Validates TCO calculations | Reviews contract financial terms
Notes: This matrix shows who does what across all four stages. Use it as a reference when assigning people to selection activities.
The pattern to notice: the Executive Sponsor bookends each stage with approval decisions but is not involved in day-to-day evaluation. The PM coordinates everything. The BA provides strategic validation at every stage. Functional Leaders are most active during Market Engagement & RFI (S7) and Software Selection (S8) when vendor responses and demos need expert assessment. Procurement runs the formal process and commercial negotiations.
The Management Accountant row is worth flagging. TCO analysis and cost structure validation is detailed, time-consuming work. It should not fall to the CFO — they need to review and approve, not build the models. The Management Accountant does the analytical heavy lifting across all four stages.
If someone asks about total time commitment for functional leaders — it is roughly 1 to 2 days for RFI scoring in S7, 4 to 5 days for demos and scoring in S8, and half a day for SI approach validation in SI Selection with ROM Pricing (S9). That is 6 to 8 days over 12 to 16 weeks. It is not trivial, but it is the difference between a selection based on evidence and one based on assumption.