## Slide 1
Setup & Design
Setup & Design (S10–S12): From Mobilisation to Approved Design
Programme Lifecycle · Setup & Design Phase · Stages 10–12
Notes: This deck covers the first three stages of delivery — from the moment the SI is on board through to approved solution designs ready for build.
Programme Setup & Mobilisation (S10) sets up the programme: team structure, environments, governance cadence, Agile working agreements with the SI. Discovery (S11) is detailed requirements, gap analysis, and product backlog. Solution Design & Full Business Case (S12) is functional design, technical architecture, data migration design — all signed off by Design Authority.
The SI is embedded throughout. Vendor deployment services (LCS, FastTrack, SAP Activate, Oracle CSM, Workday Launch) become operationally relevant from S10 onwards — that's the "third pillar" alongside Client and SI. End of S12 is Board Gate 2 — the second of two board funding decisions. Worth flagging that gate up front.

## Slide 2
Why Setup & Design Governance Matters
Ensure the SI delivers designs that are traceable to strategic outcomes, governed by Design Authority, and ready for a controlled build phase.
Three risks when setup and design are ungoverned
Scope drift: Discovery becomes open-ended — the SI documents everything without filtering against the Benefits Map
Design by committee: Workshops produce conflicting views, nobody has the mandate to decide
SI independence: The SI makes design decisions without Design Authority approval
What governed setup and design ensures
SI team embedded in the RACI from day one — not a separate workstream
Design Authority (co-chaired by Client and SI) approves every decision against the Benefits Map
Gap analysis uses a clear decision framework: fit, process change, workaround, or customise
Product backlog traces every User Story to a Feature, every Feature to an Epic, every Epic to the Benefits Map
“The SI delivers. Design Authority governs. If the SI makes design decisions outside governance, the programme loses control of scope, cost, and value.”
Programme Lifecycle · Setup & Design Phase · Stages 10–12
Notes: The SI relationship is a partnership but it needs governance. Without it, three things happen.
Scope drift. I worked with an organisation where the SI ran 6 weeks of Discovery workshops with 80 stakeholders, documented over 400 requirements. Nobody filtered them against the Benefits Map or the Guiding Principles. Original scope was 120 requirements. The SI was happy — more scope means more revenue. The programme team was drowning. When Design Authority finally reviewed the backlog, 40 per cent of requirements were out of scope or low value. Six weeks of work was partly wasted.
Design by committee. Multiple stakeholders weighing in on every design decision, no clear owner, designs relitigated every fortnight. Build starts with conflicting designs, rework consumes 30 per cent of effort.
SI marking their own homework. Without strong DA, the SI signs off their own designs. Quality drops, scope creeps, the Client team realises too late that what's being built isn't what was needed.
Governance prevents all three. DA is the discipline that makes the SI relationship work.

## Slide 3
What This Deck Covers
Core Slides (1–16)
Why setup and design governance matters
Three stages: Setup & Mobilisation, Discovery, Solution Design
SI team integration and governance
Design Authority operating model (Client + SI co-chaired)
Gap analysis decision framework
Agile backlog structure: Epics, Features, User Stories
Roles (Client + SI), timeline, and decision gates
Appendix — Setup & Design Playbook (Slides 17+)
Mobilisation checklist with SI onboarding tasks
Discovery workshop approach (Client + SI facilitation)
Gap analysis templates and decision framework
User Story writing guide with good and bad examples
FDD structure and Design Authority sign-off process
Design Authority operating procedures
Stage gate checklists for Stages 10, 11, and 12
Illustrative — to be adapted to your SI's methodology, programme Agile maturity, and organisational context
Notes: Map for the deck. First 17 slides are the strategic walkthrough for the room — what we're doing in S10 to S12, who does what, what gets signed off. Appendix from slide 18 is the Setup & Design Playbook for the team — checklists, gap analysis frameworks, FDD structures, gate criteria.

## Slide 4
Stages 10–12 at a Glance
Stage | Name | Key Output | Duration
10 | Programme Setup & Mobilisation | Teams onboarded (Client + SI), environments provisioned, governance live | 2–4 weeks
11 | Discovery | As-is process maps, gap analysis, product backlog, integration catalogue | 4–6 weeks
12 | Solution Design | FDDs signed off by DA, technical architecture, data migration design, prototype | 6–8 weeks
Total Setup & Design duration: typically 12–18 weeks
Pre-requisite: SI contract signed, named personnel confirmed, SI Selection with ROM Pricing (S9) complete
Output: Approved designs ready for Sprint 0 and Build (Build & Configuration (S13))
Programme Lifecycle · Setup & Design Phase · Stages 10–12
Notes: Three stages, brisk overview.
Programme Setup & Mobilisation (S10): 4 to 6 weeks. Mobilise teams, provision environments, agree governance cadence with the SI, confirm vendor service tier (LCS / FastTrack / Activate / etc).
Discovery (S11): 6 to 10 weeks. Joint Client–SI workshops. Detailed requirements, gap analysis, product backlog.
Solution Design & Full Business Case (S12): 6 to 10 weeks. FDDs per workstream, technical architecture, data migration design. End with Board Gate 2 — the Full Business Case with firm SI build and test pricing.

## Slide 5
Programme Setup & Mobilisation (S10)
Key Objectives
Onboard Client programme team and SI delivery team
Map all SI roles into the programme RACI — named individuals
Provision environments (development, test, staging, production)
Activate governance cadence — SC monthly, DA bi-weekly
Establish Agile working agreements (sprint length, ceremonies, DoD)
Confirm scope prioritisation matrix against Benefits Map
Outputs
Programme team structure with named Client and SI individuals
Updated RACI with all SI roles mapped
Environments provisioned and tooling in place
Governance cadence live (SC and DA scheduled)
Agile working agreements signed by Client PM and SI Programme Director
Scope prioritisation matrix confirmed
“The SI team is mapped into the RACI from day one. They attend Design Authority, run sprint ceremonies, and are governed by the same Decision Rights Framework as the Client team.”
Programme Lifecycle · Setup & Design · S10
Notes: Programme Setup & Mobilisation (S10) is where the SI shows up and the programme actually starts running. Four things to land:
Team structure. SI roles mapped into the RACI from day one — named individuals, not generic roles.
Environments. Development, test, staging, production all provisioned. IT often underestimates how long this takes; if you don't start at S10, the SI sits idle.
Governance cadence. Design Authority calendar set, sprint ceremonies agreed, escalation paths confirmed.
Vendor service tier. This is where you confirm Microsoft FastTrack, SAP Activate level, Oracle CSM engagement, Workday Launch — the third pillar. It runs alongside the SI, not instead of them.
Gate at end of S10: Governance Live. Without that gate, you can't start Discovery cleanly.

## Slide 6
Vendor Deployment Services: The Third Pillar
What it is
Every major ERP platform has its own vendor-led delivery framework that runs alongside your SI. These aren’t optional — the vendor methodology shapes what’s possible, what’s supported, and what isn’t.
Why it matters
Cutting across vendor services or working without them creates support gaps post-go-live. Build it into your governance from Programme Setup & Mobilisation (S10), not after the fact.
Platform | Vendor Service | Owner | When it engages
Microsoft D365 | Lifecycle Services (LCS) + FastTrack | Microsoft FastTrack Solution Architect | From S10, peak S11–S15
SAP S/4HANA | SAP Activate + SAP MaxAttention / Premium Engagement | SAP CTM (Customer Team Manager) | From S10, peak S11–S16
Oracle Cloud ERP | Oracle Cloud Implementation Methodology + Customer Success | Oracle CSM | From S10, peak S11–S15
Workday | Workday Launch / Tenant Lifecycle Management | Workday Engagement Manager | From S10, peak S11–S15
See Command Centre — Vendor & Platform tab — for full RACI and decision framework.
Programme Lifecycle · Setup & Design · S10
Notes: New slide flagging vendor deployment services as the third pillar.
Land the point clearly: every major ERP platform has its own vendor-led delivery framework that runs alongside your SI. These aren't optional. The vendor methodology shapes what's possible, what's supported, and what isn't.
Walk the table briefly: D365 has LCS plus FastTrack, owned by the FastTrack Solution Architect. SAP has Activate plus MaxAttention or Premium Engagement, owned by the CTM. Oracle has the Cloud Implementation Methodology plus Customer Success, owned by the CSM. Workday has Launch and Tenant Lifecycle Management, owned by the Engagement Manager.
Common trap: cutting across vendor services or working without them. Creates support gaps post-go-live. Build it into governance from S10, not after the fact. Refer the room to the Command Centre Vendor & Platform tab for the full RACI.

## Slide 7
Discovery (S11)
Key Objectives
Gather detailed requirements by workstream through joint Client + SI workshops
Document as-is process maps with pain points (Client leads, SI observes)
Complete gap analysis: standard capability vs requirements (SI leads, Client validates)
Build product backlog as Epics, Features, and User Stories
Confirm integration catalogue with technical approach per interface
Complete data assessment with migration strategy
Outputs
As-is process maps per workstream (joint Client + SI)
Gap analysis per workstream: fit, process change, workaround, customise
Product backlog: Epics → Features → User Stories
Integration catalogue with technical approach (SI Technical Lead)
Data assessment with migration strategy (SI Data Migration Lead)
“Discovery is joint. The Client owns the business knowledge. The SI owns the platform knowledge. Gap analysis brings the two together.”
Programme Lifecycle · Setup & Design · S11
Notes: Discovery (S11) is where requirements get nailed down. Joint Client–SI workshops. Worth flagging two things up front:
One — Process Owners and SMEs are NOT interchangeable. Process Owners own the business outcome and sign off the work. SMEs know how the work is currently done. You need both, doing different jobs.
Two — gap analysis runs every requirement against the platform. Three outcomes: out-of-the-box (no work), configuration (settings only), customisation (build). The configuration vs customisation call sits with Design Authority. Default to out-of-the-box; treat customisation as exception, not norm.
Output is the product backlog: epics, features, user stories — all traceable to the Benefits Map.

## Slide 8
Epics → Features → User Stories
EPIC
Maps to a Benefits Map outcome. Owned by a Benefit Owner.
Example: ‘Order-to-Cash Transformation’
FEATURE
A deliverable capability within an Epic. Owned by a Process Owner.
Example: ‘Automated Credit Check at Order Entry’
USER STORY
As a [role], I want [action], so that [benefit]. With acceptance criteria.
Example: ‘As a Credit Controller, I want automated credit checks’
Who creates what
Epics: Client BA maps to Benefits Map, agreed at Steering Committee
Features: Joint — SI Functional Lead proposes, Client Process Owner validates
User Stories: Joint — SI drafts, Client Process Owner reviews acceptance criteria
Governance thread
Epic → Benefits Map → Steering Committee
Feature → Epic → Design Authority
User Story → Feature → Scrum Master / Product Owner
Programme Lifecycle · Setup & Design Phase · Stages 10–12
Notes: The structure: Epics roll up to a strategic outcome. Features sit under epics — distinct pieces of capability. User stories sit under features — granular, sized for a sprint.
Worth landing for the room: every user story traces upward to a benefit. No benefit, no story. That's the discipline that prevents scope drift.
Common trap: writing user stories without epics. The result is a flat backlog of 600 stories, no narrative, no prioritisation logic. Always start at epic.

## Slide 9
Writing Effective User Stories
Structure: As a [role], I want [capability], so that [business value]
✘ Bad Examples
Finance
“The system should do month-end close faster.”
No role, no specific capability, not testable. The SI cannot build from this.
Operations
“We need better inventory management.”
Vague, no user, no testable outcome. The SI will interpret differently.
Sales
“Credit checks need to be automatic.”
No user context, no exception handling. The SI builds the happy path only.
✔ Good Examples
Finance
“As a Financial Controller, I want the system to generate all recurring journals automatically at period end, so that I can reduce manual entry from 3 days to 4 hours.”
AC: Templates configurable • Auto-generated day 1 • Failed journals flagged <1hr • Completes <4hrs for 200 journals
Operations
“As a Warehouse Manager, I want the system to trigger automatic reorder notification when stock falls below threshold, so I can prevent stock-outs.”
AC: Threshold per product/warehouse • Email + system alert • Triggers <15 min
Sales
“As a Sales Order Processor, I want automatic credit checks on order entry, so overdue accounts are flagged before I commit stock.”
AC: Auto-trigger • Over-limit orders held • Release by Credit Controller only • <3 sec
SI Functional Leads draft User Stories. Client Process Owners review and own the acceptance criteria.
Notes: A good user story is small, testable, and benefit-linked. The format: As a [role], I want [capability], so that [benefit].
Watch for stories that lack the "so that" — those are scope items, not stories. The "so that" is the reason this matters. If nobody can write it, the story shouldn't be in the backlog.
Acceptance criteria sit on the story. They're how the SI knows when it's done and how the Client Test Manager builds test cases. Without acceptance criteria, "done" is a negotiation, not a definition.

## Slide 10
Design Authority: Client + SI Co-Governance
Govern every design and scope decision against the Benefits Map, Guiding Principles, and approved architecture.
Co-chairs: Solution Architect + SI Solution Architect
Cadence: Bi-weekly, 90 minutes
Members: Client BA, SI Functional Leads, Client Process Owners, SI Technical Lead
Standing Agenda
Design decisions requiring approval (20 min)
Customisation requests — SI cost-benefit, DA decides (30 min)
Scope changes assessed against Benefits Map (20 min)
Integration and architecture decisions (15 min)
Actions and next meeting preparation (5 min)
Gap Type | Decision | Who Proposes | Who Decides
Fit | Configure standard — no DA approval needed | SI Functional Lead | SI Functional Lead
Process Change | Adapt business process to match platform | SI Functional Lead | Design Authority
Workaround | Use standard tools (Power Automate etc.) | SI Functional Lead | Design Authority
Customise | Custom dev — cost-benefit required | SI Functional Lead | Design Authority
Key rule: The SI does not build anything that Design Authority has not approved. No exceptions.
Programme Lifecycle · Setup & Design Phase · Stages 10–12
Escalation
If DA cannot reach consensus, escalate to Steering Committee. Do not delay design — park the item and continue with agreed scope.
Decision Framework
See table below — the SI Functional Lead identifies gaps and proposes the approach. Design Authority decides for anything beyond standard configuration.
Notes: Design Authority is the discipline that makes everything else work. It's the joint Client + SI body where every design decision lands.
Membership: Client Solution Architect, SI Solution Architect, Functional Leaders for the workstream, Business Architect. Not 15 people — usually 6 to 8.
Cadence: weekly during S11–S12, then twice-weekly during build for change control.
The thing to flag hard: DA decisions are binding. If the SI builds something DA hasn't approved, the programme has lost control of scope. And if the Client team raises a design change after DA sign-off, it goes back through DA — no shortcuts.
Worth pausing on: this is co-governance, not Client-led. The SI Solution Architect is in the room, not waiting outside it.

## Slide 11
Solution Design & Full Business Case (S12)
Key Objectives
SI Functional Leads produce FDDs per workstream
SI Solution Architect confirms technical architecture and integration design
SI Data Migration Lead designs migration approach and cleansing rules
DA (Client + SI co-chaired) reviews and signs off all designs
SI demonstrates prototype of key scenarios to Process Owners
All customisation decisions documented with DA rationale
Outputs
Functional Design Documents per workstream (DA signed off)
Technical architecture document (SI Solution Architect)
Integration design per interface (SI Technical Lead)
Data migration design with cleansing rules
Prototype reviewed and approved by Process Owners
DA decision log — all customisation decisions with rationale
“Every design decision passes through Design Authority. If it is not in the FDD and signed off, it does not get built. No exceptions.”
Programme Lifecycle · Setup & Design · S12
Notes: Solution Design & Full Business Case (S12) is the final design phase before build. SI Functional Leads produce FDDs per workstream. SI Solution Architect confirms technical architecture and integration design. SI Data Migration Lead designs migration approach, cleansing strategy, validation rules.
Everything signed off by Design Authority. Nothing goes into Build & Configuration (S13) without DA sign-off.
End of S12 is the second Board Gate. The Full Business Case lands here — firm SI build and test pricing at plus-or-minus 10 to 15 per cent. This is the real investment decision, not the original board approval. Worth flagging that distinction loud.

## Slide 12
Inputs & Outputs Across Stages 10–12
# | Stage | Key Inputs | Key Outputs
10 | Setup & Mobilisation | SI contract, RACI, mobilisation plan, scope matrix | Team structure (Client + SI), environments, governance cadence, Agile agreements
11 | Discovery | Heatmap, Benefits Map, Guiding Principles, SI platform knowledge | As-is maps, gap analysis, product backlog, integration catalogue, data assessment
12 | Solution Design | Gap analysis, backlog, technical architecture, SI best practice | FDDs (DA signed off), prototype, data migration design, integration design, DA log
Programme Lifecycle · Setup & Design Phase · Stages 10–12
Notes: Inputs and outputs across S10–S12. Each stage's outputs feed the next. Walk the linkage left to right; the value is the chain. Spend a moment on the FDDs at S12 — that's the artefact set that drives every build sprint.

## Slide 13
Roles & Responsibilities During Setup & Design
Role | S10: Setup | S11: Discovery | S12: Design
Executive Sponsor | Confirms team, activates governance | Reviews progress at Steering | Approves DA decisions via Steering
Programme Manager | Runs mobilisation, establishes cadence | Manages workstream coordination | Manages design review schedule
Project Manager(s) | Confirms workstream team and plan | Manages workstream discovery | Manages workstream design delivery
Solution Architect | Co-activates DA with SI SA | Validates integration approach | Co-chairs DA, co-signs architecture
Business Architect | Confirms scope prioritisation | Leads gap analysis (business side) | Validates strategic fit of designs
Process Owners | Confirm workstream scope | Provide requirements, validate as-is | Review and sign off FDDs
Change Lead | Plans change approach | Assesses change impact | Begins training strategy
Client Test Manager | Drafts test strategy | Identifies test scenarios | Designs test cases from FDDs
SI Programme Director | Onboards SI team, agrees agreements | Manages SI resource allocation | Manages SI delivery to DA schedule
SI Solution Architect | Co-activates DA, confirms tech arch | Leads gap analysis (platform side) | Co-chairs DA, produces arch doc
SI Functional Leads | Familiarise with Heatmap/Benefits Map | Co-facilitate workshops, document gaps | Produce FDDs, demonstrate prototype
SI Technical Lead | Confirms integration approach | Designs integration catalogue | Produces integration design docs
SI Data Migration Lead | Begins data assessment | Completes data assessment | Produces migration design
SI Scrum Master | Configures backlog tooling | Supports backlog creation | Prepares for Sprint 0
Programme Lifecycle · Setup & Design Phase · Stages 10–12
Notes: Roles for Setup & Design.
Programme Manager: Client-side, owns delivery and governance cadence.
Project Managers (one per workstream): cut by discipline (Functional, Data, Integration, NFT, Change) or by process area depending on programme shape.
Business Architect: anchors decisions to the Benefits Map.
SI Solution Architect: owns the technical design.
SI Functional Leads: own the FDDs.
Process Owners: sign off business design.
Design Authority: governs the lot.
Worth flagging: the SI roles are mapped into the same RACI as the Client roles. There isn't a separate SI RACI. One programme, one RACI.

## Slide 14
Setup & Design Timeline
Timeline is indicative. Duration depends on scope complexity, number of workstreams, and SI team size.
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
W14
W15
S10
Mobilisation, SI onboarding, governance activation
S11
Discovery workshops (Client + SI joint)
S12
Solution Design (overlaps late Discovery)
Key Milestones
Week 1: SI Team Onboarded, First DA Meeting
Week 3: Governance Live Gate (Programme Setup & Mobilisation (S10) complete)
Week 9: Discovery Complete Gate (Discovery (S11) complete)
Week 15: Design Authority Sign-Off Gate — all FDDs approved, backlog ready for Sprint 0
Notes: Timeline for S10–S12. 12 to 18 weeks total. S10 is short and intense (4–6 weeks). S11 and S12 are the workhorse stages.
Worth flagging: don't compress S11 to start S12 early. Discovery output drives Design quality. A rushed Discovery means a re-worked Design.

## Slide 15
Setup & Design Decision Points
Checkpoint — Governance Live (Programme Setup & Mobilisation (S10))
Client and SI teams structured with named individuals, environments provisioned, DA co-chair model active, Agile agreements signed. Forum review confirms readiness. Proceed to Discovery.
Checkpoint — Discovery Sign-Off (Discovery (S11))
As-is documented, gap analysis per workstream with fit/gap/workaround/customise decisions, product backlog populated, integration catalogue confirmed, data assessment complete. Forum review confirms exit. Proceed to Design.
BOARD GATE 2 — Full Business Case (S12)
Second of the programme's two real board gates. All FDDs signed off by Design Authority, technical architecture confirmed, data migration designed, prototype approved by Process Owners, customisation decisions documented. Firm/capped SI build & test pricing locked at ±10–15%. Board commits to build.
“Two checkpoints and one board gate. Solution Design & Full Business Case (S12) is the second of the programme's two real board gates — no unsigned design enters the build phase, and the board commits to firm SI pricing here.”
Programme Lifecycle · Setup & Design Phase · Stages 10–12
Notes: Three big decision points across S10–S12.
End of S10: Governance Live gate. Are teams in, environments up, governance cadence running. Phase Checkpoint.
End of S11: Discovery Complete gate. Product backlog ready, gap analysis done, configuration-vs-customisation calls made. Phase Checkpoint.
End of S12: Board Gate 2 — DA sign-off plus Full Business Case approval. Real money decision. Don't conflate with the Phase Checkpoints — this is board level.
Worth flagging: the Go-Live Gate is later, at end of S15, and it's an Exec Sponsor decision, not a Board Gate.

## Slide 16
How the SI Integrates into Programme Governance
Programme Lifecycle · Setup & Design Phase · Stages 10–12
Steering Committee
Monthly • Client Exec Sponsor (Chair)
SI Programme Director attends, reports delivery status
Design Authority
Bi-weekly • Client SA + SI SA (Co-chairs)
Client BA, SI Functional Leads, Process Owners
Sprint Ceremonies
Per sprint cadence • SI Scrum Master (facilitates)
SI Functional Leads + Client Process Owners participate
Key Principles
The SI operates within the Client’s governance framework — not alongside it
Design Authority decisions are binding on the SI
SI scope changes go through the Decision Rights Framework
SI Programme Director reports to Steering Committee monthly — progress, risks, commercial
SI personnel changes require Client PM approval per contract
Notes: How the SI integrates. They're not a separate workstream — they're embedded in the programme RACI from day one. They attend Design Authority. They run sprint ceremonies. They're governed by the same Decision Rights Framework as the Client team.
The line to land: the SI is governed BY the programme, not just delivering TO it. That's the difference between a partnership and a vendor relationship.

## Slide 17
Handover to Build & Test (Build & Configuration (S13))
At the end of Solution Design & Full Business Case (S12), the following are handed to the Build phase:
Approved FDDs per workstream (DA signed off)
Technical architecture document (co-signed by both Solution Architects)
Integration design per interface
Data migration design with cleansing rules
Prioritised product backlog (Epics → Features → User Stories with acceptance criteria)
DA decision log (all customisation decisions with rationale)
Test strategy with test cases designed from FDDs
Sprint 0
Begins immediately after S12 gate — 1 to 2 weeks of backlog refinement and build preparation before Sprint 1.
Design Authority remains active through Build and Test. Every build deviation from approved FDDs must return to DA for approval.
The governance thread continues
“The SI continues to operate within the governance framework. DA remains active. Every build deviation from approved FDDs must return to DA for approval.”
Programme Lifecycle · Setup & Design Phase · Stages 10–12
Notes: Handover to Build & Test (Build & Configuration (S13)). What moves: signed-off FDDs, approved technical architecture, agreed data migration design, prioritised product backlog, full RACI with named SI personnel.
Worth flagging: handover is a moment, not an event. The same teams continue — they just shift from designing to building. No team handover, no knowledge loss.

## Slide 18
APPENDIX
Setup & Design Playbook: Mobilisation, Discovery, Design Authority & Templates
Stages 10–12 · Detailed reference for Client and SI programme teams
Notes: Appendix opens here. Setup & Design Playbook for the team — mobilisation checklist, gap analysis framework, FDD structure, DA operating procedures, gate checklists. Not exec material; reference for the PM, BA, and SI leads running the work.

## Slide 19
Programme Setup & Mobilisation (S10): Mobilisation Checklist
# | Checklist Item | Owner | Evidence
1 | Client programme team confirmed and onboarded | Client PM | Team roster signed off
2 | SI delivery team onboarded with named individuals | SI Programme Director | SI resource schedule
3 | All SI roles mapped into programme RACI | Client PM + SI PD | Updated RACI document
4 | Development and test environments provisioned | SI Technical Lead | Environment access log
5 | Backlog tool configured with access for all team members | SI Scrum Master | Tool access confirmed
6 | Steering Committee scheduled with SI PD attendance | Client PM | SC calendar invites
7 | Design Authority scheduled with SI SA as co-chair | Client SA | DA calendar invites
8 | Agile working agreements signed (sprint length, ceremonies, DoD) | Client PM + SI PD | Signed agreement
9 | Scope prioritisation matrix reviewed against Benefits Map | Client BA | Prioritised matrix
10 | SI familiarisation session on pre-programme outputs | Client BA | Session attendance log
11 | Communication plan issued to all stakeholders | Client PM | Distribution record
12 | Risk register initiated with SI-specific risks | Client PM + SI PD | Risk register v1
Programme Lifecycle · Setup & Design · S10 Mobilisation
Notes: The S10 Mobilisation Checklist. Use this as the operational running list for the first 4–6 weeks. Twelve items grouped under Team, Environments, Governance, and Vendor Services. Tick them off; you're not done until every item is signed.

## Slide 20
Programme Setup & Mobilisation (S10) Gate Checklist: Governance Live
# | Gate Criterion | Evidence | Approved By
1 | Client programme team confirmed with named individuals | Signed team roster | Executive Sponsor
2 | SI delivery team onboarded, all roles mapped into RACI | Updated RACI document | Client PM
3 | Development and test environments provisioned | Environment access log | SI Technical Lead
4 | Steering Committee scheduled with SI PD attendance confirmed | Calendar invites issued | Client PM
5 | Design Authority scheduled with SI SA as co-chair | Calendar invites issued | Client SA
6 | Agile working agreements signed (sprint length, ceremonies, DoD) | Signed agreement document | Client PM + SI PD
7 | Scope prioritisation matrix reviewed against Benefits Map | Confirmed prioritisation matrix | Client BA
8 | Communication plan issued to all Client and SI stakeholders | Distribution confirmation | Client PM
All items must be met before proceeding to Discovery (S11) Discovery.
Notes: The S10 Gate Checklist — Governance Live. Six criteria, all must be met before you start S11 Discovery cleanly. Most-missed: the Vendor Service tier confirmation. People assume the SI handles it. They don't — that's a Client commitment via the platform vendor.

## Slide 21
Discovery (S11): Discovery Workshop Approach
Day | Focus | Led By | Key Activities
Day 1 | As-Is Process Mapping | Client Process Owner | Walk through current process end-to-end, document pain points and workarounds, identify key data flows and integration points, capture volume and frequency metrics
Day 2 | Platform Capability & Gap Analysis | SI Functional Lead | Demonstrate standard platform capability, joint gap analysis per requirement: fit / process change / workaround / customise, document gap decisions for DA review
Day 3 | Requirements & Backlog | Joint (Client BA + SI FL) | Draft Features and User Stories from gap analysis, review acceptance criteria with Process Owner, identify integration scope (SI Technical Lead joins), identify data migration scope (SI Data Migration Lead joins)
Workshop Attendees
All 3 days: Client Process Owner, Client BA, SI Functional Lead, Change Lead (observer)
Day 3 only: SI Technical Lead (integration scope), SI Data Migration Lead (data scope)
Output: As-is map, gap analysis log, draft Features/User Stories entered into backlog tool
Illustrative — adapt workshop duration and structure to workstream complexity and SI methodology.
Programme Lifecycle · Setup & Design · S11 Discovery
Notes: Discovery Workshop Approach. Joint Client–SI workshops, structured by process stream. Each workshop has a Process Owner (sign-off authority), SMEs (current state experts), SI Functional Lead (target state and platform fit), Client BA (synthesis).
Common trap: running open-ended "tell us about your process" workshops. Output is unfocused and re-work is heavy. Better: structured workshops with pre-mapped current state and a clear hypothesis to test.

## Slide 22
Discovery (S11): Gap Analysis Decision Framework
Programme Lifecycle · Setup & Design · S11 Gap Analysis
Requirement identified
Standard platform handles it?
YES
FIT — Configure standard
NO
Can business process adapt?
YES
PROCESS CHANGE — DA approves
NO
Standard tools address it?
YES
WORKAROUND — DA approves
NO
CUSTOMISE — SI cost-benefit, DA decides
No DA approval needed
Customisation Approval Criteria
Supports a Benefits Map KPI
Cost proportionate to benefit
Aligns with Guiding Principles
Acceptable long-term maintenance impact
Notes: Gap Analysis Decision Framework. Three outcomes per requirement: out-of-the-box, configuration, customisation.
The discipline: default is out-of-the-box. Configuration only when business value justifies it. Customisation only when there's no alternative — and customisations need DA sign-off and a documented business case.
Worth flagging: customisations have hidden cost. They break under vendor upgrades, they slow upgrades, and they create support burden post-go-live. The TCO of a customisation is typically 5x its build cost over 5 years.

## Slide 23
User Story Writing Guide (1 of 2)
Workstream | ✘ Bad Example | ✔ Good Example + Acceptance Criteria
Finance | "The system should do month-end close faster." | "As a Financial Controller, I want the system to generate all recurring journals automatically at period end, so that I can reduce manual entry from 3 days to 4 hours." AC: Templates configurable • Auto-generated day 1 • Failed journals flagged <1hr • <4hrs for 200 journals
Operations | "We need better inventory management." | "As a Warehouse Manager, I want the system to trigger automatic reorder notification when stock falls below threshold, so I can prevent stock-outs." AC: Threshold per product/warehouse • Email + system alert • Triggers <15 min
Sales | "Credit checks need to be automatic." | "As a Sales Order Processor, I want automatic credit checks on order entry, so overdue accounts are flagged before I commit stock." AC: Auto-trigger • Over-limit orders held • Release by Credit Controller only • <3 sec
SI Functional Leads draft stories. Client Process Owners own acceptance criteria. Illustrative examples.
Notes: User Story Writing Guide, part 1. Format, common pitfalls, INVEST criteria (Independent, Negotiable, Valuable, Estimable, Small, Testable).
The two pitfalls to flag hardest: stories without a "so that" clause (no traceable benefit), and stories sized larger than a sprint (which means it's actually a feature in disguise).

## Slide 24
User Story Writing Guide (2 of 2)
Workstream | ✘ Bad Example | ✔ Good Example + Acceptance Criteria
HR | "Holiday approvals should be easier." | "As a Line Manager, I want to approve or reject holiday requests within the system with one click, so that my team's leave is recorded accurately without email chains." AC: One-click approve/reject • Auto-updates leave balance • Notification to employee <5 min • Calendar view for team
Procurement | "We need automatic POs." | "As a Procurement Officer, I want the system to auto-generate a purchase order when a requisition is approved and the supplier is on the approved list, so I can reduce manual PO creation from 2 hours to 10 minutes per batch." AC: Auto-PO on approved requisition • Approved supplier list check • PO number auto-assigned • Batch processing <10 min for 50 POs
Data Migration | "Migrate all customer data." | "As a Data Migration Lead, I want the system to validate migrated customer records against defined rules before go-live, so that only clean, complete records enter the new system." AC: Address completeness >95% • Duplicate detection on name+postcode • Failed records flagged with reason • Validation report auto-generated
SI Functional Leads draft stories. Client Process Owners own acceptance criteria. Illustrative examples.
Notes: User Story Writing Guide, part 2. Acceptance criteria, definition of done, traceability to features and epics.
Acceptance criteria are how the SI knows when it's done and how testing builds test cases. They're not optional. A story without acceptance criteria is a wish, not a deliverable.

## Slide 25
Discovery (S11) Gate Checklist: Discovery Complete
# | Gate Criterion | Evidence | Approved By
1 | As-is process maps documented per workstream | Process map documents | Client Process Owners
2 | Gap analysis completed per workstream with fit/gap decisions | Gap analysis log per workstream | Design Authority
3 | Product backlog populated (Epics, Features, User Stories) | Backlog tool export | Client BA + SI SM
4 | Integration catalogue confirmed with technical approach | Integration catalogue document | SI Technical Lead
5 | Data assessment completed with migration strategy | Data assessment report | SI Data Migration Lead
6 | All customisation requests submitted to DA with rationale | DA decision log | Design Authority
7 | Test scenarios identified from discovery requirements | Test scenario register | Client Test Manager
8 | Change impact assessment completed per workstream | Change impact report | Change Lead
All items must be met before proceeding to Solution Design & Full Business Case (S12) Solution Design.
Notes: The S11 Gate Checklist — Discovery Complete. Eight criteria, all must be met before S12 Design starts. Most-missed: configuration-vs-customisation calls signed off by DA for every gap. People defer the call to S12 "to keep momentum." Don't. Discovery is incomplete until the calls are made.

## Slide 26
Solution Design & Full Business Case (S12): FDD Structure & DA Sign-Off
Recommended FDD Sections
Overview — scope, link to Epic/Benefits Map
As-Is Summary — current state from discovery
To-Be Process Design — detailed future-state flow
Configuration Specification
Customisation Specification — DA-approved items only
Integration Touchpoints
Data Migration Requirements
User Stories Covered — traceability to backlog
Open Items and Assumptions
DA Sign-Off Process
SI Functional Lead submits FDD to DA
Client Process Owner reviews for business accuracy
SI Solution Architect reviews for technical soundness
Design Authority reviews for strategic alignment
Both co-chairs sign off (Client SA + SI SA)
FDD enters approved backlog — ready for build
No FDD enters build without dual sign-off from both DA co-chairs.
Programme Lifecycle · Setup & Design · S12 FDD Process
Notes: FDD Structure & DA Sign-Off. Use the FDD template — every FDD has the same sections so DA can review them efficiently. Section headings: Process scope, Functional design, Configuration approach, Integration touchpoints, Data implications, Test approach, Open issues.
Worth flagging: incomplete FDDs slow DA. If a section is "TBC", the FDD isn't ready for sign-off. Don't book DA time for incomplete FDDs.

## Slide 27
Solution Design & Full Business Case (S12): Design Authority Operating Procedures
Purpose: Govern design and scope decisions against Benefits Map and Guiding Principles
Co-chairs: Solution Architect + SI Solution Architect
Cadence: Bi-weekly, 90 minutes
Members: Client BA, SI Functional Leads, Client Process Owners, SI Technical Lead (as needed)
Standing Agenda
Design decisions requiring approval (20 min)
Customisation requests — SI cost-benefit, DA decides (30 min)
Scope change requests vs Benefits Map (20 min)
Integration and architecture decisions (15 min)
Actions and next meeting preparation (5 min)
Documentation: DA decision log — every decision recorded with rationale
Escalation: If DA cannot reach consensus, escalate to Steering Committee
Key Rules
The SI does not build anything that DA has not approved — no exceptions
DA decisions are documented in the decision log and are final
No offline lobbying — all scope and design requests go through DA
Both co-chairs must be present for decisions to be binding
SI Functional Lead proposes — DA decides. The SI does not decide unilaterally
If stakeholders lobby the SI directly, the SI refers them to DA
Customisation requests require full cost-benefit analysis before DA considers them
Programme Lifecycle · Setup & Design · S12 Design Authority
Notes: DA Operating Procedures. Cadence, agenda, decision logging, escalation. Worth pausing on the decision log — every DA decision is recorded with date, decision, owner, and rationale. Without the log, DA decisions get relitigated every fortnight.

## Slide 28
Solution Design & Full Business Case (S12): Prototype Review Process
SI Functional Lead demonstrates key scenarios in the live platform — not a slide deck. Process Owners validate hands-on.
Recommended Format
3–4 prototype sessions across priority workstreams
90 minutes each session
Attendees: Process Owner, BA, SI Functional Lead, SI Solution Architect
Focus on end-to-end scenarios, not individual screens
Feedback Categorisation
Approve — design as demonstrated is correct
Adjust design — minor changes, SI updates FDD
Escalate to DA — fundamental gap or new requirement identified
Why Prototype?
A 30-minute prototype walkthrough catches more design issues than a 30-page document. People react to what they can see and touch — not what they read.
Programme Lifecycle · Setup & Design · S12 Prototype Review
Notes: Prototype Review Process. Where DA reviews working prototypes alongside FDDs. Two reasons it matters: catches design errors early (before build), and gives Process Owners visibility of what they're about to sign off.
Common trap: prototype review without DA in the room. Process Owners give feedback that DA hasn't seen and the design splits. Always run prototype review with DA.

## Slide 29
Solution Design & Full Business Case (S12) Gate Checklist: DA Sign-Off
# | Gate Criterion | Evidence | Approved By
1 | All FDDs signed off by DA (both co-chairs) | Signed FDD documents | DA Co-chairs
2 | Technical architecture confirmed and co-signed | Architecture document | Client SA + SI SA
3 | Integration design confirmed per interface | Integration design docs | SI Technical Lead
4 | Data migration design and cleansing rules agreed | Migration design document | SI Data Migration Lead
5 | Prototype reviewed and approved by Process Owners | Prototype review sign-off | Client Process Owners
6 | All customisation decisions documented in DA log | DA decision log complete | Design Authority
7 | Sprint 0 plan confirmed with backlog ready | Sprint 0 plan document | SI Scrum Master
8 | Test cases designed from FDDs | Test case repository | Client Test Manager
9 | Risk register updated with design-phase risks | Updated risk register | Client PM + SI PD
No unsigned design enters the build phase. All items must be met before Sprint 0.
Notes: The S12 Gate Checklist — DA Sign-Off plus Full Business Case approval. This is Board Gate 2. Six criteria for DA Sign-Off, plus the Full Business Case package for the board.
Most-missed criterion: data migration design signed off by Data Lead AND Data Owners. People forget the Data Owners — they're the ones whose data it is. Without their sign-off, you'll discover problems at cutover.

## Slide 30
SI Team Structure & RACI Matrix
Activity | ES | PM | SA | BA | PO | CL | TL | SI-PD | SI-SA | SI-FL | SI-TL | SI-DM | SI-SM
Mobilisation | A | R | C | C | I | I | I | R | C | I | I | I | I
Environment provisioning | I | C | C | I | I | I | I | A | C | I | R | I | I
Discovery workshops | I | C | C | R | R | C | C | I | C | R | C | C | I
Gap analysis | I | I | C | R | C | I | I | I | A | R | C | I | I
As-is process mapping | I | I | I | C | R | C | I | I | I | C | I | I | I
Backlog creation | I | C | I | R | C | I | I | I | I | R | I | I | R
FDD production | I | C | C | C | R | I | I | A | R | R | C | C | I
Technical architecture | I | I | R | I | I | I | I | C | R | I | C | I | I
Integration design | I | I | C | I | I | I | I | C | A | C | R | I | I
Data migration design | I | I | I | I | I | I | I | C | C | I | I | R | I
DA governance | I | C | R | C | C | I | I | I | R | C | C | I | I
Prototype review | I | I | C | C | R | C | C | I | C | R | I | I | I
Sprint 0 planning | I | C | C | R | C | I | C | C | C | C | C | C | R
R=Responsible A=Accountable C=Consulted I=Informed · ES=Exec Sponsor PM=Programme Mgr SA=Solution Arch BA=Business Arch PO=Process Owner CL=Change Lead TL=Client Test Mgr
Notes: SI Team Structure & RACI Matrix. The structural reference — every SI role mapped against every workstream activity. Use it when assigning people during S10. Worth flagging: this is the same RACI the Client team uses. One programme, one RACI.