## Slide 1
Build & Test
Build & Test (S13–S14): From Build Sprints to Go-Live Readiness
Build & Test (S13–S14): Build & Test
Programme Lifecycle · Build & Test · Every decision traced to the Benefits Map
Notes: This deck spans Setup & Design through Build & Test (S10–S14). Two phase colours on the slide — purple for S10–S12 (Setup & Design) and coral for S13–S14 (Build & Test). The visual split reinforces the discipline: design has to be complete before build begins. If you're building from incomplete designs, you're building twice.

## Slide 2: Why Build & Test Governance Matters
Programme Lifecycle · Build & Test · Delivery Governance
Three Risks When Delivery is Ungoverned
Scope Drift
Requirements expand without value assessment — the programme delivers features nobody asked for
Design by Committee
Decisions relitigated, conflicting designs built, rework consumes 30% of effort
Testing Theatre
UAT becomes a rubber stamp — users click through scripts without understanding what they validate
What Governed Delivery Ensures
Design Authority approves every functional design against the Benefits Map and Guiding Principles
Agile sprints structured around Epics and Features tied to strategic outcomes
Testing is layered (Unit → FAT → Mini-BAT → SAT → SIT → Pre-UAT → UAT → BAT → NFT) with business sign-off at every level
“Ungoverned delivery produces a system. Governed delivery produces business value.”
Notes: Most ERP programmes that fail don't fail on technology. They fail on governance gaps, unclear accountability, and the assumption that the SI will handle it.
Three failure patterns to land:
Scope drift — requirements expand without value assessment.
Design by committee — decisions get relitigated, conflicting designs go into build, rework consumes 30 per cent of effort.
Testing theatre — UAT becomes a rubber stamp instead of a real validation.
Governance prevents all three. Design Authority approves every functional design against the Benefits Map. Testing is layered through eight levels (Unit, FAT, Mini-BAT, SAT, SIT, UAT, BAT, NFT) with role-appropriate sign-off. Defects classify on impact, not on who raised them.

## Slide 3: What This Deck Covers
Core Slides (1–18)
Why delivery governance matters
How Client-side requirements mapping feeds into SI Discovery
Two stages: Build & Configuration (13), Testing Execution (14)
Agile delivery: Epics, Features, User Stories
Sprint structure, ceremonies, definition of done
Testing: Unit → FAT → Mini-BAT → SAT → SIT → Pre-UAT → UAT → BAT → NFT
Roles, timeline, and executive decision gates
Appendix — Delivery Playbook (19+)
Agile governance: Sprint structure, ceremonies, Definition of Done
User Story writing guide with good and bad examples
Testing strategy templates and test phase detail
Stage gate checklists for every stage
Design Authority operating procedures
Use core slides for executive briefings; appendix slides support the delivery team’s day-to-day governance
Notes: Map for the deck. Core slides are for the steering committee and executives — what we're doing, who does it, where the gates are. Appendix slides are working-level detail for the programme team. Worth flagging up front: the testing methodology shows eight levels (Unit, FAT, Mini-BAT, SAT, SIT, UAT, BAT, NFT). NFT is folded in. That's the standard.

## Slide 4
Build & Test in Context · Setup & Design through Build & Test (S10–S14)
10
Mobilisation
Team onboarding, environments, backlog seeding
4–6 weeks
11
Discovery
Process workshops, requirements gathering, Epic definition
6–8 weeks
12
Solution Design
Functional design, DA approval, configuration specs
8–12 weeks
13
Build & Configuration
Configured system, custom development, integration build
12–16 weeks
14
Testing Execution
Unit, FAT, SAT, SIT, UAT, BAT, NFT with business sign-off
8–12 weeks
Setup & Design (Stages 10–12)
Build & Test (Build & Test (S13–S14))
Each stage has a review before proceeding — see Slide 18 for the one board gate (Solution Design & Full Business Case (S12)) and the surrounding checkpoints
Notes: Five stages, one flow. Sequential but overlapping at the boundaries. Discovery (S11) informs Design (S12), Design feeds Build (S13), Build produces something testable (S14).
The purple-to-coral transition at Build & Configuration (S13) is the visual cue: this is where you cross from designing to executing. After this point, every change has a cost.

## Slide 5
Epic → Feature → User Story Hierarchy
EPIC
Strategic
Maps to a Benefits Map outcome. Owned by a Benefit Owner.
“Order-to-Cash Transformation”
FEATURE
Tactical
DA-approved functional design. Traced to parent Epic.
“Automated Invoice Generation”
USER STORY
Deliverable
Testable, sprint-sized increment with acceptance criteria.
“As a finance clerk, I want...”
Governance Thread
Epic → traced to Benefits Map → governed by Steering Committee
Feature → traced to Epic → governed by Design Authority
User Story → traced to Feature → governed by Scrum Master / Product Owner
Epics and Features are created during Client-side requirements mapping (Market Engagement through SI Selection (S7–S9)). Draft User Stories are written by Client BAs with business-side acceptance criteria. During Discovery (Discovery (S11)), the SI refines stories and adds platform-specific acceptance criteria. See Setup & Design deck for full requirements mapping methodology.
Programme Lifecycle · Build & Test · Agile Hierarchy
Notes: The hierarchy: Epics map to the Benefits Map, Features map to Epics, User Stories map to Features. Each level has a governance owner.
Worth flagging: Epics and Features came out of Client-side requirements mapping during Selection. Draft user stories came out of Discovery (S11). The SI doesn't write the epics for you — they're owned by the Client BA.

## Slide 6: User Stories: Good vs Bad Examples
Structure: As a [role], I want [capability], so that [business value]
✗ BAD — Finance
“The system should do month-end close faster.”
No role, no specific capability, no measurable outcome
✓ GOOD — Finance
“As a Financial Controller, I want the system to generate all recurring journals automatically at period end, so that I can reduce manual entry from 3 days to 4 hours.”
Recurring journal templates configurable by Finance team
Auto-generated on first working day of each period
Failed journals flagged for manual review within 1 hour
Completes within 4 hours for up to 200 recurring journals
✗ BAD — Operations
“We need better inventory management.”
Vague, no specific user, no testable outcome
✓ GOOD — Operations
“As a Warehouse Manager, I want auto reorder notifications when stock falls below threshold, so I can prevent stock-outs without daily manual checks.”
Minimum threshold configurable per product and warehouse
Notification via email and system alert to designated buyer
Includes product code, current stock, threshold, suggested qty
Triggers within 15 minutes of stock below threshold
Every User Story must trace to a Feature → Epic → Benefits Map. If it cannot be traced, challenge whether it belongs.
Notes: Walk both examples. A good user story is small, testable, benefit-linked, and has acceptance criteria. A bad one is vague, ambiguous, and impossible to test.
The line to land: acceptance criteria become the FAT checklist during sprint review. Without them, "done" is a negotiation. With them, "done" is binary.

## Slide 7
Sprint 0 bridges Solution Design (Solution Design & Full Business Case (S12)) and Build (Build & Configuration (S13)). No production code is written. Focus is readiness.
Sprint 0 Activities
Refine backlog: all stories have acceptance criteria and estimates
Confirm Sprint 1 scope: highest-priority stories selected
Prepare dev environments: config, access, sample data
Establish CI/CD pipeline and version control
Confirm Definition of Done for Stories, Features, Epics
Run backlog grooming with full delivery team
Brief dev team on Design Authority governance
Sprint 0 is NOT:
A design phase (design is complete at Solution Design & Full Business Case (S12))
A free sprint for technical housekeeping
Optional
Duration: Typically 1–2 weeks
S0
Sprint 0: Design-to-Build Transition
Programme Lifecycle · Build & Test · Sprint 0
Notes: Sprint 0 bridges Solution Design (S12) and Build & Configuration (S13). Most structured sprint in the programme — backlog grooming, environment validation, tooling configuration, Definition of Done agreed.
Worth pausing on: if Sprint 0 is sloppy, every sprint that follows pays the tax. Don't compress it. The temptation to "just start building" because the contract's signed kills downstream velocity.

## Slide 8
Build & Configuration (S13)
Key Objectives
Configure platform per approved FDDs
Develop approved custom code with DA sign-off
Build integrations per integration catalogue
Build data migration scripts, complete dry run
Run Unit Testing on all configuration and development
Sprint reviews with Process Owners at end of each sprint
Outputs
Configured system per FDDs
Custom development completed and unit tested
Integration build completed and unit tested
Data migration scripts built, dry run completed
Sprint review sign-offs from Process Owners
“Every sprint ends with a review where the Process Owner sees working software. No sprint closes without business validation.”
Programme Lifecycle · Build & Test · S13
Notes: Build & Configuration (S13) is the build phase. Coral accent from here because we've crossed from design into execution.
The discipline to land: every sprint ends with a Process Owner seeing working software. No sprint closes without Process Owner sign-off. That's how you keep build aligned to design.

## Slide 9: Testing Methodology: Eight Levels of Assurance
During Sprints (S13)
Post-Build (Testing (S14)) — Sequential: SAT → SIT → UAT → BAT → NFT
Level 1: Unit Testing (SI Developer)
Individual components in isolation
Level 2: FAT (SI Tester · Process Owner accepts at sprint review)
User Stories tested against acceptance criteria
Level 3: Mini-BAT (Benefit Owner or Senior User, every 2nd/3rd sprint)
Realistic scenario walkthrough. 1–2 hrs, hands-on, no scripts. Early warning.
Level 4–5: SAT → SIT
SAT (SI-led): system functional + regression. SIT (Joint): end-to-end + 3rd party.
Level 6: UAT (Users — formal; Pre-UAT prepared by Test Mgr + POs; Types: UAT/Role/Business Readiness/DILO)
End-to-end business processes (scripts written by the business). Scripted, traceable.
Level 7: BAT (Process Owners execute, Benefit Owners sign off)
Full business simulation. Not script-based.
Level 8: NFT (IT Ops + SI Infrastructure — performance, security, DR, stress)
Performance, security, DR, data migration validation (Non-Functional Testing)
"UAT (run by users) confirms the system meets requirements through end-to-end business processes. BAT confirms the wider business can operate under realistic conditions. Both are essential — UAT alone is not enough, which is why programmes that only do UAT still have go-live failures."
Programme Lifecycle · Build & Test · Testing Methodology
Notes: Eight levels of assurance, aligned to standard testing taxonomy.
Sprint level (during Build & Configuration (S13)):
- Unit Testing — SI developer per work-package.
- FAT (Functional Acceptance) — SI Functional Consultant tests user-story acceptance criteria.
- Mini-BAT — Process Owner spot-checks scenarios mid-sprint.
Post-build level (during Testing (S14)):
- SAT (Solution Acceptance) — SI Test Lead confirms full SI scope works end-to-end before handover.
- SIT (System Integration) — Client Test Manager runs cross-module and external integration tests.
- UAT (User Acceptance) — actual users execute scripts; Process Owners and Client Test Manager sign off.
- BAT (Business Acceptance) — Benefit Owners run real-world scenarios.
- NFT (Non-Functional) — performance, security, resilience; runs alongside.
Worth landing hard: the SI Test Lead owns SAT (their scope, signed off by them). Everything else is Client Test Manager territory.

## Slide 10: Testing Methodology: Eight Levels of Sign-Off
"SI Tester executes FAT; Process Owner accepts at sprint review. SI Test Lead leads SAT (system-level functional). SIT is jointly run by Client Test Manager and SI. Users execute UAT (scripts written by the business); Client Test Manager + Process Owners sign off. Process Owners and Senior Users execute BAT scenarios; Benefit Owners sign off business readiness. NFT is run by IT Ops and SI Infrastructure. Executive Sponsor authorises handover to Deploy based on evidence from all test levels."
Test Level | When | Who Executes | Who Signs Off | What They Confirm | Evidence Required
Unit Test | During sprint | SI Developer / Consultant | SI Tech Lead | Component works in isolation | Unit test results log
FAT | Sprint review | SI Tester (Process Owner observes at sprint review) | Process Owner | User stories meet acceptance criteria | FAT results + sign-off form
Mini-BAT | Every 2nd/3rd sprint | Process Owners and Senior User | Benefit Owner | Features work for real business operations | Mini-BAT session notes + feedback
SAT | Post-build (before SIT) | SI Test Lead + Test Team | SI Test Lead (with Process Owner observers) | Integrated solution meets Solution Design — functional, usability, regression | SAT scripts + cycle results + defect log
SIT | After SAT | SI Test Team + Client Test Manager | Client Test Manager + Solution Architect | End-to-end processes and integrations work | SIT results + defect resolution log
UAT | After SIT | Users / End Users (scripted, supported by Client Test Manager and BA) | Client Test Manager + Process Owners | End-to-end business processes work; scripts written by the business | UAT scripts + results + sign-off
BAT | After UAT | Process Owners + Senior Users (scenario-based) | Benefit Owners + Exec Sponsor | Business can operate on this system | BAT scenario results + Benefit Owner sign-off
NFT | After UAT (parallel with BAT) | IT Ops + SI Infrastructure | IT Ops Lead + Solution Architect | Non-functional requirements met (performance, security, DR, batch) | NFT results + performance benchmarks
Programme Lifecycle · Build & Test · Testing
Notes: Same eight levels with role-appropriate execution and sign-off. The thing to land here is that execution and sign-off are different jobs.
UAT in particular: USERS execute. Process Owners + Client Test Manager sign off. This is the most common mistake we see — Process Owners running UAT scripts. It kills user buy-in because the people who'll use the system have never touched it before go-live. Worth pausing on this point. Users execute. Process Owners sign off.

## Slide 11
Testing (S14): Execution
Key Objectives
Execute all post-build levels: SAT → SIT → Pre-UAT → UAT → BAT → NFT (parallel)
Execute UAT with Users (scripts written by the business; Process Owners coordinate; Client Test Manager signs off)
Execute BAT — Process Owners and Senior Users run end-to-end business scenarios; Benefit Owners review evidence and sign off
Manage defects: classification, resolution, retest
Complete data migration testing (dry runs)
Complete performance and load testing
Confirm Deploy readiness against baseline KPIs
Outputs
Test results per level with sign-off evidence
Defect log (zero P1, P2 trending to zero)
UAT sign-off + BAT Benefit Owner sign-off + Deploy readiness confirmation
“Zero P1. Zero P2 unless a workaround is agreed and documented. No quiet acceptance. The go-live gate is the final checkpoint before the business operates on a new system.”
Programme Lifecycle · Build & Test · S14
Notes: Testing (S14) is the formal post-build test phase with five sequential test types plus NFT in parallel.
Sequence: SAT (SI confirms their scope) → SIT (cross-module + integrations) → Pre-UAT (smoke before users get involved) → UAT → BAT.
NFT runs alongside, typically performance from SIT onwards.
Roles to flag: SAT is owned by the SI Test Lead. Everything else is owned by the Client Test Manager. Don't blur the line — you'll get marking-of-own-homework on SI scope.

## Slide 12: Inputs & Outputs Across Stages 10–14
# | Stage | Key Inputs | Key Outputs
10 | Setup & Mobilisation | SI contract, RACI, mobilisation plan, scope matrix | Team structure, environments, governance cadence, Agile agreements
11 | Discovery | Heatmap, Benefits Map, Guiding Principles | As-is maps, gap analysis, product backlog, integration catalogue
12 | Solution Design | Gap analysis, backlog, technical architecture | FDDs, prototype, data migration design, integration design
13 | Build & Configuration | Approved FDDs, prioritised backlog, Sprint 0 outputs | Configured system, unit tested code, integration build, migration scripts
14 | Testing | Built system, test strategy, baseline KPIs | Test results per level, defect log, BAT sign-off, go-live readiness
Programme Lifecycle · Stages 10–14
Notes: Inputs and outputs across S10–S14. Walk the chain — what comes into each stage, what comes out. The artefact thread runs Heatmap → Backlog → FDDs → Built System → Tested System.

## Slide 13
Roles & Responsibilities During Delivery — Client Team
Programme Lifecycle · Stages 10–14
Role | S10: Setup | S11: Discovery | S12: Design | S13: Build | S14: Test
Executive Sponsor | Confirms team, activates governance | Reviews at Steering | Approves DA decisions | Reviews monthly | Authorises handover to Deploy
Programme Manager | Runs mobilisation, establishes governance | Coordinates workstreams, manages dependencies | Manages design schedule across workstreams | Manages programme delivery, reports to Steering | Manages test governance, owns readiness gate
Project Manager(s) | Confirms workstream team and plan | Manages workstream discovery schedule | Manages workstream design delivery | Manages workstream sprint delivery | Manages workstream test execution
Solution Architect | Co-activates DA | Validates integration approach | Co-chairs DA, signs architecture | Governs build quality | Signs off SIT and NFT
Business Architect | Confirms scope prioritisation | Leads gap analysis (business side) | Validates strategic fit of designs | Validates outputs vs Benefits Map | Validates BAT scenarios vs Benefits Map
Process Owners | Confirm workstream scope | Provide requirements, validate as-is | Review and sign off FDDs | Attends sprint reviews · accepts FAT per Feature | Coordinate Pre-UAT/UAT (write scripts with Test Mgr); sign off UAT acceptance; review BAT
SMEs | Identified and assigned per workstream | Discovery workshops, detailed process knowledge | Review FDD detail, validate business rules | Attend sprint reviews, support FAT | Execute BAT scenarios hands-on
Users | Identified for UAT and training | Not typically involved | Not typically involved | Training development and review | Execute UAT scripts hands-on, usability feedback
Change Lead | Plans change approach | Assesses change impact | Develops training strategy | Builds training materials, identifies testers | Validates user readiness, coordinates UAT/BAT
Client Test Manager | Drafts test strategy | Identifies test scenarios | Designs test cases from FDDs | Oversees unit testing | Owns SIT execution · authors Pre-UAT scripts with POs · coordinates UAT/BAT · manages defects
Notes: Roles for delivery — Client team. Programme Manager owns delivery cadence. Project Managers run workstreams. Business Architect anchors decisions to the Benefits Map. Process Owners sign off business design. Client Test Manager owns testing from SIT onwards. Benefit Owners run BAT.
Worth flagging: Process Owners and Client Test Manager have a specific divide. PO signs off business design and BAT scenarios. Client Test Manager owns test execution discipline. Different jobs.

## Slide 14
Roles & Responsibilities During Delivery — SI Team
Programme Lifecycle · Build & Test · Roles (SI)
Role | S10: Setup | S11: Discovery | S12: Design | S13: Build | S14: Test
SI Programme Director | Onboards SI team | Manages SI resources | Manages delivery to DA schedule | Manages SI build delivery | Supports defect resolution
SI Solution Architect | Co-activates DA, confirms architecture | Leads gap analysis (platform side) | Co-chairs DA, produces architecture doc | Governs technical quality | Signs off SIT/SAT (SI side)
SI Functional Leads | Familiarise with Heatmap and Benefits Map | Co-facilitate discovery, document gaps | Produce FDDs, demonstrate prototype | Configure and build per FDDs | Support UAT queries, resolve functional defects
SI Technical Lead | Confirms integration approach | Designs integration catalogue | Produces integration design | Custom development, integration build | Resolves technical defects
Notes: SI side roles — broken out into four. Programme Director (commercial and senior governance). Solution Architect (technical design lead). Functional Leads (one per workstream, FDDs). Technical Lead (build, integration, environments).
The line to land: the SI is not a single entity. Each role has distinct accountabilities. The Client RACI maps each one in.

## Slide 15: Delivery Timeline: Stages 13–14
W0
W5
W10
W15
W20
W25
W30
W35
S10: Mobilisation
Wk 1–3
S11: Discovery
Wk 4–9
S12: Solution Design
Wk 8–15
Sprint 0
Wk 14–15
S13: Build
Wk 16–29
S14: Testing
Wk 24–35
Wk 3 Governance Live
Wk 9 Discovery Complete
Wk 15 DA Sign-Off
Wk 29 Build Complete
Wk 35 Testing Complete
Timeline is indicative. Workstreams may run at different speeds. Total duration depends on scope complexity and team capacity.
Notes: Timeline from mobilisation through go-live. Key milestones are the gate reviews at end of each stage.
Worth flagging: the timeline should feel tight but achievable. If it feels impossible, the scope is too large or the team is too small. Don't compress; rescope.

## Slide 16: Delivery Timeline: Stages 13–14
1
S10
Governance Live
Team structured, environments provisioned, governance cadence activated. Proceed to Discovery.
2
S11
Discovery Complete
As-is documented, gap analysis per workstream, product backlog populated. Proceed to Design.
3
S12
Design Authority Sign-Off
All FDDs approved, technical architecture confirmed, data migration designed. Sprint 0 authorised.
4
S13
Build Complete
All Features built and unit tested, FAT sign-off from Process Owners, data migration dry run complete. Proceed to SIT.
5
S14
Testing Complete
Zero P1/P2 defects, BAT signed off by Benefit Owners, data migration validated. Handover to Deploy phase (Cutover Planning (S15)) authorised.
“One board gate (Solution Design & Full Business Case (S12)) and four checkpoints. Each requires evidence. None is passed on assurance alone.”
Programme Lifecycle · Stages 10–14
Notes: Five executive decision gates, one at the end of each stage. Each gate has explicit criteria, evidence requirements, and named approvers.
These are not rubber stamps. No stage proceeds without gate approval. The two big ones are end of S12 (Board Gate 2 — Full Business Case) and end of S15 (Go-Live Gate — Exec Sponsor's binary call). Worth flagging the GLG distinction: it's an Exec Sponsor decision, not a Board Gate.

## Slide 17
APPENDIX
Detailed Delivery Playbook — Stages 10–14
For PMs, Scrum Masters, Functional Consultants, Client Test Managers, and Process Owners
Notes: Appendix opens here. Working-level detail for the team. Core slides told the exec story; appendix gives the how. Use these as reference during programme delivery.

## Slide 18
Agile Sprint Structure and Ceremonies
Day 1
Sprint Planning
2–4 hours
Review prioritised backlog
Select stories by capacity
Break stories into tasks
Confirm dependencies
Days 1–9
Daily Standups
15 minutes
What did I complete?
What am I working on?
What is blocking me?
Days 1–9
Build, Configure, Unit Test
Core activity
Build per FDD
Unit test during build
Raise design questions to DA immediately
Day 9
Sprint Review
2 hours
Demo to Process Owners
Validate vs acceptance criteria
Accept or return stories
Sprint review = FAT acceptance gate
Day 10
Retrospective
1 hour
What went well?
What needs improving?
One actionable improvement
↻ Repeat every 2 weeks — 6–8 sprints in Build & Configuration (S13)
Programme Lifecycle · Delivery Playbook · Agile Ceremonies
Notes: Sprint structure — two-week cadence, ceremonies, roles, outputs.
FAT (Functional Acceptance) is executed by the SI Tester during the sprint, then accepted by the Process Owner at sprint review. The Process Owner doesn't run the test — they review evidence and validate the demo, hands-on where appropriate.

## Slide 19: Definition of Done: Stories, Features, and Epics
User Story — Done when:
Code/configuration complete per FDD
Unit tested with all tests passing
Peer reviewed by another team member
All acceptance criteria met and evidenced
Process Owner reviewed in sprint demo
Documentation updated
No P1 or P2 defects outstanding
Feature — Done when:
All User Stories meet Story-level DoD
FAT completed: Process Owner signed off
Traced to Epic and Benefits Map — confirmed
Test evidence logged in test management tool
Epic — Done when:
All Features meet Feature-level DoD
SIT passed for cross-workstream integrations
Benefit Owner confirms KPI contribution
Design Authority confirms alignment with Guiding Principles
Programme Lifecycle · Delivery Playbook · Definition of Done
Notes: Definition of Done is the contract between the build team and the business. A user story isn't done until every criterion is met.
The common failure: accepting partially-done work into the next sprint to keep velocity numbers up. Compounds. By sprint 6 you have a backlog of "done" stories that aren't actually done. Hold the line on DoD.

## Slide 20: User Story Writing Guide — Extended Examples
HR
✗ BAD: “HR needs employee self-service.”
✓ GOOD:
“As a Line Manager, I want to approve holiday requests with a single click, so that I can process approvals in under 30 seconds instead of 3-day email chains.”
Acceptance Criteria:
Notification in manager’s task list + email
Single-click approve/reject
Auto-updates team calendar + HR system
View team calendar before approving
Procurement
✗ BAD: “Purchase orders should be automated.”
✓ GOOD:
“As a Procurement Officer, I want auto-generated POs when a requisition is approved and supplier has a valid contract, so that PO creation drops from 45 min to under 2 min.”
Acceptance Criteria:
PO auto-generated within 2 min of approval
References correct contract + pricing
Sent to supplier via email with PDF
Exception: no contract → route to Procurement Mgr
Data Migration
✗ BAD: “Migrate all customer data.”
✓ GOOD:
“As a Data Migration Lead, I want to migrate active customer records with validated addresses and credit terms, so Sales can process orders from day one.”
Acceptance Criteria:
Only active customers (inactive >24mo excluded)
Address validated against PAF database
Credit terms mapped to new credit groups
Duplicates merged (company name + postcode)
Validation report: counts, match rates, exceptions
Programme Lifecycle · Delivery Playbook · User Stories
Notes: Worked examples for HR, Procurement, and Data Migration. Walk the room through the good and bad versions.
The acceptance criteria become the FAT checklist. That's the practical test of a good user story — could a tester build a checklist from it without asking questions? If yes, it's good. If no, rewrite.

## Slide 21: FAT & Mini-BAT: Testing During Sprints
FAT Purpose
SI Tester validates each completed Feature against acceptance criteria. Process Owner accepts at sprint review.
When: Every sprint | Executed by: SI Tester | Accepted by: Process Owner at sprint review
How It Works
Sprint delivers completed User Stories
SI Tester executes FAT during the sprint against acceptance criteria
Sprint review: Process Owner reviews evidence, witnesses demo, hands-on validation where appropriate
Each criterion: Pass / Fail / Partial
Pass: Process Owner signs FAT acceptance form. Fail: defect raised, story returns to backlog
Mini-BAT: Business Acceptance During Sprints
Run every 2nd or 3rd sprint in addition to FAT:
Benefit Owner runs a realistic scenario across delivered Features
1–2 hours, hands-on in the system, no formal test scripts
Purpose: early warning that what is being built works for the business
Example: Sprint 4 delivers order entry + credit check + partial shipment. Sales Ops lead runs an end-to-end order — catches usability issue at Sprint 4, not at UAT in Month 6
Example: FAT for Recurring Journals
✓ Templates configurable by Finance
Created 3 templates with different frequencies → PASS
✓ Auto-generated on first working day
Set period-end, triggered auto-generation at 06:00 → PASS
✗ Failed journals flagged within 1 hour
Introduced error — alert took 3 hours → FAIL (P2)
✓ Completes within 4 hours for 200 journals
Generated 200 journals in 2.5 hours → PASS
FAT Evidence Required
Screenshot/recording of each criterion tested
Process Owner sign-off form
Any defects logged with classification
Programme Lifecycle · Delivery Playbook · FAT & Mini-BAT
Notes: FAT runs during the sprint. SI Tester executes against the user-story acceptance criteria. Process Owner attends sprint review, reviews evidence, validates the demo, hands-on where appropriate.
Mini-BAT is the Process Owner's spot-check mid-sprint — picks a scenario, walks through it, checks the system behaves as expected. Catches design errors before sprint close.
Worth flagging: FAT is technical sign-off; Mini-BAT is business sign-off. Both must happen each sprint.

## Slide 22: SIT: System Integration Testing — Approach
Purpose
Validate that components work together end-to-end across workstreams and 3rd party systems. Joint Client + SI ownership (Client Test Manager leads, SI supports). Comes after SAT.
When: After SAT signed off — SAT proves the solution functionally; SIT proves it integrates
Who: Client Test Manager (owns) · SI Test Team (supports) · Solution Architect (signs off architecture)
What SIT Tests That FAT Does Not
Data flows between modules
Integration with external systems (CRM, bank, EDI)
Cross-workstream process handoffs
Data consistency across modules
Batch processing and scheduled jobs
SIT Scenarios
Order-to-Cash E2E: Order → credit → fulfilment → despatch → invoice → payment → cash allocation
Procure-to-Pay E2E: Requisition → PO → goods receipt → invoice → 3-way match → payment
Month-End Close: Journals → IC eliminations → FX reval → trial balance → reporting
Data Migration Validation: Migrated data used in all above scenarios
Exit Criteria
All E2E scenarios pass
All integrations tested with realistic data volumes
Zero P1 defects, P2 resolved or accepted
Client Test Manager + Solution Architect sign off
Programme Lifecycle · Delivery Playbook · SIT
Notes: SIT tests end-to-end processes across modules and external integrations. This is where the gaps between workstreams surface.
Client Test Manager owns execution. Solution Architect signs off the technical bits. Process Owners sign off the business outcomes. Three sign-offs because integrations cross all three.

## Slide 23
UAT & Pre-UAT: User Acceptance Testing — Approach
Purpose
Formal, scripted acceptance testing executed by USERS, confirming the system supports end-to-end business processes. Scripts written by the business (Process Owners + Test Manager). Industry-standard acceptance gate — what auditors expect.
When: After SIT signed off. Pre-UAT precedes UAT. Before BAT.
Who executes: USERS / business representatives. Who supports: Client Test Manager, BAs, SI Functional Leads (queries/defects). Who signs off: Client Test Manager + Process Owners.
How UAT Differs from FAT and BAT
FAT tests individual Features during sprints (SI Tester) — UAT tests end-to-end business processes (Users)
UAT is scripted and systematic — scripts written by the business based on real business processes (not just user stories)
BAT is scenario-based and unscripted (a wider business-readiness test) — UAT is the formal scripted evidence trail
UAT Test Approach
Test scripts authored by Process Owners + Client Test Manager based on end-to-end business processes (Pre-UAT)
Each script references the business process and traces back to user stories where applicable
Users execute hands-on — supported by Client Test Manager and BA. Process Owners coordinate, do not execute the scripts themselves
Each script marked: Pass / Fail with defect reference. UAT Scope = E2E (multi-dept business processes) + Isolated (single-workstream) + DILO/WILO (Day/Week In the Life Of). Pre-UAT rehearsal de-risks UAT.
UAT sign-off per workstream by Client Test Manager + Process Owners when all scripts pass
UAT Exit Criteria
All test scripts executed
All critical and high-priority scripts pass
Zero P1 defects
P2 defects resolved or formally accepted with workaround
Client Test Manager + Process Owner sign-off per workstream
"UAT is the formal evidence trail that the system meets requirements. It is what auditors and regulators will ask for.
A system can pass UAT — every script passes — and still fail BAT because the end-to-end business process feels wrong or is too slow. This is why both are needed."
Programme Lifecycle · Delivery Playbook · UAT
Notes: UAT is the formal evidence trail that the system supports end-to-end business processes — auditors and regulators expect it.
Scope splits into three test types:
- E2E Tests: multi-department processes from start to finish.
- Functional Scenarios: deeper validation per process area.
- Edge cases and exception handling.
Critical role split to land: USERS execute. Process Owners + Client Test Manager sign off. Most common mistake: Process Owners running scripts themselves, which means real users never touch the system before go-live. Don't let it happen.
Pre-UAT is the smoke pass before users get involved — catches the obvious breaks so users aren't burning time on environment issues.

## Slide 24: BAT: Business Acceptance Testing — Approach
Purpose
Validate that the business can operate using this system. Real users, real scenarios, realistic data.
When: After UAT complete
Executed by: Process Owners + Senior Users
Sign-off: Benefit Owners + Exec Sponsor
How BAT Differs
Not script-based: business scenarios, not step-by-step scripts
Realistic data: migrated production data, not sanitised
Tests outcomes: "Can you close the books in 5 days?"
Two-tier sign-off: Process Owners execute, Benefit Owners review and approve
BAT Scenarios (executed by Process Owners)
Finance: Financial Controller runs month-end close (IC, FX reval, reporting). 5 days.
Sales: Sales Ops Lead processes 50 orders (credit holds, returns, multi-currency).
Procurement: Procurement Mgr runs P2P for 20 reqs (3-way match + payment run).
HR: HR Ops Lead processes 5 new starters through full onboarding.
Exception: Process Owner tests recovery (e.g. bank feed lost mid-payment).
Exit Criteria
All scenarios completed by Process Owners and Senior Users
Benefit Owners confirm KPI targets achievable based on evidence
Exception handling procedures documented and tested
Exec Sponsor authorises handover to Deploy phase (Cutover Planning (S15))
Programme Lifecycle · Delivery Playbook · BAT
Notes: BAT is the business simulation. Benefit Owners run realistic scenarios with real data volumes. Not scripted — scenario-based.
The point: can the business actually operate on this system? A system can pass UAT and fail BAT — the scripts pass but the day-job throughput doesn't work. BAT catches that.

## Slide 25: NFT: Non-Functional Testing — Approach
Test Area | What We Test | Pass Criteria
Performance | Response times under expected user load | All transactions < agreed thresholds (e.g. 3 sec)
Load / Stress | System behaviour under peak volumes | Handles 150% of expected peak without degradation
Data Migration | Full migration with production volumes | Completes within cutover window, 99.5%+ validation
Security | Role-based access, data segregation, audit trail | No role accesses data outside permission set
Backup / DR | Backup completion, restore time, failover | Restore within agreed RTO; failover tested
Batch Processing | Scheduled jobs, overnight processing | All batch jobs complete within overnight window
Programme Lifecycle · Delivery Playbook · NFT (Non-Functional Testing)
Notes: NFT — non-functional testing. Performance, security, resilience.
Worth flagging the cloud vendor angle: on D365, S/4HANA Cloud, Oracle Cloud, Workday, the vendor sets production-readiness prerequisites — regression pass rate, NFT certificate, defect thresholds (typically zero P1, defined P2 ceiling). These align with but are independent of your UAT/BAT thresholds.
Common trap: programme passes its own UAT, fails the vendor deployment readiness check, slips production by weeks. Test exit criteria must be aligned to vendor prerequisites at S10, not discovered at S14. That's why vendor service tier confirmation at S10 matters.

## Slide 26: Defect Management: Classification, Resolution & Retest
Priority | Description | Response Time | Resolution Target
P1 — Critical | System unusable, no workaround | Immediate | 24 hours
P2 — High | Major function impaired, workaround exists | 4 hours | 3 working days
P3 — Medium | Minor function impaired, acceptable workaround | 1 working day | Next sprint
P4 — Low | Cosmetic or minor inconvenience | Next sprint planning | Backlog
Defect Lifecycle
Raised → Classified → Assigned → Resolved → Retested → Closed (or Reopened)
Defect Governance
Client Test Manager owns defect log, reports daily during test execution
P1 defects escalate immediately to PM + Solution Architect
P2 reviewed in daily test standup
Steering Committee receives weekly defect summary
Go-Live Defect Criteria
Zero P1 open
Zero P2 open, unless a workaround is agreed by Design Authority and Process Owner and documented (formal SC acceptance)
P3 defects documented with post-go-live fix plan
P4 defects in backlog for future release
Programme Lifecycle · Delivery Playbook · Defect Management
Notes: Defect classification drives priority. P1 is a showstopper. P2 is significant impact.
Go-Live Gate criteria: zero P1, AND zero P2 unless a workaround is agreed and documented. The workaround clause matters — sometimes a P2 has a manual workaround and the business accepts it for a limited period. That's a legitimate go-live; what isn't legitimate is going live with unacknowledged P2s.
P3 and P4 accepted with workarounds but documented and tracked.
The defect lifecycle: discovered → triaged → resolved → retested → closed. Don't shortcut the retest step.

## Slide 27: Build & Configuration (S13): Build Complete Checkpoint Checklist
# | Criterion | Evidence | Approved By
1 | All Features built and unit tested | Unit test results per Feature | Tech Lead
2 | All integrations built and unit tested | Integration test results | Solution Architect
3 | FAT completed — SI Tester executed; Process Owners accepted per Feature at sprint reviews | FAT sign-off forms | Process Owners
4 | Data migration scripts built, first dry run completed | Dry run results report | Data Migration Lead
5 | All sprint review sign-offs collected | Sprint review minutes | Scrum Master
6 | No outstanding P1 defects from FAT | Defect log | Client Test Manager
7 | Test strategy for SAT, SIT, Pre-UAT/UAT, BAT, NFT confirmed and resourced | Test strategy document | Client Test Manager
Programme Lifecycle · Delivery Playbook · S13 Checkpoint
Notes: End-of-S13 gate: Build Complete. All sprints delivered, Unit testing passed, FAT signed off, Mini-BAT feedback addressed, backlog items marked Done, code frozen and ready for formal Testing (S14).
Don't rush this gate. If FAT or Mini-BAT items are open, don't move into S14 — you'll just absorb the backlog into SIT and miss the integration issues underneath.

## Slide 28: Testing (S14): Test Exit & Go-Live Readiness Checklist
# | Criterion | Evidence | Approved By
1 | SAT completed — SI Test Lead signed off integrated functional/usability/regression | SAT scripts + results + sign-off | SI Test Lead
1 | SIT completed — all end-to-end scenarios pass | SIT results + sign-off | Client Test Manager + Sol. Architect
2 | UAT completed — Users executed all scripts; Client Test Manager + Process Owners signed off per workstream | UAT scripts + results + sign-off forms | Process Owners
3 | BAT completed — Benefit Owners signed off | BAT results + sign-off forms | Benefit Owners
4 | NFT completed — performance, security, DR, batch processing pass | NFT results + sign-off | IT Ops + Sol. Architect
5 | Zero P1; zero P2 unless a workaround is agreed and documented (formal acceptance recorded) | Defect log | Client Test Manager
6 | Data migration validated (second dry run passed) | Migration validation report | Data Migration Lead
7 | Performance tested against volume benchmarks | Performance test results | Solution Architect
8 | Training completed for all user groups | Training completion records | Change Lead
9 | Cutover plan documented and rehearsed | Cutover plan | PM
10 | Hypercare plan and support structure confirmed | Hypercare plan | PM + SI Lead
11 | Executive Sponsor confirms go-live authorisation | Go-live authorisation form | Executive Sponsor
Programme Lifecycle · Delivery Playbook · S14 Checkpoint
Notes: End-of-S14 gate: Go-Live Readiness. The most critical gate in the programme.
Eight criteria including UAT sign-off (the new row), SIT pass, BAT pass, SAT pass, NFT cert, zero P1, zero P2 unless workarounds agreed and documented, cutover plan rehearsed, rollback plan documented and tested.
The Go-Live Gate is the Exec Sponsor's binary call — not a board decision. If any item is red, the business doesn't go live. Worth pausing on this — the Exec Sponsor signs because they're the one accountable to the board for the call.

## Slide 29: RACI Matrix: Stages 10–14
Activity | Exec Sponsor | PM | Sol. Arch | BA | Process Owners | SMEs | Users | Scrum Master | Test Lead | Change Lead | SI Prog Dir | SI Sol Arch | SI Func Leads | SI Tech Lead
Mobilisation & team setup | A | R | C | C | I | I | I | C | I | C | R | C | I | I
Environment provisioning | I | A | R | I | I | I | I | I | C | I | I | R | I | R
Discovery workshops | I | A | C | R | R | R | I | C | I | C | I | C | R | C
Gap analysis | I | I | R | R | C | C | I | I | I | I | I | R | R | C
Backlog creation | I | C | C | R | C | C | I | R | I | I | I | C | R | I
FDD production | I | I | R | C | C | C | I | I | I | I | I | C | R | R
Design Authority governance | I | C | A | C | C | I | I | I | I | I | I | A | C | C
Sprint planning | I | C | C | C | C | I | I | R | I | I | I | C | C | I
Sprint execution (build) | I | C | C | I | I | I | I | R | I | I | I | C | R | R
Unit testing | I | I | C | I | I | I | I | I | C | I | I | C | I | R
Sprint reviews / FAT | I | C | I | C | A | C | I | C | C | I | I | I | R | I
Mini-BAT * | I | C | I | C | A | R | I | C | C | I | I | I | C | I
SAT execution | I | C | C | I | I | I | I | I | A | I | C | C | R | R
SIT execution | I | C | A | C | C | I | I | I | R | I | C | C | C | R
UAT execution | I | C | I | C | A | C | R | I | C | I | I | I | C | C
BAT execution * | A | C | C | R | R | R | C | I | R | C | I | I | C | I
NFT execution | I | C | A | I | I | I | I | I | R | I | I | R | I | R
Defect management | I | C | C | I | I | C | I | I | R | I | C | C | C | R
Deploy readiness | A | R | C | C | C | C | I | I | C | C | C | C | C | C
Programme Lifecycle · Delivery Playbook · RACI
* FAT: SI Tester executes (R), Process Owner accepts (A) at sprint review. SAT: SI Test Lead owns (A), SI Functional/Technical execute (R). SIT: Client Test Manager owns (A), SI supports (R). UAT: USERS execute (R), Client Test Mgr + Process Owners sign off (A). BAT/Mini-BAT: POs+SMEs execute (R), Benefit Owners sign off (A). NFT: IT Ops + SI-TL execute (R), Solution Architect signs off (A).
Notes: RACI matrix for S10–S14. Four SI roles broken out: Programme Director, Solution Architect, Functional Leads, Technical Lead.
The SI is not a single entity. Each role has distinct responsibilities at each stage. Use the RACI when assigning people; revisit at every stage transition.