## Slide 1
Deploy & Post-Programme
Stages 15–19: From Cutover to Benefits Realisation
DEPLOY · Stages 15–17
POST-PROGRAMME · Stages 18–19
Programme Lifecycle · Final Phases · Proving the Value
Notes: This deck covers the final stages — cutover planning through go-live, hypercare, and into benefits realisation and platform optimisation.
By this point, the system's built and tested. BAT is signed off. The Exec Sponsor has confirmed go-live readiness. Everything from here is about executing the transition, stabilising operations, and proving the programme delivered the value it promised.
Worth flagging: the benefits baselines were set in Value Definition & Case for Change (S2) — over 12 months ago. The Benefits Map has named owners, agreed KPIs, and measurement methods. If any of that's missing, you can't prove the programme worked. You're just hoping it did.

## Slide 2
Why Deployment Governance Matters
Programme Lifecycle · Deploy & Post-Programme
“The quality of your Benefits Realisation & Review (S18) benefits realisation was determined in Week 6 of your pre-programme. Everything in between is the work.”
Execute a controlled transition to the new system, stabilise operations, and prove benefits realisation against pre-programme baselines.
Three risks when deployment is poorly governed
Chaotic cutover: data migration fails, users cannot log in, critical processes break on day one
Premature hypercare exit: support withdrawn too early, users revert to old workarounds
Benefits evaporation: nobody tracks KPIs after go-live, the board never learns if the investment paid off
What governed deployment ensures
Cutover is rehearsed with documented go/no-go criteria and rollback plans
Hypercare has defined exit criteria — support is not withdrawn until stability is proven
Benefits are measured against Value Definition & Case for Change (S2) baselines with named owners reporting to Steering Committee
Notes: Three failure patterns in deployment — all avoidable.
Chaotic cutover. A professional services firm went live on a Friday evening. By Saturday morning, 40 per cent of users couldn't access the system because role provisioning was incomplete. Data migration had missed 3 months of open transactions. Root cause: the cutover plan had never been rehearsed end to end.
Premature hypercare exit. A manufacturer contracted 4 weeks of SI hypercare. At week 4, 12 P3 defects open and warehouse adoption at 60 per cent. The SI exited per contract. Two months later the programme was in recovery, costs doubled.
Forgotten benefits. A retail business went live, ran hypercare cleanly, declared success. Two years later they couldn't tell you what benefits had been realised. Baselines were estimates, owners were unclear, KPIs hadn't been tracked. The whole investment case was fictional after the fact.
Governance prevents all three. Cutover Lead owns the runbook. Hypercare exit is gated, not contractual. Benefits Realisation & Review (S18) holds people accountable.

## Slide 3
What This Deck Covers
Core Slides (1–16)
Why deployment governance matters
Five stages: Cutover Planning, Go-Live, Hypercare, Benefits Realisation, Optimisation
Go/No-Go decision framework
Hypercare operating model and exit criteria
Benefits measurement against Case for Change (S2) baselines
Programme closure and transition to BAU
Roles, timeline, and executive decision gates
Appendix — Deployment & Closure Playbook (17+)
Cutover plan template and rehearsal checklist
Go/No-Go decision framework with criteria
Hypercare operating model and support structure
Benefits tracker and reporting templates
Programme closure report structure
Lessons learned framework
Stage gate checklists for every stage
Illustrative — to be adapted to your organisation’s deployment approach and BAU operating model
Notes: Map for the deck. Core slides for the governance story; appendix for operational playbooks.
Five stages, two phases. Deploy runs S15–S17 — Cutover Planning (S15), Deployment & Go-Live (S16), Hypercare & Stabilisation (S17). Post-Programme runs S18–S19 — Benefits Realisation & Review (S18), Optimisation & Maturity (S19).
The programme formally closes at end of S18 once the agreed benefit reviews are complete. S19 carries on as continuous improvement.

## Slide 4
Stages 15–19 at a Glance
Stage | Name | Key Output | Duration
15 | Cutover Planning | Cutover plan rehearsed, go/no-go criteria defined, rollback plan tested | 3–4 weeks
16 | Deployment & Go-Live | System live, data migrated, war room active | 1–2 weeks
17 | Hypercare & Stabilisation | Defects resolved, adoption monitored, exit criteria met | 4–8 weeks
18 | Benefits Realisation & Review | KPIs measured against baselines, closure report documented | 3–6 months
19 | Optimisation & Maturity | CI pipeline, platform health reviewed | Ongoing
DEPLOY (Deploy (S15–S17)) Transition to the new system and stabilise operations
POST-PROGRAMME (Post-Programme (S18–S19)) Prove benefits and establish continuous improvement
Deploy phase: typically 8–14 weeks. Post-Programme: 3–6 months formal, then ongoing BAU governance.
Notes: Five stages. First three are intense — cutover, go-live, hypercare in quick succession over 2 to 3 months. Post-Programme stages (S18–S19) are longer and less intense, but arguably more important — this is where you prove the investment delivered.
The S18 timescale is deliberately long. Benefits don't realise on day one; you need at least two quarterly review cycles before you can talk credibly about realisation.

## Slide 5
Cutover Planning (S15)
“The cutover plan is not a document. It is a rehearsed, timed, sequenced operation. If it has not been rehearsed, it is not a plan — it is a hope.”
Key Objectives
Finalise cutover plan with detailed task sequencing and timing
Define go/no-go criteria with Steering Committee
Document contingency and rollback plan
Rehearse full cutover end to end (cutover dress rehearsal)
Confirm user readiness — training complete, communications issued
Validate data migration final dry run
Outputs
Cutover plan with task-level sequencing and owners
Go/no-go criteria signed off by Steering Committee
Contingency and rollback plan documented and rehearsed
Cutover dress rehearsal results with timing validated
User readiness confirmation from Change Lead
Programme Lifecycle · Deploy · S15
Notes: Cutover Planning (S15) is where preparation meets reality. System's built and tested; now you plan exactly how you transition from old to new.
The cutover plan must be granular — task-level sequencing, owners, durations, dependencies, go/no-go checkpoints. Owned by the Cutover Lead, not the PM (different jobs).
The dress rehearsal is non-negotiable. Run the cutover end-to-end against production-like data. The first rehearsal will fail; that's the point. You find issues with 4 weeks to fix them, not 4 hours.
Worth flagging: rollback. Have a tested rollback plan. If you can't rollback, you can't go live — that's the discipline.

## Slide 6
Deployment & Go-Live (S16)
“Go-live is not the end. It is the moment the benefits clock starts. Baselines set 12+ months ago are now measured for real.”
Key Objectives
Execute data migration and validate against quality thresholds
Transition system to live for all users
Activate war room with SI, programme team, and IT support
Issue go-live communications to all stakeholders
Execute go/no-go decision per agreed criteria
Begin KPI tracking from the moment of go-live
Outputs
Data migration completed and validated
System live for all users
War room active with incident management
Go-live communications issued
KPI tracking initiated (benefits clock starts)
Programme Lifecycle · Deploy · S16
Notes: Go-live weekend. Most operationally intense period in the entire programme.
The war room is the command centre. Staff it with the PM, Cutover Lead, Solution Architect, SI Functional Leads per workstream, IT infrastructure support, Change Lead. Run it 12 hours a day for the first week.
The Benefit Owners are NOT in the war room — they're confirming process readiness on day one and reporting early adoption signal. Different jobs.
Worth flagging: floor-walking support. Change Lead manages a team of floor-walkers in the offices and warehouses on day one. Real users will hit problems in the first hour; floor-walkers solve them in real time and feed patterns back to the war room.

## Slide 7
Go/No-Go Decision Framework
Decision-maker: Executive Sponsor (with Steering Committee input) | Timing: 24 hours before planned go-live
# | Go Criterion (ALL must be met) | Confirmed By
1 | Zero P1 defects open | Client Test Manager
2 | Zero P2 defects open, unless a workaround is agreed and documented (formal acceptance recorded) | Client Test Manager + Exec Sponsor
3 | BAT signed off by all Benefit Owners | Benefit Owners
4 | Data migration final dry run passed at 99.5%+ | Data Migration Lead
5 | All users provisioned and access tested | IT / Solution Architect
6 | Training completed for all user groups | Change Lead
7 | War room staffed and incident process confirmed | PM
8 | Rollback plan tested and ready | Solution Architect
9 | Go-live communications prepared | Change Lead
10 | Cutover dress rehearsal completed within window | Cutover Lead
No-Go Triggers (ANY one triggers delay):
Any P1 defect open | Data migration validation below 99.5% | BAT not signed off by any Benefit Owner | Rollback plan not tested | Executive Sponsor not available
Notes: Most consequential decision in the programme. The Exec Sponsor personally decides: are we ready to operate the business on this system from Monday morning.
Ten criteria, all binary. No partial readiness. If any criterion fails, you delay.
The cost of delaying go-live by 4 weeks is high — but the cost of going live unready is much higher. Hold the line.
Worth flagging the role split for criterion 10 (Cutover dress rehearsal completed within window) — that's owned by the Cutover Lead, not the PM. And the workaround clause on criterion 2: zero P2 unless a workaround is agreed and documented (formal acceptance by Client Test Manager + Exec Sponsor). That's not a loophole — it's how you handle legitimate exceptions.

## Slide 8
Hypercare & Stabilisation (S17)
“Hypercare exit is earned, not scheduled. Support is not withdrawn until stability is proven and adoption is embedded.”
Key Objectives
Resolve critical defects within agreed SLAs
Monitor user adoption and provide targeted support
Validate system performance against benchmarks
Manage early-life change requests through governance
Meet hypercare exit criteria before transition to BAU
Outputs
Defects resolved — zero P1, P2 trending to zero
User adoption metrics tracked (target: 85%+ active usage within 8 weeks)
System performance validated against benchmarks
Hypercare exit criteria met and documented
BAU support structure confirmed and transitioned
Programme Lifecycle · Deploy · S17
Notes: Hypercare is the bridge between go-live and normal operations. Typically 4 to 8 weeks, depending on complexity and adoption speed.
User adoption is the leading indicator. If people aren't using the system, the benefits won't materialise. Track active usage by role — not just login counts. A user logging in once a day for 5 minutes isn't using the system.
Worth flagging: hypercare exit is gated, not contractual. The SI doesn't leave because the contract says they leave; they leave when the exit criteria are met. If criteria aren't met, the SI stays — and the contract should have provision for that.

## Slide 9
From Deployment to Value Realisation
The system is live. Operations are stable. Hypercare is complete. Now we answer the question the board has been waiting for: Did this programme deliver the value it promised?
DEPLOY
POST-PROGRAMME
Notes: Transition from delivery to accountability. Everything up to here has been about building and deploying a system. Everything from here is about proving it was worth it.
The Benefits Map was created in Value Definition & Case for Change (S2) with real baselines from Functional Leaders. It has named Benefit Owners. It has agreed KPIs and measurement methods.
Worth flagging: this is when the work done in Pre-Programme pays off. If baselines were estimated, owners were unclear, or KPIs were never agreed, this is when that surfaces. And there's no way to fix it retrospectively. Pre-Programme rigour is what makes Benefits Realisation possible.

## Slide 10
Benefits Realisation & Review (S18)
“Benefits are measured against baselines from Value Definition & Case for Change (S2) — real numbers set 12+ months before go-live. The ROI Driver Matrix is the scorecard.”
Key Objectives
Measure KPI actuals against Value Definition & Case for Change (S2) baselines and targets
Benefit Owners report progress, blockers, and corrective actions
Update Benefits Tracker and present to Steering Committee
Identify benefits at risk and agree interventions
Produce programme closure report with lessons learned
Outputs
Benefits Tracker with actuals vs baselines vs targets
Benefit Owner review reports per function
ROI Driver Matrix scorecard — actual vs planned
Programme closure report with lessons learned
Board-level benefits realisation summary
Programme Lifecycle · Post-Programme · S18
Notes: S18 is where the programme is held accountable. Benefit Owners present their KPI actuals against the baselines and targets agreed in S2.
This isn't a one-off review. Benefits realisation runs quarterly for 3 to 6 months minimum. Some benefits realise in 2 quarters; some take 4 or more. The programme doesn't close until at least two quarterly review cycles are complete.
Worth flagging: the Benefit Owner brings their own data, in their own template, signed by their own finance contact. Programme Manager coordinates the review but doesn't produce the numbers. Otherwise the Benefit Owner's accountability is fictional.

## Slide 11
Optimisation & Maturity (S19)
“Optimisation & Maturity (S19) ensures the platform continues to deliver value beyond go-live. The programme ends. The value chain does not.”
Key Objectives
Establish continuous improvement pipeline from benefit reviews
Agree and fund additional phase/module roadmap
Review platform health — technical debt, performance, security
Deepen user adoption through advanced training and self-service
Transition programme governance to BAU governance
Outputs
Continuous improvement pipeline prioritised by value
Additional phase roadmap agreed and funded
Platform health review completed
Advanced training programme in place
BAU governance model confirmed (replaces programme governance)
Programme Lifecycle · Post-Programme · S19
Notes: S19 is where the programme transitions to business as usual — but with a deliberate continuous improvement mandate.
The continuous improvement pipeline is built from the benefit review data. Every quarterly review in S18 identifies improvement opportunities. Those feed the S19 pipeline. Without that linkage, S19 becomes a wishlist of features people would like; with the linkage, it stays anchored to benefits.
Worth flagging: a phase roadmap for further improvements gets approved here, with funding scoped at the same rigour as the original programme. No "while we're at it" enhancements without a business case.

## Slide 12
Inputs & Outputs Across Stages 15–19
# | Stage | Key Inputs | Key Outputs
15 | Cutover Planning | BAT sign-off, migration dry run results, training records | Cutover plan, go/no-go criteria, rollback plan, rehearsal results
16 | Deployment & Go-Live | Cutover plan, go/no-go decision, migration scripts | System live, migration validated, war room active, KPI tracking started
17 | Hypercare & Stabilisation | Live system, defect log, adoption metrics | Defects resolved, adoption confirmed, hypercare exit, BAU transition
18 | Benefits Realisation | Benefits Map (S2), baseline KPIs, adoption data | Benefits Tracker, ROI scorecard, closure report, lessons learned
19 | Optimisation & Maturity | Benefit review data, platform health data, improvement ideas | CI pipeline, phase roadmap, platform health plan, BAU governance
Programme Lifecycle · Deploy & Post-Programme
Notes: Inputs and outputs across S15–S19. The thread from Pre-Programme to Post-Programme is visible. S18 inputs include the Benefits Map from S2 — those baselines set in Week 6, over 12 months before go-live.
If any of those Pre-Programme outputs are missing, the chain breaks. Walk left to right; the chain itself is the message.

## Slide 13
Roles & Responsibilities During Deploy & Post-Programme
Role | S15: Cutover | S16: Go-Live | S17: Hypercare | S18: Benefits | S19: Optimisation
Exec Sponsor | Approves go/no-go criteria | Makes go/no-go decision | Reviews stability weekly | Signs off benefits report | Approves phase roadmap
Programme Manager | Owns cutover plan, runs rehearsal | Commands war room | Manages defect resolution | Coordinates benefit reviews | Manages transition to BAU
Cutover Lead | Owns cutover runbook; runs dress rehearsals | Commands cutover war room; runs the live cutover | Hands over to Hypercare; tapering off | — | —
Project Manager(s) | Plans workstream cutover tasks | Coordinates workstream cutover execution | Manages workstream defect resolution | Supports benefit owners with workstream data | Hands workstream platform to BAU owner
Solution Architect | Validates migration, tests rollback | Leads technical war room | Resolves technical defects | Validates system performance | Leads platform health review
Change Lead | Confirms user readiness | Manages floor-walking support | Monitors adoption | Assesses change embedding | Plans advanced training
Benefit Owners | Confirm KPI tracking readiness | Confirm process readiness | Report early adoption | Present KPI actuals vs targets | Identify improvement opportunities
IT Operations | Validates infrastructure readiness | Manages system monitoring | Takes over BAU support | Maintains platform performance | Executes technical roadmap
Notes: Role emphasis shifts in these stages.
The PM moves from delivery coordination to operational command during cutover, then to benefits coordination in S18. The Cutover Lead is the operational owner of cutover and go-live — runbook, rehearsals, the live cut. The Change Lead becomes the most important role during hypercare — adoption determines benefits, and adoption is Change's job. Benefit Owners step forward in S18, becoming the public face of programme accountability.
Worth flagging: in S15–S17, the SI is heavily involved. From S18 onwards, accountability shifts to the Client. The SI may have a continuing support relationship, but the benefits are owned and reported by the Client.

## Slide 14
Deployment Timeline: Stages 15–19
Cutover Planning (S15)
S16: Go-Live
Hypercare & Stabilisation (S17)
Benefits Realisation & Review (S18)
S19: Optimisation
Weeks 1–4
Week 5
Week 12
Month 9+
★
Go/No-Go Decision
★
GO-LIVE
★
Hypercare Exit BAU Transition
★
First Benefits Review
★
Programme Closure
Deploy phase: typically 8–14 weeks. Post-Programme: 3–6 months formal, then ongoing BAU governance.
Notes: Deploy phase is intense and compressed — about 12 weeks from cutover planning to hypercare exit. Post-Programme is deliberately longer — 6 months minimum for benefits realisation.
The go/no-go decision at Week 4 is the highest-stakes decision. Schedule it for a Tuesday or Wednesday — not a Friday. You want time to act on the decision, not to handle it when half the team is unavailable.

## Slide 15
The Benefits Thread: From Baseline to Realisation
Wk 6 S2
Baselines set from real data
Wk 8 S2
Benefits mapped to named owners
Wk 12 S3
Owners locked in Governance Charter
S9
Change network mobilised
S14
BAT validated against KPIs
S16
Benefits clock starts at go-live
S18
Measured against Week 6 baselines
S19
CI drives further value
“The chain is unbroken or it is broken everywhere. Every benefit measured at Benefits Realisation & Review (S18) was set up in Week 6.”
Notes: The complete benefits story on one slide. Baselines set in Week 6 — real data from Functional Leaders, not estimates. Carried through the entire programme.
If the chain was broken at any point — baselines estimated, owners not named, KPIs not measurable — this slide can't be drawn. Take a moment to walk the chain visibly. That's the strongest argument for Pre-Programme rigour you'll ever make to the room.

## Slide 16
Deploy & Post-Programme Decision Points
“One executive go/no-go and three phase checkpoints. The Deployment & Go-Live (S16) go/no-go is the single most consequential executive decision in the programme.”
Checkpoint — Cutover Readiness (S15)
Cutover plan rehearsed, go/no-go criteria agreed, rollback tested, users trained. Proceed to go-live.
EXEC GO / NO-GO — Go-Live (Deployment & Go-Live (S16))
All criteria met per the Go/No-Go framework. Executive Sponsor's binary decision — proceed with cutover or stop. Benefits clock starts at go-live.
Checkpoint — Hypercare Exit (S17)
Zero P1 for 2+ weeks, P2 below 5 and trending down, adoption above 85%, BAU support ready. Transition to business as usual.
Checkpoint — Programme Closure (S18)
Benefits tracked for minimum 2 quarterly cycles, programme closure report produced, lessons learned documented, BAU governance confirmed.
Programme Lifecycle · Deploy & Post-Programme
Notes: Four decisions across the phases — but only one is binding for go-live, and none is a Board Gate. The two Board Gates of the lifecycle (Funding Envelope at end of S6, Full Business Case at end of S12) have already passed by the time Deploy begins.
Exec Go-Live Go/No-Go (GLG) at end of Cutover Planning (S15) carries the most personal accountability. The Executive Sponsor — not the Board — makes the binary call: proceed with cutover or stop. Once data starts migrating to production, the cost of pulling back rises by the hour.
Checkpoint — Hypercare Exit at end of Hypercare & Stabilisation (S17) is the most commonly rushed. Commercial pressure to release the SI, desire to close the programme, urge to declare success. Hold the line on the exit criteria. Premature hypercare exit costs more than extending it.
Checkpoint — Programme Closure at end of Benefits Realisation & Review (S18) requires the agreed quarterly benefit reviews to be complete. Not 'we plan to track them' — actually completed.
S19 Optimisation roadmap approval scopes any further investment with the same business case rigour as the original programme. None of these is a Board Gate — they are checkpoints, with the GLG sitting alongside as the one binding executive decision in Deploy.