## Slide 1
SI SELECTION & METHOD ALIGNMENT — S7-S9
SI Selection &
Method Alignment.
Methodology alignment is a selection criterion, not a post-contract assumption.
01
The MSA and SOW 1 (Discovery) are signed at end of S9, before Programme Setup & Mobilisation (S10) — not negotiated later during Discovery.
02
Procurement and Legal due diligence runs during S7-S9 as part of vendor evaluation.
03
The people who will deliver the programme — on both sides — should be in the selection workshops.
SELECTION-PHASE ARTEFACT · TAKE THIS INTO YOUR SI SELECTION WORKSHOPS

## Slide 2
SI SELECTION · PURPOSE
What this deck is for.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
Why methodology alignment belongs in selection — not in Discovery.
01
Anchor the SI selection process around methodology alignment, not just price and demo quality.
02
Establish — before contracts are signed — that the SI's delivery methodology is understood by the Client team and agreed as the single programme method.
03
Surface red flags during selection rather than discovering them in Discovery.
04
Make the commercial framework (MSA, multi-SOW pattern) ready to sign at end of S9, not negotiated into S11.

## Slide 3
SI SELECTION · THREE ROUTES TO MARKET
Three routes to market.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
The three patterns Clients use to bring an SI on board.
ROUTE A
Client → platform vendor
Common in large enterprise and public sector. The vendor refers the opportunity to certified partners via the Partner Center referral programme.
Vendor earns licence revenue; SI earns implementation. The Client still runs RFI/RFP discipline against the referred shortlist — the referral isn't a selection.
ROUTE B
Client → the market
Most common in mid-market and private sector. Formal procurement sequence: RFI to long-list, RFP/ITT to shortlist, orals/demos, BAFO, selection.
The chosen SI typically resells platform licences as part of the engagement.
ROUTE C
Client → a known SI
Common in mid-market. Existing relationship or peer referral. No competitive process — straight to SOW negotiation. Risk: no comparator on price, capability or methodology.
Procurement and Legal due diligence still applies; methodology alignment still applies. The absence of a competitive process makes both harder, not less important.

## Slide 4
SI SELECTION · THE FORMAL SEQUENCE (ROUTE B)
RFI → RFP/ITT → Orals → BAFO.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
The formal selection sequence, with worked-example notes.
RFI · 8-15 VENDORS · 2-3 WKS
Request for Information — long-list filter
Capability, experience, financial standing, methodology overview. No commitment to price or solution.
Worked example — AcmeWidget (mid-market mfg) issued an RFI to 12 D365 partners. Six returned with depth to score; three made the shortlist.
RFP/ITT · SHORTLIST · 4-6 WKS
Request for Proposal / Invitation to Tender
How the SI proposes to deliver, what they would implement, at what price. The first ROM lands here.
Worked example — Three SIs each returned a 60-page proposal with solution architecture, timeline, CVs and ROM at ±30%. Range: £4.1m-£6.8m for the same scope.
ORALS / DEMOS · 1-2 DAYS EACH
Shortlisted SIs present to the Client
The proposed delivery team presents, not just pre-sales. Reference site visits where practical.
BAFO · FINAL ROUND · 1-2 WKS
Best and Final Offer
Final commercial round after orals. The SI knows it's in the final round and prices accordingly.
Worked example — At BAFO the spread narrowed to £4.4m-£5.2m. The middle-priced SI won on methodology alignment, not on price.

## Slide 5
SI SELECTION · PROCUREMENT TERMINOLOGY
Procurement terminology.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
The terms used precisely — same across all three routes.
RFI
Request for Information
Long-list filter: capability, experience, financial standing. No price commitment, no solution.
RFP / ITT
Request for Proposal / Invitation to Tender
Shortlist: how the SI will deliver, what solution they propose, at what price. The first ROM appears here.
RFQ
Request for Quotation
Used when scope is fully defined and the comparison is on price only. Rare in ERP — scope is rarely that fixed pre-Discovery.
BAFO
Best and Final Offer
Final commercial round after orals/presentations. Used to narrow the spread between two or three finalists.
Conflating these terms produces ambiguity at exactly the wrong moment. The RFP is not an RFQ; the orals are not a BAFO; the BAFO is not a contract negotiation. Each has a precise purpose.

## Slide 6
SI SELECTION · THE ONE-METHOD PRINCIPLE
The one-method principle.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
Why the programme needs a single methodology both sides can navigate.
01
Two methods, parallel governance
Two separate methodologies — one Client, one SI — produce confusion, parallel governance, and disputes about which version of “the plan” wins.
02
One agreed programme method
There is one programme method, agreed before contracts. The SI's methodology either aligns with Keystone (lifecycle phases, gates, role definitions, testing levels) or the gaps are explicitly named and bridged in the SOW Suite.
03
Documented, not retrofitted
Method alignment is documented before contracts are signed — not negotiated retroactively at the first Steering Committee.
The simplest test: can your CFO navigate the agreed method without an interpreter? If not, it's not the method.

## Slide 7
SI SELECTION · SELECTION CRITERIA CHECKLIST
Score the SI against these.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
Not just demo polish and price.
#
CRITERION
WHAT TO LOOK FOR
01
Methodology simplicity
Client team can navigate the agreed approach without translation.
02
Governance alignment
SI's gates, checkpoints and roles map cleanly to Keystone — or gaps are named in the SOW Suite.
03
Delivery team presence
The people who will run the programme are in the selection workshops, not just pre-sales.
04
Commercial framework readiness
SI has a standard MSA, can negotiate before S10, and accepts the multi-SOW pattern.
05
Financial viability
Procurement-led DD complete (credit checks, insurance, recent accounts) — not deferred.
06
Testing posture
SI accepts the eight-level testing framework, non-transferable sign-off, and UAT run by independent business testers.
07
Methodology demonstration
SI walks the Client through their proposed method on a comparable engagement.

## Slide 8
SI SELECTION · ROLES IN THE WORKSHOP
Roles expected from SI vs Client.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
Minimum viable team in SI selection workshops.
CLIENT SIDE
The buying and delivery team
›
Executive Sponsor
›
Programme Manager
›
Business Architect
›
Solution Architect (Client side, from S9)
›
Procurement Lead
›
Legal / Commercial
SI SIDE
Delivery, not pre-sales
›
SI Programme Director (delivery, not pre-sales)
›
SI Solution Architect (co-chairs Design Authority)
›
Proposed SI Functional Leads for the largest workstreams
THE TWO FAILURE MODES
If the SI brings only pre-sales: this is a red flag. The pre-sales commitments their delivery team hasn't seen are the most reliable source of post-contract dispute.
If the Client brings only the buying team and not the future delivery team: same problem inverted.

## Slide 9
SI SELECTION · COMMERCIAL FRAMEWORK
Commercial framework checklist.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
MSA, multi-SOW pattern, assumptions review — agreed at S9, signed before S10.
Master Services Agreement (MSA) — overarching contract; reviewed by Legal during S9; signed before S10 entry.
MULTI-SOW PATTERN
WHAT IT COVERS
TIMING
SOW 1 · Discovery
Fixed-scope, fixed-price.
Signed end of S9 with the MSA
SOW 2 · Design
Structure agreed at S9.
Firmed at S12 · Board Gate 2
SOW 3 · Build / Test / Deploy / Hypercare
Structure agreed at S9.
Firmed end of S12
ASSUMPTIONS · PRE-DRAFTED SUITE
›
Assumptions review — every SOW lists its assumptions on a single page; assumptions are tested in selection workshops, not discovered in Discovery.
›
Pre-drafted SoW Suite (Keystone artefact) — the Client walks in with the commercial structure drafted, not waiting for the SI to bring its own.

## Slide 10
SI SELECTION · PROCUREMENT & LEGAL DD
Procurement & Legal due diligence.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
What runs during S7-S9 — not after the SI is chosen.
S7
Market Engagement & RFI
Financial viability checks, credit checks, insurance verification. Built into the RFI scoring, not a separate exercise.
S8
Software Selection
Commercial DD continues alongside the demo and reference-call activity. A vendor that wins on demo and fails on financial viability is not a winner.
S9
SI Selection
Legal reviews the SI's standard MSA. Procurement negotiates terms. SOW 1 (Discovery) drafted and signed alongside the MSA before S10 entry.
If DD slips to post-contract, the Client has lost negotiating leverage at exactly the wrong moment.

## Slide 11
SI SELECTION · COMBINED vs SEPARATE
Combined vs separate selection.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
When software (S8) and SI (S9) selection merge — and when to keep them separate.
METHOD DEFAULT
Separate selection
S8 chooses the platform on its merits; S9 chooses the SI against the chosen platform. Adds time; produces sharper criteria at each stage.
Use when — the platform decision is genuinely open, peer comparators differ in platform choice, or the Client wants explicit pressure on each decision.
COMMON VARIANT
Combined selection
Platform and SI selected together — typically when the chosen SI is also the licencing partner (reselling Microsoft licences as part of the engagement). Faster; reduces decision-fatigue.
Use when — platform is effectively decided, the bundled commercial offer is materially better, and the Client is explicit on which decision dominates.
Risk on combined: the implementation runs on the wrong platform with the right SI, or the right platform with the wrong SI. Get clarity on which is the primary decision before the combined process starts. Both patterns are valid — the method covers both.

## Slide 12
SI SELECTION · QUESTIONS FOR THE SI
Questions for the SI in workshops.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
Distinguishes pre-sales polish from delivery capability.
01
Show us your method on a comparable engagement. Who from that team is on this bid?
02
Which of the people in this room will be on the delivery team? Name them.
03
Walk us through your gates and how they map to ours. Where are the gaps, and how do you bridge them?
04
How does your method handle Discovery sign-off? FDD traceability from workshop to design?
05
Show us your standard MSA. What's negotiable in it; what isn't?
06
What's your position on the Process Owners not running UAT principle?
07
How do you handle re-baselining when scope shifts post-Discovery?
08
Walk us through a recovery you've done. What did you change? What did you keep?

## Slide 13
SI SELECTION · RED FLAGS
Red flags — pull back if you see these.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
Patterns that surface in selection but cost most after contract.
#
RED FLAG — PULL BACK IF YOU SEE IT
01
Pre-sales-only delivery presence — the people in the room won't be the people running the programme.
02
Methodology too dense to explain in plain English — if the CFO can't navigate it, the Steering Committee can't govern it.
03
No standard MSA, or MSA “to be agreed later” — pushes commercial negotiation into Discovery (S11), where weeks slip into months.
04
Resistance to Client governance — “we have our own gates” means the SI runs the programme, not the Client.
05
Insistence on Process Owners running UAT — a different testing philosophy that will collide at Stage 14.
06
Pricing well under benchmark with no commentary on assumptions — the gap closes back during build, slower and more painfully.
07
Reluctance to provide reference sites at peer scale and platform — they don't have any.

## Slide 14
SI SELECTION · REFERENCE CALL GUIDANCE
Reference call guidance.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
Pick references at peer scale, peer platform, and peer programme stage. Two go-live references are worth ten in-flight ones.
WHAT TO ASK
›
What went well, and what would you do differently if you started over?
›
How did the SI handle scope changes? Show me a Change Request and how it was priced.
›
Was the team proposed at selection the team that delivered? If not, what happened?
›
How did the SI handle the period between Discovery sign-off and Design sign-off?
›
Did you go live on the date set at Solution Design (S12)? If not, what slipped and why?
›
Would you use the SI again? For this programme, or for something different?
WHAT TO LISTEN FOR
Hesitation on the team question is a tell
bait-and-switch happens. “Mostly the same” is not yes.
“Great at flexing scope” can mean two things
flexibility helped, or scope drifted. Ask which.
“Tough on commercials” is usually positive
it means the MSA mattered.

## Slide 15
SI SELECTION · METHOD ALIGNMENT SIGN-OFF
Method alignment sign-off.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
Document the agreed approach before contracts — not after.
Output of selection: a one-page Method Alignment Statement, signed by both sides before MSA + SOW 1 sign.
CONTENTS
›
The agreed single programme method — phases, gates, role names, testing levels.
›
Where the SI's standard method differs and how the difference is bridged.
›
Named delivery team on both sides — the people who will deliver the programme.
›
Named Procurement and Legal sign-off on MSA and SOW 1.
›
Confirmation that pre-sales commitments are reflected in SOW 1 scope.
Attach this statement as Schedule A to the MSA. It is now contractually load-bearing — not a working document to be revised.

## Slide 16
SI SELECTION · SUMMARY & NEXT STEPS
Summary & next steps.
SELECTION (S7-S9) · SI SELECTION & METHOD ALIGNMENT
What to take from this deck back into your selection process — take five things away.
1
There are three routes to market. Pick the one that fits the scale and the relationship — but the discipline (financial DD, methodology alignment, MSA negotiation) is the same regardless.
2
Methodology alignment is a selection criterion. The single programme method is agreed before contracts are signed.
3
The delivery team — on both sides — is in the workshops. Pre-sales-only attendance is a red flag.
4
MSA + SOW 1 (Discovery) are signed before S10 entry. Signing SOW 1 mid-S11 is a recurring source of delay.
5
Document the agreed method on one page, signed by both sides, attached as Schedule A to the MSA.
Companion toolkit — RFI Template (S7), RFP Template (S8-S9), Selection Scoring Matrix (S8-S9), Reference Call Questions (S8-S9). All in the Selection-phase toolkit.