## Cover
Benefit Realisation Plan
Stage 18 onwards — quarterly tracking against Stage 12 ROI Driver Matrix.
Purpose
Tracks benefits as they materialise post go-live. Inputs are the targets agreed at Stage 12 (FBC); actuals come from finance MI quarterly. Variance >10% triggers root-cause review with the named Benefit Owner. Reported to SteerCo monthly through Stage 18; transitions to BAU governance at Stage 19.

## Realisation Tracker
Benefit Realisation Tracker
Annual target from ROI Driver Matrix. Quarterly actual & variance. Inputs in BLUE.
# | Benefit | Owner | Annual target (£k) | Yr1 target | Yr1 actual | Yr1 var % | Yr1 RAG | Yr2 target | Yr2 actual | Yr2 var % | Yr2 RAG | Yr3 target | Yr3 actual | Yr3 var % | Yr3 RAG
B-01 | DSO reduction | CFO | 1260 | 315 | 320 | 1.587% | Green | 756 | 765 | 1.19% | Green | 1260 | 1245 | -1.19% | Green
B-02 | Slow-moving inventory | Supply Chain Dir | 570 | 142.5 | 95 | -33.33% | Red | 342 | 380 | 11.11% | Green | 570 | 580 | 1.754% | Green
B-03 | Indirect spend leakage | CPO | 910 | 227.5 | 198 | -12.97% | Amber | 546 | 510 | -6.593% | Amber | 910 | 880 | -3.297% | Green
B-04 | Finance close productivity | Group FC | 360 | 90 | 105 | 16.67% | Green | 216 | 235 | 8.796% | Green | 360 | 380 | 5.556% | Green
B-05 | OTC / revenue protection | Commercial Dir | 396 | 99 | 75 | -24.24% | Red | 237 | 220 | -7.173% | Amber | 396 | 380 | -4.04% | Green
B-06 | Audit savings | Audit | 176 | 44 | 50 | 13.64% | Green | 105 | 110 | 4.762% | Green | 176 | 180 | 2.273% | Green
B-07 | AP / SSC automation | SSC Dir | 378 | 94.5 | 105 | 11.11% | Green | 226 | 240 | 6.195% | Green | 378 | 405 | 7.143% | Green
B-08 | Decision support | CIO | 150 | 37.5 | 25 | -33.33% | Red | 90 | 80 | -11.11% | Amber | 150 | 145 | -3.333% | Green
| TOTAL |  | 4200 | 1050 | 973 | -7.333% |  | 2518 | 2540 | 0.8737% |  | 4200 | 4195 | -0.119%

## Variance Commentary
Variance Commentary
For any benefit with non-Green RAG, capture root cause and corrective action. Reviewed monthly.
Benefit ID | Owner | Period | Variance | Root cause | Action / by when
B-02 | Supply Chain Dir | Yr1 | -33% | Slow-mover write-down deferred — finance review pending Q4 stock count | Action: complete Q4 count by 31-Dec; recognise write-down in Q1
B-05 | Commercial Dir | Yr1 | -24% | Customer portal adoption slower than projected — only 40% of top customers using it | Action: customer success team to drive adoption; targeting 70% by Q2
B-08 | CIO | Yr1 | -33% | Decision support benefit largely qualitative; CFO requesting better quantification | Action: define 3 measurable KPIs by end-Q1; baseline against pre-go-live decisions