Data Migration Specification — Customers

Build & Configuration (S13). Worked example. One per source domain. Companion mapping in Excel.

| Document | Data Migration Specification — Customers |
| --- | --- |
| Version | v1.0 |
| Date | April 2026 |
| Owner | Data Migration Lead (with Commercial Director as Data Owner) |
| Classification | Programme Use |

# 1. Domain overview

| Item | Detail |
| --- | --- |
| Domain | Customers (master) + open AR (transactional) |
| Source system | Legacy ERP (Oracle EBS) |
| Target system | D365 Finance + Supply Chain Management |
| Volume | ~12,400 customer master records; ~78,000 open AR transactions |
| Data Owner (business) | Commercial Director |
| Migration Owner (technical) | SI Data Migration Lead |
| Cleansing approach | Cleanse-in-source (preferred); cleanse-in-flight only for known historical mappings |

# 2. Scope

In scope:

Customer master records active in last 24 months

Customer hierarchies (parent/child relationships)

Customer ship-to addresses (active)

Customer payment terms and credit limits

Open AR invoices (open or partially paid)

Open credit notes

Out of scope (read-only retention in legacy):

Customers with no transactions in last 24 months (~3,800 records)

Closed AR transactions

Historical AR ageing reports (rebuilt from new system data post go-live)

Customer contact history (CRM remains source of truth)

# 3. Field mapping (high level — full mapping in Excel)

Each customer record involves ~45 fields. Full field-by-field mapping with transformation logic, defaults and validation rules is in the companion Data Migration Mapping - Customers.xlsx. Sample of key fields:

| Source field (Oracle EBS) | Target field (D365) | Transformation |
| --- | --- | --- |
| HZ_PARTIES.PARTY_NAME | CustomerName | Direct; truncate 100 chars |
| HZ_CUST_ACCOUNTS.ACCOUNT_NUMBER | CustomerAccount | Prefix with BU code |
| HZ_CUST_ACCOUNTS.STATUS | Blocked | Map A→0, I→1, B→1 |
| HZ_CUST_PROFILE_AMTS.OVERALL_CREDIT_LIMIT | CreditLimit | Direct; convert to entity currency |
| AR_PAYMENT_SCHEDULES_ALL.AMOUNT_DUE_REMAINING | InvoiceAmountOpen | Direct; AR records only |
| HZ_PARTY_SITES.LOCATION_ID | AddressId | Lookup; create if not exists |

# 4. Cleansing rules

| Rule | Action | Owner |
| --- | --- | --- |
| Customer name with leading/trailing spaces | Trim | Cleanse in source |
| Customer name in all caps | Convert to title case (with exceptions list — 'IBM', 'BBC', etc.) | Cleanse in source |
| Duplicate customers (matched on VAT number + name) | Merge in source; nominate survivor | Commercial Director sign-off |
| Missing tax registration number | Block migration; raise to Data Owner | Commercial Director |
| Credit limit = 0 but with active orders | Set to default per category | Cleanse in source |
| Address with no postcode | Geo-lookup; manual review if not found | Cleanse in source |
| Currency mismatch between customer and orders | Block; raise to Data Owner | Commercial Director |

# 5. Reconciliation

Reconciliation runs in three modes for each migration:

Row count: every record extracted is loaded or rejected with documented reason. Variance > 0.1% halts the load

Sum total: customer credit limit sum, open AR sum — must match legacy to ±0.5%

Functional walk: 25 sample customers walked through full transaction history by Commercial Director's team

Reconciliation report produced in Power BI immediately after each load. A 'green' result is pre-condition for sign-off.

# 6. Mock load schedule & exit criteria

| Mock | When | Purpose | Exit criterion |
| --- | --- | --- | --- |
| Mock Load 1 | S13 mid | Quality assessment | All issues categorised; cleansing plan signed off by Data Owner |
| Mock Load 2 | Testing (S14) entry | Functional rehearsal | 100% load success; reconciliation passes; SIT can use the data |
| Mock Load 3 | S14 late | Performance + cutover rehearsal | Loads in cutover window; reconciliation passes |

# 7. Cutover migration plan

| Activity | Time (hrs) | Owner |
| --- | --- | --- |
| Master data freeze in Oracle EBS | T-5 days | Commercial Director (lock customer maintenance) |
| Final delta extract — customer master | T-1 18:00 | SI Data Migration Lead |
| Master customer load to D365 | T0 00:30 (4 hrs) | SI Data Migration Lead |
| Open AR load (open invoices, credit notes) | T0 04:30 (3 hrs) | SI Data Migration Lead |
| Reconciliation run | T0 08:00 (1 hr) | SI Data Migration Lead + Group FC for sign-off |
| Sample functional walk | T0 09:00 (3 hrs) | Commercial team — 25-customer sample |
| Sign-off & release for go/no-go #1 | T0 14:00 | Data Owner + Group FC |

# 8. Risks

| Risk | Mitigation |
| --- | --- |
| Mock load 1 reveals significant duplicate population | Cleansing pod sized to handle 5%+ duplicate rate |
| Open AR balances drift between extract and load | Use exact-time delta extract; reconcile to penny |
| Customer hierarchy parent missing | Validate hierarchies in source pre-migration; fix in source |
| Address quality below threshold | Geo-validation tool deployed at S13; cleanse pre-mock-load-2 |
| Cleansing not complete by mock load 3 | Tracked weekly to Data Owner; escalate to SteerCo if slipping |

# 9. Sign-off

| Role | Name | Date |
| --- | --- | --- |
| Data Owner (Commercial Director) |  |  |
| SI Data Migration Lead |  |  |
| Group Financial Controller (AR) |  |  |
| Solution Architect |  |  |
| Design Authority |  |  |