Operating Model & Service Wrap

Stages 17-18. Post go-live support model: L1/L2/L3, escalation, SLA, SI exit, transition to BAU.

| Document | Operating Model & Service Wrap |
| --- | --- |
| Version | v1.0 |
| Date | April 2026 |
| Owner | Programme Manager (transitioning to IT Service Director at S19) |
| Classification | Programme Use |

# 1. Purpose

Defines how the new ERP is supported once the programme ends. Approved by SteerCo at Hypercare & Stabilisation (S17) entry. Operationalised through Stages 17–19. Re-baselined annually as part of the Optimisation & Maturity (S19) optimisation cycle.

# 2. Three-tier support model

| Tier | Responsibility | Provided by | Hours |
| --- | --- | --- | --- |
| L1 | First-point-of-contact; password resets; how-to questions; ticket routing | Internal Service Desk (ServiceNow) | 06:00-20:00 UK Mon-Fri; weekend on-call |
| L2 | Functional configuration changes; investigation of business issues; routine fixes | Internal Centre of Excellence (CoE) — 6 FTE: 2 finance, 2 supply chain, 1 commercial, 1 BI | 08:00-18:00 UK; on-call rota |
| L3 | Code-level fixes; complex configuration; integration issues; vendor escalation | SI managed service (Years 1-2) → blended client+SI from Year 3 | Per SLA below |

# 3. Centre of Excellence (CoE)

The CoE is the heart of the operating model. It is staffed during S17 from a combination of programme team members (super users converted to CoE) and lateral transfers. Its remit:

L2 incident & request resolution

Continuous improvement backlog (small enhancements; feeds S19 optimisation cycle)

Master data governance ownership (with business Data Owners)

Training material maintenance and new-starter onboarding

Period-close support for finance

Vendor management (Microsoft, ISVs) — partnered with IT Service Director

# 4. SLA framework

| Severity | Definition | Response | Resolution target |
| --- | --- | --- | --- |
| P1 — Critical | Production down or major business function unavailable | 15 min | 4 hrs |
| P2 — High | Significant functional issue; workaround possible | 1 hr | 1 working day |
| P3 — Medium | Functional issue with workaround | 1 working day | 5 working days |
| P4 — Low | Cosmetic / nice-to-have / how-to | 2 working days | 20 working days |
| Service Request | Standard request (access, report, etc.) | 1 working day | 10 working days |

# 5. SI exit & transition

The SI's role transitions deliberately and contractually through Stages 17–19:

| Stage | SI involvement | Internal capability |
| --- | --- | --- |
| Stage 17 (Hypercare, 4-8 weeks) | Full team on-site / on-call; SI leads L3 | CoE shadowing + receiving knowledge transfer |
| Stage 18 (Months 3-6) | L3 only via managed service contract; ad-hoc CoE coaching | CoE owns L2; KT formal sign-off at month 6 |
| S19 onwards (Year 1+) | L3 via SLA-backed managed service; quarterly partnership review | CoE fully L2 capable; selects which L3 to insource |
| Year 3+ | Optional managed service renewal; or blended internal+SI L3 | CoE fully self-sufficient for L2 + 60-70% of L3 |

# 6. Knowledge transfer plan

Knowledge transfer (KT) starts at Testing (S14) and runs through S17. Tracked formally with a KT Tracker in the CoE backlog tool.

Pair-walking: every SI Functional Lead pairs with a CoE counterpart through Stages 14-17

Documentation: SI produces operational runbooks per process; signed off by CoE before S17 close

Test capability: CoE runs the regression suite for the first cycle of post-go-live changes

Shadowing: CoE attends every L3 ticket with SI through Hypercare

Solo runs: CoE solo-resolves at least 10 L2 tickets and 3 L3 tickets before SI exit

# 7. Governance — post-programme

| Forum | Cadence | Purpose |
| --- | --- | --- |
| ERP Operations Forum | Monthly | L1/L2/L3 incident review, change calendar, capacity planning |
| Data Governance Council | Quarterly | Master data quality KPIs; emerging issues |
| Vendor Partnership Review | Quarterly | SI managed service performance vs SLA; Microsoft roadmap |
| Optimisation Backlog Review | Quarterly | Continuous improvement priorities; feeds S19 |
| Annual Operating Model Review | Annual | Re-baseline of this document |

# 8. Costs (run rate, Year 1 — illustrative)

| Item | Cost (£k pa) |
| --- | --- |
| CoE FTE (6 people, fully loaded) | 780 |
| Service Desk capacity uplift (1.5 FTE) | 75 |
| SI managed service (L3, Year 1) | 320 |
| Microsoft licences (run rate) | 595 |
| Cloud subscription consumption | 165 |
| Tooling — monitoring, ITSM uplift | 60 |
| Annual Microsoft updates support | 40 |
| Total | 2,035 |

# 9. Continuous improvement

The CoE owns a backlog of optimisation items, sized in the same story-point framework as the build phase. Quarterly release cycle, deployed via the same ALM toolchain. Annual budget envelope agreed by SteerCo (transitioning to IT Investment Forum at S19).

# 10. Key risks

| Risk | Mitigation |
| --- | --- |
| CoE under-staffed at S17 close | FTE plan signed off at S14; recruitment starts Build & Configuration (S13) |
| KT incomplete — SI exits with knowledge gaps | Solo-run criterion gates SI exit; explicit sign-off required |
| L3 SLA breach in first 3 months | Daily incident review with SI through Benefits Realisation & Review (S18); escalation to SI Programme Director |
| Continuous improvement budget cut | Ring-fenced as % of run cost; reaffirmed at annual review |
| Microsoft platform updates introduce regressions | Regression suite run before each environment update; Microsoft early-access programme |