## Cover
Stakeholder Map
Companion to the Communications & Engagement Plan
How to use this workbook
Captures every named stakeholder with influence/interest scoring, current attitude, target attitude, comms approach and owner. Refreshed monthly by the Change Lead. The Influence x Interest grid drives the engagement strategy: who do we manage closely, keep satisfied, keep informed, or just monitor.

## Stakeholders
Stakeholder Register
Influence (1-5), Interest (1-5). Attitude: Champion / Supporter / Neutral / Sceptic / Blocker.
# | Name / Role | Function | Influence (1-5) | Interest (1-5) | Quadrant | Current attitude | Target attitude | Approach | Engagement owner | Last contact | Next action
1 | CEO | Executive | 5 | 4 | Manage closely | Supporter | Champion | Bilateral monthly + town halls | Sponsor | 2026-04-15 | Pre-Gate 2 1:1 — discuss FBC sign-off
2 | CFO (Sponsor) | Finance | 5 | 5 | Manage closely | Champion | Champion | Programme Sponsor — chairs ESG | n/a | 2026-04-22 | ESG 28-Apr
3 | CIO | IT | 5 | 5 | Manage closely | Champion | Champion | Bilateral 2-weekly with Programme Mgr | Programme Manager | 2026-04-19 | Architecture review 02-May
4 | COO | Operations | 5 | 4 | Manage closely | Supporter | Champion | Bilateral monthly + Wave 2 town hall | Sponsor | 2026-04-10 | Bilateral 12-May
5 | Group Financial Controller | Finance | 4 | 5 | Manage closely | Champion | Champion | Process Owner forum + finance bilateral | Change Lead | 2026-04-22 | Mock load 1 review
6 | CPO (Procurement) | Procurement | 4 | 5 | Manage closely | Supporter | Champion | Process Owner forum + bilateral | Change Lead | 2026-04-18 | Catalogue scope decision
7 | Commercial Director | Commercial | 4 | 4 | Manage closely | Neutral | Supporter | Bilateral + Wave 2 town hall | Sponsor | 2026-03-30 | OTC walkthrough — bring forward
8 | Supply Chain Director | Supply Chain | 4 | 5 | Manage closely | Champion | Champion | Process Owner forum + bilateral | Change Lead | 2026-04-21 | WMS go-live readiness
9 | Group HRD | HR | 4 | 2 | Keep satisfied | Neutral | Supporter | Quarterly summary; engaged on integration | Change Lead | 2026-02-28 | HR integration sign-off
10 | Chair of Board | Board | 5 | 2 | Keep satisfied | Neutral | Supporter | Monthly summary via Sponsor | Sponsor | 2026-04-01 | Pre-Gate 2 board paper
11 | Audit Committee Chair | Board | 4 | 3 | Keep satisfied | Sceptic | Neutral | Quarterly summary; SoX evidence focus | Sponsor | 2026-03-15 | Compliance walkthrough — Wk 4 of UAT
12 | External Auditor (Big-4 partner) | External | 3 | 3 | Monitor | Neutral | Neutral | Quarterly briefing; included in audit walkthrough | Group FC | 2026-03-15 | Q2 audit walkthrough
13 | BU Head — UK | BU | 4 | 4 | Manage closely | Supporter | Champion | BU briefing + monthly bilateral | Change Lead | 2026-04-19 | BU readiness assessment 1
14 | BU Head — ROI | BU | 4 | 4 | Manage closely | Sceptic | Supporter | BU briefing + monthly bilateral; concerns on data residency | Change Lead | 2026-04-12 | Data residency walkthrough — overdue
15 | BU Head — Germany | BU | 4 | 3 | Keep satisfied | Neutral | Supporter | BU briefing in DE; localisation decisions | Change Lead | 2026-04-08 | Localisation review 06-May
16 | AP Manager | Finance | 2 | 5 | Keep informed | Champion | Champion | Process Owner forum; AP Hub demo | Change Lead | 2026-04-22 | Pre-UAT briefing
17 | AR Manager | Finance | 2 | 5 | Keep informed | Supporter | Champion | Process Owner forum | Change Lead | 2026-04-22 | Dunning workflow review
18 | Service Desk Lead | IT | 2 | 4 | Keep informed | Neutral | Supporter | Weekly L1 readiness briefing from Stage 14 | Change Lead | 2026-04-22 | L1 script walkthrough — week of 06-May
19 | Top customer #1 (key account) | External | 4 | 2 | Keep satisfied | Neutral | Neutral | Wave 4 letter + KAM bilateral | Commercial Director | n/a | EDI cutover walkthrough
20 | Key supplier — top 5 | External | 2 | 2 | Monitor | Neutral | Neutral | Wave 4 letter + Procurement bilateral | CPO | n/a | Remittance change letter
21 | Microsoft (Vendor) | External | 3 | 4 | Keep informed | Champion | Champion | Quarterly partnership review + cutover support | SI PD | 2026-04-08 | Cutover support contract
22 | SI Programme Director | External | 4 | 5 | Manage closely | Champion | Champion | Daily standup + weekly SteerCo | Programme Manager | 2026-04-22 | Weekly 1:1
23 | Internal Audit | Audit | 3 | 4 | Keep informed | Sceptic | Neutral | Quarterly walkthrough; SoX focus | Group FC | 2026-04-08 | SoX matrix review
24 | Workers Council (Germany) | Internal | 3 | 3 | Monitor | Sceptic | Neutral | Quarterly briefing + early consultation on role changes | BU Head — Germany | 2026-03-25 | Role change consultation — overdue

## Influence x Interest grid
Influence x Interest Grid
Counts pulled live from Stakeholders sheet. 5x5 = top-right quadrant 'Manage closely'.
| Interest --> | 1 Low | 2 | 3 | 4 | 5 High
Influence | 5 High | 0 | 1 | 0 | 2 | 2
| 4 | 0 | 2 | 2 | 3 | 4
| 3 | 0 | 0 | 2 | 2 | 0
| 2 | 0 | 1 | 0 | 1 | 2
| 1 Low | 0 | 0 | 0 | 0 | 0
Legend
| Manage closely | High influence + high interest. Bilateral cadence, deep engagement.
| Keep satisfied | High influence, lower interest. Don't surprise; periodic summary.
| Keep informed | Lower influence, high interest. Channels rather than 1:1s.
| Monitor | Lower influence + lower interest. Broadcast comms only.