## Slide 1
Executive Sponsor Group
ERP Programme — Pack Template
Body: Executive Sponsor Group (ESG)
Cadence: As required, plus every phase gate (Stage 6, Stage 12, Stage 16)
Audience: Executive Sponsor + named CxO members. NOT a wider exec audience.
Reporting period: [Month YYYY] | Pack version: vX.0 | Owner: Programme Manager

## Slide 2
Agenda
60-minute slot — exec briefing format
1.
Headlines & decisions needed
5 min
Sponsor
2.
Programme status — RAG, time, cost, benefit
10 min
Programme Manager
3.
Top risks (Red & escalating Amber)
10 min
Programme Manager
4.
Gate decision / commercial decision
20 min
As required
5.
Look ahead and decisions for next session
10 min
Sponsor
6.
Any other business
5 min
Sponsor
ESG | [Date]
2 / 10

## Slide 3
Headlines
Read this in 60 seconds
Overall RAG
[ G / A / R ]
Programme on plan to current Stage XX exit
Schedule
[on plan / +/- N wks]
Forecast against next gate
Cost
[on FBC / +/- N% of £X.Xm]
Forecast at completion vs FBC
Benefit
[on plan / at risk]
Top benefit at risk: [example]
Top decision
[Y / N]
[1-line of decision needed today]
ESG | [Date]
3 / 10

## Slide 4
Where we are in the lifecycle
Six phases. Twenty stages. Two gates.
Pre- Programme
S0–5
Selection
S6–9
Setup & Design
S10–12
Build & Test
S13–14
Deploy
S15–17
Post- Programme
S18–19
GATE 1 — Stage 6
GATE 2 — Stage 12
Currently at: [Stage XX — Stage Name]
Stage exit criteria: [list 3-5 criteria, with current status against each]
Forecast to next gate: [date] | Variance: [+/- weeks]
ESG | [Date]
4 / 10

## Slide 5
Top risks — Red and escalating Amber
From the RAID log; full register available in the workbook
#
Risk
L
I
Score
Owner
Mitigation
Status
1
[Risk text — concrete, current]
4
5
20
[Owner]
[Mitigation in flight + escalation route]
Red
2
[Risk text]
4
4
16
[Owner]
[Mitigation]
Red
3
[Risk text]
3
5
15
[Owner]
[Mitigation]
Red
4
[Risk text]
3
4
12
[Owner]
[Mitigation]
Amber↑
5
[Risk text]
3
4
12
[Owner]
[Mitigation]
Amber↑
ESG | [Date]
5 / 10

## Slide 6
Decisions needed today
Frame each as a question with a recommendation
D1
[Decision question]
Recommendation: [Recommendation — clear yes/no/option]
Owner: [Owner] Decision by: [By when]
D2
[Decision question]
Recommendation: [Recommendation]
Owner: [Owner] Decision by: [By when]
D3
[Decision question]
Recommendation: [Recommendation]
Owner: [Owner] Decision by: [By when]
ESG | [Date]
6 / 10

## Slide 7
Financial view
FBC at Stage 12: ±10–15%. Forecast at completion vs FBC.
Category
FBC budget (£m)
Spent to date
Committed
Forecast EAC
Variance
RAG
Software
Implementation (SI)
Programme (Client)
Infrastructure
Other
Contingency
TOTAL
ESG | [Date]
7 / 10

## Slide 8
Benefits trajectory
Pre-Stage 18: forecast vs FBC. Stage 18+: realised.
#
Benefit
Owner
Target (£k/yr)
Trajectory / actual
RAG
B-01
DSO reduction
CFO
1,800
[Forecast / actual]
G
B-02
Inventory write-down
Supply Chain Dir
950
G
B-03
Indirect spend
CPO
1,400
A
B-04
Finance close
Group FC
480
G
B-05
OTC
Commercial Dir
720
G
B-06
Audit savings
Audit
220
G
B-07
AP / SSC automation
SSC Dir
540
A
B-08
Decision support
CIO
300
G
ESG | [Date]
8 / 10

## Slide 9
Look ahead — next 90 days
Key milestones, decisions and risk events
Three-month rolling outlook
Month +1
Key milestones:
• [Milestone 1]
• [Milestone 2]
• [Milestone 3]
Decisions to be taken:
• [Decision 1]
• [Decision 2]
Risk events watched:
• [Risk event]
Month +2
Key milestones:
• [Milestone 1]
• [Milestone 2]
• [Milestone 3]
Decisions to be taken:
• [Decision 1]
• [Decision 2]
Risk events watched:
• [Risk event]
Month +3
Key milestones:
• [Milestone 1]
• [Milestone 2]
• [Milestone 3]
Decisions to be taken:
• [Decision 1]
• [Decision 2]
Risk events watched:
• [Risk event]
ESG | [Date]
9 / 10

## Slide 10
Decisions taken & actions out
Captured by ESG secretary at the end of the meeting
#
Decision / Action
Owner
Due
Status
ESG | [Date]
10 / 10